## README
Server Test Practice Data
Fictional EVT / DVT / PVT validation data for three server projects. Every name, number and problem is invented for practice. It is not real Wistron data.
The situation
You are the new product manager. Leadership says 'testing has a lot of problems' and wants to know why, and what to do next. The data covers 2026-06-01 to 2026-09-25.
Projects
ORION-2U – general-purpose 2U, 2-socket server. Now in PVT.
VEGA-1U – dense 1U compute server. In DVT, past its planned exit date.
LYRA-4U – 4U GPU server. EVT finished late; now in DVT.
Sheets
Exercises – 10 practice questions, from easy to PM-level. Answers are in the separate Answer_Key.md file.
test_runs – one row per test run (2,885 rows). Result = Pass / Fail.
issue_log – one row per failed run, logged as an issue (250 rows). Has a few messy rows on purpose.
thermal_log – temperatures and fan duty for thermal tests. Join to test_runs on Run_ID.
schedule – planned vs actual dates for each build stage, with exit criteria.
Build stages
EVT = Engineering Validation Test (工程驗證) · DVT = Design Validation Test (設計驗證) · PVT = Production Validation Test (生產驗證), the last step before mass production (量產).
Same data, other tools
CSV files for Power BI / Python and server_test.db for SQL (SQLite, same four tables) come with this workbook.

## Exercises
Level | # | Question | Suggested tool | Sheets | Hint
1 · Clean | 1 | Clean the issue_log. Fix Project names that are not in upper case, trim and standardize Test_Category, and fill in blank Owner_Dept values. How many rows did you fix for each problem? | Excel: TRIM, UPPER, filters. Power Query also works. | issue_log | Filter each column and look at the unique values. For a blank owner, use the Root_Cause_Category and the pattern in other rows to decide who owns it.
1 · Clean | 2 | Calculate the test pass rate (Pass runs ÷ all runs) for each Project × Build_Stage. Which stages miss the exit-criteria target in the schedule sheet? | Excel pivot table, or GROUP BY in SQL | test_runs, schedule | Targets: EVT ≥ 85%, DVT ≥ 92%, PVT ≥ 97%.
1 · Clean | 3 | How many issues are still open (Status is not Closed), by Project and Severity? For the open Critical issues, how many different root causes are there? | Pivot table | issue_log (cleaned) | Count issues, then group the open Critical ones by Root_Cause_Note. Many issues can be one real problem.
2 · Find the pattern | 4 | Compare the failure rate of each test station (ST-01 to ST-10, not the thermal chambers). Which station stands out? When did it start and stop, and what do its issues say the root cause is? | Pivot + filter by date, or SQL JOIN | test_runs, issue_log | Join issue_log to test_runs on Run_ID to get the Station. Look at Root_Cause_Category before and after 2026-08-12.
2 · Find the pattern | 5 | For the 'Memtest stress 12h' test, compare the failure rate by DIMM_Lot. Which lot is the problem, and which project uses it most? | Pivot table | test_runs | Compare each lot's failure rate with the others, not just the count of failures.
2 · Find the pattern | 6 | For Thermal tests, compare the failure rate, average fan duty and average CPU temperature by BMC_FW version. What happened, and did the fix work? | SQL JOIN or Excel XLOOKUP / INDEX-MATCH | test_runs, thermal_log | Filter on Failure_Symptom = 'Fan speed not responding'.
2 · Find the pattern | 7 | For LYRA-4U thermal tests, compare the failure rate, average GPU temperature and number of GPU throttle events by Ambient_C (25 / 30 / 35 °C). Is this a firmware problem or a design problem? | Pivot or Python groupby; a chart helps | test_runs, thermal_log | GPU throttles at 87 °C. Check whether failures still happen after the BMC fix (BMC_FW 2.3.4).
3 · PM decisions | 8 | For closed issues, what is the average and median days to close for each Root_Cause_Category? How many open issues are older than 30 days (as of 2026-09-25), and which departments own them? | Excel date math, Power BI | issue_log (cleaned) | Days to close = Close_Date − Open_Date. Age of open issue = 2026-09-25 − Open_Date.
3 · PM decisions | 9 | For each project stage, calculate the schedule slip in days (actual end − planned end). For stages still running, how many days past the planned end are they? Link each delay to the problem that caused it. | Excel, Gantt chart in Power BI | schedule, plus answers 4–7 | Use 2026-09-25 as today for stages with no Actual_End.
3 · PM decisions | 10 | Write a short weekly status for leadership, in Chinese: one line per project with a Red / Yellow / Green status, the top problem, the owner, and the next action with a date. | Your own words; use the vocab page | All | Useful words: 進度, 延遲, 風險, 根本原因, 負責單位, 預計完成, 待辦事項. Example: 「LYRA-4U：紅燈。GPU 散熱不足…」

## test_runs
Run_ID | Test_Date | Shift | Project | Build_Stage | Unit_SN | Station | Test_Category | Test_Item | Result | Failure_Symptom | Duration_min | Ambient_C | BMC_FW | BIOS_Ver | DIMM_Vendor | DIMM_Lot
R00001 | 2026-06-01 | Night | ORION-2U | EVT | ORI-E-0011 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00002 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0015 | ST-01 | Memory | Memtest stress 12h | Pass |  | 786 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00003 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0021 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00004 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0009 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 35 | 2.2.8 | O1.02 | Dramtek | D2606
R00005 | 2026-06-01 | Night | ORION-2U | EVT | ORI-E-0002 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00006 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0005 | ST-05 | Memory | ECC injection | Pass |  | 747 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00007 | 2026-06-01 | Night | ORION-2U | EVT | ORI-E-0017 | ST-02 | Network | NIC throughput 100G | Fail | Throughput below spec | 26 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00008 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 165 | 30 | 2.2.8 | O1.02 | Dramtek | D2606
R00009 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0017 | TC-02 | Thermal | Thermal chamber | Pass |  | 162 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00010 | 2026-06-01 | Day | ORION-2U | EVT | ORI-E-0014 | ST-09 | Storage | NVMe hot-plug | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00011 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0001 | ST-09 | Storage | FIO random R/W | Pass |  | 63 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00012 | 2026-06-02 | Night | ORION-2U | EVT | ORI-E-0021 | ST-02 | Storage | FIO random R/W | Pass |  | 58 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00013 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0009 | ST-09 | Storage | NVMe hot-plug | Pass |  | 63 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00014 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0019 | ST-10 | Storage | NVMe hot-plug | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00015 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0020 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00016 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0021 | ST-09 | Memory | ECC injection | Pass |  | 664 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00017 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0012 | ST-03 | Storage | NVMe hot-plug | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00018 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0022 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00019 | 2026-06-02 | Night | ORION-2U | EVT | ORI-E-0016 | ST-05 | Storage | NVMe hot-plug | Pass |  | 57 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00020 | 2026-06-02 | Night | ORION-2U | EVT | ORI-E-0008 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00021 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0001 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00022 | 2026-06-02 | Night | ORION-2U | EVT | ORI-E-0019 | ST-07 | Network | Link flap test | Pass |  | 60 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00023 | 2026-06-02 | Night | ORION-2U | EVT | ORI-E-0020 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00024 | 2026-06-02 | Day | ORION-2U | EVT | ORI-E-0009 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00025 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0020 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2730 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00026 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0006 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 231 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00027 | 2026-06-03 | Night | ORION-2U | EVT | ORI-E-0020 | ST-05 | Storage | FIO random R/W | Fail | IOPS below spec | 32 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00028 | 2026-06-03 | Night | ORION-2U | EVT | ORI-E-0012 | ST-04 | Memory | Memtest stress 12h | Pass |  | 649 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00029 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0008 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00030 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0014 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00031 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0016 | ST-10 | Network | NIC throughput 100G | Pass |  | 61 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00032 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0011 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00033 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0004 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00034 | 2026-06-03 | Night | ORION-2U | EVT | ORI-E-0024 | ST-02 | Memory | Memtest stress 12h | Pass |  | 719 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00035 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0002 | ST-07 | Storage | NVMe hot-plug | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00036 | 2026-06-03 | Night | ORION-2U | EVT | ORI-E-0021 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2834 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00037 | 2026-06-03 | Day | ORION-2U | EVT | ORI-E-0015 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00038 | 2026-06-03 | Night | ORION-2U | EVT | ORI-E-0004 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00039 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 197 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00040 | 2026-06-04 | Night | ORION-2U | EVT | ORI-E-0021 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00041 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0010 | ST-10 | Memory | ECC injection | Fail | Error not logged in SEL | 159 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00042 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0018 | ST-08 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 1845 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00043 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0011 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00044 | 2026-06-04 | Night | ORION-2U | EVT | ORI-E-0018 | ST-06 | Network | NIC throughput 100G | Pass |  | 65 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00045 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0024 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 262 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00046 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0015 | ST-01 | Memory | ECC injection | Pass |  | 754 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00047 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0019 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00048 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0015 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00049 | 2026-06-04 | Day | ORION-2U | EVT | ORI-E-0019 | ST-09 | Network | NIC throughput 100G | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00050 | 2026-06-05 | Day | ORION-2U | EVT | ORI-E-0024 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00051 | 2026-06-05 | Day | ORION-2U | EVT | ORI-E-0020 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00052 | 2026-06-05 | Night | ORION-2U | EVT | ORI-E-0003 | ST-04 | Storage | NVMe hot-plug | Pass |  | 59 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00053 | 2026-06-05 | Day | ORION-2U | EVT | ORI-E-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00054 | 2026-06-05 | Night | ORION-2U | EVT | ORI-E-0012 | ST-04 | Memory | Memtest stress 12h | Pass |  | 678 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00055 | 2026-06-05 | Night | ORION-2U | EVT | ORI-E-0022 | ST-08 | Network | NIC throughput 100G | Pass |  | 58 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00056 | 2026-06-05 | Day | ORION-2U | EVT | ORI-E-0019 | ST-10 | Storage | FIO random R/W | Pass |  | 65 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00057 | 2026-06-05 | Night | ORION-2U | EVT | ORI-E-0006 | ST-03 | Storage | NVMe hot-plug | Pass |  | 55 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00058 | 2026-06-05 | Night | ORION-2U | EVT | ORI-E-0014 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00059 | 2026-06-06 | Night | ORION-2U | EVT | ORI-E-0006 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00060 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0012 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 51 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00061 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0018 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2976 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00062 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0011 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00063 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0022 | ST-09 | Memory | ECC injection | Pass |  | 718 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00064 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0009 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00065 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0015 | ST-04 | Memory | Memtest stress 12h | Pass |  | 729 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00066 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0022 | ST-01 | Memory | Memtest stress 12h | Pass |  | 764 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00067 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0018 | ST-09 | Memory | Memtest stress 12h | Pass |  | 767 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00068 | 2026-06-06 | Day | ORION-2U | EVT | ORI-E-0013 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00069 | 2026-06-07 | Night | ORION-2U | EVT | ORI-E-0019 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 225 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00070 | 2026-06-07 | Night | ORION-2U | EVT | ORI-E-0024 | ST-09 | Memory | ECC injection | Pass |  | 672 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00071 | 2026-06-07 | Night | ORION-2U | EVT | ORI-E-0008 | ST-04 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 544 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00072 | 2026-06-07 | Night | ORION-2U | EVT | ORI-E-0020 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2654 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00073 | 2026-06-08 | Day | ORION-2U | EVT | ORI-E-0005 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2838 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00074 | 2026-06-08 | Day | ORION-2U | EVT | ORI-E-0002 | ST-08 | Network | NIC throughput 100G | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00075 | 2026-06-08 | Night | ORION-2U | EVT | ORI-E-0004 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00076 | 2026-06-08 | Day | ORION-2U | EVT | ORI-E-0012 | ST-06 | Storage | FIO random R/W | Pass |  | 60 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00077 | 2026-06-08 | Night | ORION-2U | EVT | ORI-E-0020 | ST-02 | Memory | ECC injection | Pass |  | 769 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00078 | 2026-06-08 | Night | ORION-2U | EVT | ORI-E-0007 | ST-04 | Storage | FIO random R/W | Fail | IOPS below spec | 44 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00079 | 2026-06-08 | Night | ORION-2U | EVT | ORI-E-0014 | ST-10 | Network | NIC throughput 100G | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00080 | 2026-06-09 | Night | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 190 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00081 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0006 | ST-02 | Network | Link flap test | Pass |  | 54 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00082 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0014 | ST-06 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00083 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0007 | ST-01 | Memory | ECC injection | Pass |  | 671 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00084 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0018 | ST-05 | Network | NIC throughput 100G | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00085 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0020 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00086 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 183 | 35 | 2.2.8 | O1.02 | Dramtek | D2606
R00087 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0002 | ST-09 | Storage | FIO random R/W | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00088 | 2026-06-09 | Night | ORION-2U | EVT | ORI-E-0019 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 240 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00089 | 2026-06-09 | Night | ORION-2U | EVT | ORI-E-0008 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 247 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00090 | 2026-06-09 | Day | ORION-2U | EVT | ORI-E-0019 | TC-02 | Thermal | Thermal chamber | Pass |  | 175 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00091 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0001 | TC-02 | Thermal | Thermal chamber | Pass |  | 180 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00092 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0006 | ST-10 | Network | Link flap test | Pass |  | 56 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00093 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0008 | ST-08 | Storage | NVMe hot-plug | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00094 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0018 | TC-01 | Thermal | Thermal chamber | Pass |  | 171 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00095 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0002 | ST-02 | Network | NIC throughput 100G | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00096 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0024 | TC-01 | Thermal | Thermal chamber | Pass |  | 174 | 35 | 2.2.8 | O1.02 | Dramtek | D2606
R00097 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0004 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 229 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00098 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0006 | ST-09 | Storage | NVMe hot-plug | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00099 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0011 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00100 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Thermal chamber | Pass |  | 190 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00101 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0023 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 231 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00102 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0001 | ST-04 | Memory | ECC injection | Pass |  | 722 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00103 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0021 | TC-02 | Thermal | Thermal chamber | Pass |  | 174 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00104 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0010 | ST-03 | Storage | FIO random R/W | Fail | IOPS below spec | 20 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00105 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 166 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00106 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0007 | ST-04 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 21 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00107 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 167 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00108 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0023 | ST-05 | Memory | Memtest stress 12h | Pass |  | 773 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00109 | 2026-06-10 | Night | ORION-2U | EVT | ORI-E-0012 | ST-10 | Network | NIC throughput 100G | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00110 | 2026-06-10 | Day | ORION-2U | EVT | ORI-E-0019 | ST-05 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 136 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00111 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0009 | ST-09 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00112 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0024 | ST-04 | Storage | NVMe hot-plug | Pass |  | 57 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00113 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0014 | ST-03 | Power-on/POST | DC cycle 500x | Fail | No POST | 12 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00114 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0011 | ST-02 | Storage | NVMe hot-plug | Pass |  | 56 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00115 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0022 | ST-06 | Network | Link flap test | Pass |  | 61 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00116 | 2026-06-11 | Night | ORION-2U | EVT | ORI-E-0010 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2645 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00117 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0023 | TC-01 | Thermal | Thermal chamber | Pass |  | 183 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00118 | 2026-06-11 | Night | ORION-2U | EVT | ORI-E-0010 | ST-10 | Memory | ECC injection | Pass |  | 765 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00119 | 2026-06-11 | Day | ORION-2U | EVT | ORI-E-0014 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3163 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00120 | 2026-06-11 | Night | ORION-2U | EVT | ORI-E-0020 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00121 | 2026-06-11 | Night | ORION-2U | EVT | ORI-E-0011 | ST-06 | Network | Link flap test | Pass |  | 56 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00122 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0021 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 65 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00123 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0008 | ST-10 | Network | NIC throughput 100G | Pass |  | 64 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00124 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0005 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 256 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00125 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0016 | TC-01 | Thermal | Thermal chamber | Pass |  | 187 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00126 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0019 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00127 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0021 | ST-05 | Memory | Memtest stress 12h | Pass |  | 673 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00128 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0002 | ST-07 | Storage | NVMe hot-plug | Pass |  | 56 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00129 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0017 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2826 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00130 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0019 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 232 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00131 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0009 | ST-07 | Network | Link flap test | Pass |  | 62 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00132 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0014 | TC-01 | Thermal | Thermal chamber | Pass |  | 182 | 30 | 2.2.8 | O1.02 | MemCo-A | A2605
R00133 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0007 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2747 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00134 | 2026-06-12 | Night | ORION-2U | EVT | ORI-E-0007 | TC-02 | Thermal | Thermal chamber | Pass |  | 181 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00135 | 2026-06-12 | Day | ORION-2U | EVT | ORI-E-0015 | ST-01 | Memory | Memtest stress 12h | Pass |  | 709 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00136 | 2026-06-13 | Night | ORION-2U | EVT | ORI-E-0013 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00137 | 2026-06-13 | Night | ORION-2U | EVT | ORI-E-0019 | ST-09 | Memory | ECC injection | Pass |  | 768 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00138 | 2026-06-13 | Day | ORION-2U | EVT | ORI-E-0004 | ST-05 | Memory | ECC injection | Pass |  | 754 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00139 | 2026-06-13 | Day | ORION-2U | EVT | ORI-E-0017 | ST-09 | Memory | Memtest stress 12h | Pass |  | 740 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00140 | 2026-06-14 | Day | ORION-2U | EVT | ORI-E-0024 | ST-04 | Memory | ECC injection | Pass |  | 757 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00141 | 2026-06-14 | Night | ORION-2U | EVT | ORI-E-0018 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3159 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00142 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0004 | ST-01 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 46 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00143 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0009 | ST-09 | Network | Link flap test | Pass |  | 57 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00144 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0016 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2614 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00145 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0002 | ST-09 | Memory | ECC injection | Pass |  | 656 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00146 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0012 | ST-03 | Network | Link flap test | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00147 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0007 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3067 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00148 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0014 | ST-07 | Storage | NVMe hot-plug | Pass |  | 65 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00149 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0006 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00150 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0005 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00151 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0018 | ST-05 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 63 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00152 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0005 | ST-02 | Network | Link flap test | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00153 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0005 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00154 | 2026-06-15 | Night | ORION-2U | EVT | ORI-E-0008 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00155 | 2026-06-15 | Day | ORION-2U | EVT | ORI-E-0015 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3060 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00156 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3021 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00157 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00158 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00159 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-01 | Memory | ECC injection | Pass |  | 749 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00160 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-10 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 449 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00161 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-07 | Memory | ECC injection | Pass |  | 674 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00162 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00163 | 2026-06-15 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00164 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-05 | Storage | NVMe hot-plug | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00165 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00166 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00167 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00168 | 2026-06-15 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3039 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00169 | 2026-06-15 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00170 | 2026-06-16 | Night | ORION-2U | EVT | ORI-E-0008 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00171 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0008 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00172 | 2026-06-16 | Night | ORION-2U | EVT | ORI-E-0021 | ST-05 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00173 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 172 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00174 | 2026-06-16 | Night | ORION-2U | EVT | ORI-E-0023 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00175 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0011 | ST-08 | Storage | NVMe hot-plug | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00176 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0023 | ST-04 | Network | Link flap test | Pass |  | 55 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00177 | 2026-06-16 | Night | ORION-2U | EVT | ORI-E-0001 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3164 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00178 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0009 | ST-01 | Memory | ECC injection | Pass |  | 699 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00179 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0016 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2644 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00180 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0010 | ST-03 | Memory | ECC injection | Pass |  | 701 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00181 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0002 | ST-01 | Network | NIC throughput 100G | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00182 | 2026-06-16 | Night | ORION-2U | EVT | ORI-E-0006 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00183 | 2026-06-16 | Day | ORION-2U | EVT | ORI-E-0016 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00184 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00185 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 252 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00186 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00187 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-01 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00188 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 260 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00189 | 2026-06-16 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-02 | Memory | Memtest stress 12h | Pass |  | 663 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00190 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00191 | 2026-06-16 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-06 | Network | NIC throughput 100G | Pass |  | 54 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00192 | 2026-06-16 | Night | VEGA-1U | EVT | VEG-E-0009 | TC-02 | Thermal | Thermal chamber | Pass |  | 168 | 30 | 2.2.8 | V1.02 | MemCo-A | A2605
R00193 | 2026-06-16 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00194 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0007 | ST-08 | Network | NIC throughput 100G | Fail | Throughput below spec | 40 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00195 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0008 | ST-08 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00196 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0003 | ST-08 | Storage | FIO random R/W | Pass |  | 54 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00197 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0018 | ST-02 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00198 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0014 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 186 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00199 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0018 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 220 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00200 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0022 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2741 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00201 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0012 | TC-01 | Thermal | Thermal chamber | Pass |  | 191 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00202 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0006 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 243 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00203 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0016 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 64 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00204 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0005 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3080 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00205 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0005 | ST-09 | Storage | FIO random R/W | Pass |  | 65 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00206 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0010 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2840 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00207 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Thermal chamber | Pass |  | 175 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00208 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0018 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00209 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0022 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00210 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0012 | ST-06 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 47 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00211 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0004 | ST-04 | Network | NIC throughput 100G | Pass |  | 64 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00212 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0002 | TC-01 | Thermal | Thermal chamber | Pass |  | 167 | 30 | 2.2.8 | O1.02 | MemCo-A | A2607
R00213 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0018 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2888 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00214 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0020 | ST-08 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 40 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00215 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0006 | ST-08 | Network | Link flap test | Pass |  | 58 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00216 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0024 | ST-10 | Network | Link flap test | Pass |  | 64 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00217 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0003 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2898 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00218 | 2026-06-17 | Day | ORION-2U | EVT | ORI-E-0003 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00219 | 2026-06-17 | Night | ORION-2U | EVT | ORI-E-0024 | ST-05 | Network | Link flap test | Fail | Link down | 26 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00220 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-05 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00221 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-10 | Network | NIC throughput 100G | Pass |  | 56 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00222 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 258 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00223 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0015 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2986 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00224 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-07 | Network | Link flap test | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00225 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-03 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00226 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-01 | Storage | FIO random R/W | Pass |  | 57 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00227 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-05 | Memory | ECC injection | Pass |  | 728 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00228 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00229 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-05 | Network | Link flap test | Pass |  | 65 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00230 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 238 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00231 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0001 | ST-02 | Storage | NVMe hot-plug | Pass |  | 59 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00232 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0024 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 30 | 2.2.8 | V1.02 | Dramtek | D2606
R00233 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-06 | Network | NIC throughput 100G | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00234 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-01 | Storage | NVMe hot-plug | Pass |  | 60 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00235 | 2026-06-17 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 243 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00236 | 2026-06-17 | Night | VEGA-1U | EVT | VEG-E-0001 | ST-02 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 144 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00237 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0005 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2836 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00238 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0003 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2788 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00239 | 2026-06-18 | Day | ORION-2U | EVT | ORI-E-0010 | ST-07 | Storage | FIO random R/W | Pass |  | 65 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00240 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0003 | ST-08 | Memory | Memtest stress 12h | Pass |  | 684 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00241 | 2026-06-18 | Day | ORION-2U | EVT | ORI-E-0014 | ST-06 | Network | NIC throughput 100G | Pass |  | 64 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00242 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0012 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00243 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0023 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00244 | 2026-06-18 | Day | ORION-2U | EVT | ORI-E-0007 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00245 | 2026-06-18 | Night | ORION-2U | EVT | ORI-E-0013 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00246 | 2026-06-18 | Night | VEGA-1U | EVT | VEG-E-0001 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00247 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2716 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00248 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-03 | Memory | Memtest stress 12h | Pass |  | 737 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00249 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00250 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00251 | 2026-06-18 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2778 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00252 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-08 | Memory | ECC injection | Pass |  | 709 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00253 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 3114 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00254 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-10 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 36 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00255 | 2026-06-18 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-08 | Memory | Memtest stress 12h | Pass |  | 759 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00256 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0007 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00257 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0008 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00258 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0011 | ST-06 | Memory | ECC injection | Pass |  | 736 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00259 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0014 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 252 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00260 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0014 | ST-09 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00261 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0011 | TC-01 | Thermal | Thermal chamber | Pass |  | 191 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00262 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0019 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2978 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00263 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0006 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2930 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00264 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0002 | ST-01 | Storage | NVMe hot-plug | Pass |  | 65 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00265 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0023 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2746 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00266 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0022 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00267 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0001 | ST-04 | Network | Link flap test | Pass |  | 59 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00268 | 2026-06-19 | Day | ORION-2U | EVT | ORI-E-0002 | ST-06 | Memory | ECC injection | Pass |  | 785 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00269 | 2026-06-19 | Night | ORION-2U | EVT | ORI-E-0021 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00270 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-07 | Storage | NVMe hot-plug | Pass |  | 64 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00271 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 35 | 2.2.8 | V1.02 | MemCo-A | A2607
R00272 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00273 | 2026-06-19 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 258 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00274 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 178 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00275 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-05 | Storage | NVMe hot-plug | Pass |  | 55 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00276 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2663 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00277 | 2026-06-19 | Night | VEGA-1U | EVT | VEG-E-0007 | ST-01 | Network | NIC throughput 100G | Pass |  | 55 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00278 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 54 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00279 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00280 | 2026-06-19 | Day | VEGA-1U | EVT | VEG-E-0013 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 35 | 2.2.8 | V1.02 | MemCo-A | A2607
R00281 | 2026-06-20 | Day | ORION-2U | EVT | ORI-E-0010 | ST-02 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00282 | 2026-06-20 | Night | ORION-2U | EVT | ORI-E-0001 | ST-09 | Memory | ECC injection | Pass |  | 758 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00283 | 2026-06-20 | Day | ORION-2U | EVT | ORI-E-0002 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 257 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00284 | 2026-06-20 | Day | ORION-2U | EVT | ORI-E-0013 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00285 | 2026-06-20 | Night | ORION-2U | EVT | ORI-E-0017 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2780 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00286 | 2026-06-20 | Day | ORION-2U | EVT | ORI-E-0002 | ST-02 | Storage | NVMe hot-plug | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00287 | 2026-06-20 | Day | ORION-2U | EVT | ORI-E-0018 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00288 | 2026-06-20 | Night | ORION-2U | EVT | ORI-E-0012 | ST-01 | Power-on/POST | DC cycle 500x | Fail | System stuck in S5 | 43 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00289 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-04 | Storage | NVMe hot-plug | Pass |  | 55 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00290 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-03 | Storage | NVMe hot-plug | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00291 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-03 | Network | Link flap test | Fail | Link down | 41 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00292 | 2026-06-20 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00293 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3133 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00294 | 2026-06-20 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 61 | 22 | 2.2.8 | V1.02 | MemCo-B | B2604
R00295 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-04 | Network | NIC throughput 100G | Pass |  | 61 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00296 | 2026-06-20 | Night | VEGA-1U | EVT | VEG-E-0015 | ST-08 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1401 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00297 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2974 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00298 | 2026-06-20 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2990 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00299 | 2026-06-21 | Day | ORION-2U | EVT | ORI-E-0021 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00300 | 2026-06-21 | Day | ORION-2U | EVT | ORI-E-0016 | ST-10 | Storage | NVMe hot-plug | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00301 | 2026-06-21 | Night | ORION-2U | EVT | ORI-E-0016 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3143 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00302 | 2026-06-21 | Day | ORION-2U | EVT | ORI-E-0002 | ST-06 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00303 | 2026-06-21 | Night | ORION-2U | EVT | ORI-E-0006 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00304 | 2026-06-21 | Day | ORION-2U | EVT | ORI-E-0014 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00305 | 2026-06-21 | Day | ORION-2U | EVT | ORI-E-0017 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00306 | 2026-06-21 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 54 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00307 | 2026-06-21 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00308 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-10 | Storage | FIO random R/W | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00309 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0022 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 107 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00310 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-04 | Network | Link flap test | Pass |  | 56 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00311 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-01 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 550 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00312 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-04 | Memory | Memtest stress 12h | Pass |  | 657 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00313 | 2026-06-21 | Night | VEGA-1U | EVT | VEG-E-0017 | ST-09 | Memory | ECC injection | Pass |  | 751 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00314 | 2026-06-21 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-03 | Power-on/POST | DC cycle 500x | Fail | No POST | 34 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00315 | 2026-06-21 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-04 | Power-on/POST | AC cycle 500x | Fail | No POST | 25 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00316 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0014 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3107 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00317 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0021 | ST-08 | Network | NIC throughput 100G | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00318 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0022 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00319 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0001 | ST-09 | Storage | FIO random R/W | Pass |  | 63 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00320 | 2026-06-22 | Night | ORION-2U | EVT | ORI-E-0005 | ST-03 | Network | NIC throughput 100G | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00321 | 2026-06-22 | Night | ORION-2U | EVT | ORI-E-0021 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00322 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0010 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 226 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00323 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0018 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00324 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0013 | ST-08 | Memory | ECC injection | Pass |  | 747 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00325 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0001 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00326 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0005 | ST-08 | Memory | Memtest stress 12h | Fail | DIMM not detected | 190 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00327 | 2026-06-22 | Day | ORION-2U | EVT | ORI-E-0023 | ST-10 | Memory | Memtest stress 12h | Pass |  | 784 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00328 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-08 | Network | NIC throughput 100G | Fail | Throughput below spec | 38 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00329 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-05 | Network | Link flap test | Pass |  | 58 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00330 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-02 | Memory | Memtest stress 12h | Pass |  | 759 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00331 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3060 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00332 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-03 | Memory | Memtest stress 12h | Pass |  | 786 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00333 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0004 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | CPU throttling | 54 | 30 | 2.2.8 | V1.02 | Dramtek | D2606
R00334 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0006 | TC-01 | Thermal | Thermal chamber | Pass |  | 175 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00335 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00336 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0010 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 30 | 2.2.8 | V1.02 | MemCo-A | A2605
R00337 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00338 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0005 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 64 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00339 | 2026-06-22 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-10 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 23 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00340 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0004 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00341 | 2026-06-23 | Night | ORION-2U | EVT | ORI-E-0006 | ST-08 | Memory | ECC injection | Pass |  | 690 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00342 | 2026-06-23 | Night | ORION-2U | EVT | ORI-E-0007 | ST-04 | Storage | FIO random R/W | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00343 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0022 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2688 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00344 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0012 | ST-01 | Memory | ECC injection | Pass |  | 660 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00345 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0002 | ST-02 | Network | Link flap test | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00346 | 2026-06-23 | Night | ORION-2U | EVT | ORI-E-0016 | ST-01 | Storage | NVMe hot-plug | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00347 | 2026-06-23 | Night | ORION-2U | EVT | ORI-E-0023 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 62 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00348 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0020 | ST-03 | Memory | Memtest stress 12h | Pass |  | 664 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00349 | 2026-06-23 | Day | ORION-2U | EVT | ORI-E-0018 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00350 | 2026-06-23 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-07 | Memory | ECC injection | Pass |  | 756 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00351 | 2026-06-23 | Night | VEGA-1U | EVT | VEG-E-0007 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3055 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00352 | 2026-06-23 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-05 | Network | Link flap test | Pass |  | 62 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00353 | 2026-06-23 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-01 | Network | NIC throughput 100G | Pass |  | 63 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00354 | 2026-06-23 | Day | VEGA-1U | EVT | VEG-E-0010 | TC-02 | Thermal | Thermal chamber | Pass |  | 165 | 35 | 2.2.8 | V1.02 | MemCo-A | A2605
R00355 | 2026-06-23 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-05 | Storage | FIO random R/W | Pass |  | 62 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00356 | 2026-06-24 | Night | ORION-2U | EVT | ORI-E-0019 | ST-02 | Storage | NVMe hot-plug | Pass |  | 62 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00357 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0011 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00358 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0012 | ST-02 | Memory | Memtest stress 12h | Pass |  | 657 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00359 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0002 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00360 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0010 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00361 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0009 | ST-03 | Network | NIC throughput 100G | Pass |  | 60 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00362 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0011 | ST-04 | Memory | Memtest stress 12h | Fail | DIMM not detected | 495 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00363 | 2026-06-24 | Night | ORION-2U | EVT | ORI-E-0012 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00364 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0016 | ST-03 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 39 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00365 | 2026-06-24 | Night | ORION-2U | EVT | ORI-E-0001 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 61 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00366 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0012 | TC-01 | Thermal | Thermal chamber | Pass |  | 177 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00367 | 2026-06-24 | Day | ORION-2U | EVT | ORI-E-0019 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2638 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00368 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 35 | 2.2.8 | V1.02 | MemCo-B | B2607
R00369 | 2026-06-24 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00370 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-10 | Storage | NVMe hot-plug | Pass |  | 57 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00371 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-03 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00372 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0016 | TC-01 | Thermal | Thermal chamber | Pass |  | 196 | 30 | 2.2.8 | V1.02 | MemCo-A | A2607
R00373 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00374 | 2026-06-24 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-03 | Memory | ECC injection | Pass |  | 650 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00375 | 2026-06-24 | Night | VEGA-1U | EVT | VEG-E-0001 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00376 | 2026-06-24 | Day | VEGA-1U | EVT | VEG-E-0003 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 30 | 2.2.8 | V1.02 | MemCo-A | A2605
R00377 | 2026-06-25 | Day | ORION-2U | EVT | ORI-E-0019 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 258 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00378 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0024 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 184 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00379 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0002 | ST-04 | Network | Link flap test | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00380 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0016 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00381 | 2026-06-25 | Day | ORION-2U | EVT | ORI-E-0019 | TC-02 | Thermal | Thermal chamber | Pass |  | 169 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00382 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0015 | TC-01 | Thermal | Thermal chamber | Pass |  | 178 | 30 | 2.2.8 | O1.02 | MemCo-A | A2605
R00383 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0005 | ST-05 | Memory | Memtest stress 12h | Pass |  | 743 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00384 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0001 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00385 | 2026-06-25 | Day | ORION-2U | EVT | ORI-E-0015 | ST-10 | Memory | ECC injection | Pass |  | 745 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00386 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0011 | ST-09 | Network | Link flap test | Fail | Link down | 32 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00387 | 2026-06-25 | Night | ORION-2U | EVT | ORI-E-0009 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 62 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00388 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-04 | Memory | ECC injection | Pass |  | 757 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00389 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00390 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2757 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00391 | 2026-06-25 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2816 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00392 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00393 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-09 | Memory | Memtest stress 12h | Pass |  | 696 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00394 | 2026-06-25 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-04 | Memory | Memtest stress 12h | Pass |  | 685 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00395 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-02 | Thermal | Thermal chamber | Pass |  | 170 | 35 | 2.2.8 | V1.02 | MemCo-A | A2607
R00396 | 2026-06-25 | Day | VEGA-1U | EVT | VEG-E-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 178 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00397 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0012 | ST-01 | Memory | Memtest stress 12h | Pass |  | 666 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00398 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0006 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00399 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0024 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2998 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00400 | 2026-06-26 | Night | ORION-2U | EVT | ORI-E-0019 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2905 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00401 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0002 | ST-05 | Storage | FIO random R/W | Pass |  | 58 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00402 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0001 | ST-04 | Memory | ECC injection | Pass |  | 781 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00403 | 2026-06-26 | Night | ORION-2U | EVT | ORI-E-0005 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 35 | 2.2.8 | O1.02 | MemCo-A | A2607
R00404 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0004 | TC-01 | Thermal | Thermal chamber | Pass |  | 178 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00405 | 2026-06-26 | Night | ORION-2U | EVT | ORI-E-0021 | ST-04 | Memory | ECC injection | Fail | Error not logged in SEL | 427 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00406 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0007 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00407 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0015 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2744 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00408 | 2026-06-26 | Night | ORION-2U | EVT | ORI-E-0016 | ST-01 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00409 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0022 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00410 | 2026-06-26 | Day | ORION-2U | EVT | ORI-E-0017 | ST-02 | Network | Link flap test | Pass |  | 59 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00411 | 2026-06-26 | Night | VEGA-1U | EVT | VEG-E-0018 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 66 | 35 | 2.2.8 | V1.02 | MemCo-B | B2607
R00412 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-06 | Network | Link flap test | Pass |  | 59 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00413 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-07 | Network | NIC throughput 100G | Pass |  | 60 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00414 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-09 | Storage | NVMe hot-plug | Pass |  | 64 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00415 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 247 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00416 | 2026-06-26 | Night | VEGA-1U | EVT | VEG-E-0002 | ST-07 | Memory | Memtest stress 12h | Pass |  | 657 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00417 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-03 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00418 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3089 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00419 | 2026-06-26 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-02 | Memory | Memtest stress 12h | Pass |  | 771 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00420 | 2026-06-27 | Night | ORION-2U | EVT | ORI-E-0012 | ST-02 | Storage | FIO random R/W | Pass |  | 64 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00421 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0019 | ST-08 | Memory | ECC injection | Pass |  | 748 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00422 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0005 | TC-01 | Thermal | Thermal chamber | Pass |  | 179 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00423 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0006 | ST-03 | Memory | Memtest stress 12h | Pass |  | 692 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00424 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0003 | ST-04 | Storage | FIO random R/W | Pass |  | 56 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00425 | 2026-06-27 | Night | ORION-2U | EVT | ORI-E-0012 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2660 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00426 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0012 | ST-05 | Storage | NVMe hot-plug | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00427 | 2026-06-27 | Night | ORION-2U | EVT | ORI-E-0003 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 258 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00428 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0009 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00429 | 2026-06-27 | Day | ORION-2U | EVT | ORI-E-0010 | ST-07 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00430 | 2026-06-27 | Day | VEGA-1U | EVT | VEG-E-0006 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 164 | 30 | 2.2.8 | V1.02 | MemCo-B | B2607
R00431 | 2026-06-27 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00432 | 2026-06-27 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-09 | Memory | Memtest stress 12h | Pass |  | 673 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00433 | 2026-06-27 | Night | VEGA-1U | EVT | VEG-E-0009 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 35 | 2.2.8 | V1.02 | MemCo-A | A2605
R00434 | 2026-06-27 | Night | VEGA-1U | EVT | VEG-E-0024 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 56 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00435 | 2026-06-27 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-04 | Memory | ECC injection | Pass |  | 759 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00436 | 2026-06-27 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2830 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00437 | 2026-06-28 | Day | ORION-2U | EVT | ORI-E-0013 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00438 | 2026-06-28 | Day | ORION-2U | EVT | ORI-E-0001 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00439 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0023 | ST-05 | Storage | FIO random R/W | Pass |  | 54 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00440 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0022 | ST-03 | Storage | NVMe hot-plug | Pass |  | 55 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00441 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0011 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00442 | 2026-06-28 | Day | ORION-2U | EVT | ORI-E-0011 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00443 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00444 | 2026-06-28 | Day | ORION-2U | EVT | ORI-E-0003 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00445 | 2026-06-28 | Day | ORION-2U | EVT | ORI-E-0022 | ST-04 | Memory | ECC injection | Pass |  | 714 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00446 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0003 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 59 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00447 | 2026-06-28 | Night | ORION-2U | EVT | ORI-E-0007 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00448 | 2026-06-28 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 236 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00449 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-06 | Memory | Memtest stress 12h | Pass |  | 667 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00450 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-08 | Storage | NVMe hot-plug | Pass |  | 58 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00451 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 184 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00452 | 2026-06-28 | Night | VEGA-1U | EVT | VEG-E-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 195 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00453 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00454 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00455 | 2026-06-28 | Night | VEGA-1U | EVT | VEG-E-0013 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 57 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00456 | 2026-06-28 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-07 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00457 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0002 | ST-03 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00458 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0015 | ST-03 | Network | NIC throughput 100G | Pass |  | 60 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00459 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0002 | TC-01 | Thermal | Thermal chamber | Pass |  | 196 | 35 | 2.2.8 | O1.02 | MemCo-A | A2607
R00460 | 2026-06-29 | Day | ORION-2U | EVT | ORI-E-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 195 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00461 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0005 | TC-02 | Thermal | Thermal chamber | Pass |  | 174 | 30 | 2.2.8 | O1.02 | MemCo-A | A2607
R00462 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0016 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00463 | 2026-06-29 | Day | ORION-2U | EVT | ORI-E-0020 | ST-01 | Network | NIC throughput 100G | Pass |  | 58 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00464 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0024 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 60 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00465 | 2026-06-29 | Day | ORION-2U | EVT | ORI-E-0001 | ST-09 | Storage | NVMe hot-plug | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00466 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0013 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2604 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00467 | 2026-06-29 | Day | ORION-2U | EVT | ORI-E-0018 | ST-04 | Memory | Memtest stress 12h | Pass |  | 723 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00468 | 2026-06-29 | Night | ORION-2U | EVT | ORI-E-0023 | ST-03 | Storage | NVMe hot-plug | Pass |  | 56 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00469 | 2026-06-29 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-04 | Storage | FIO random R/W | Pass |  | 55 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00470 | 2026-06-29 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-02 | Network | Link flap test | Pass |  | 55 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00471 | 2026-06-29 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00472 | 2026-06-29 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00473 | 2026-06-29 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-01 | Network | NIC throughput 100G | Pass |  | 60 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00474 | 2026-06-29 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2832 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00475 | 2026-06-30 | Night | ORION-2U | EVT | ORI-E-0002 | TC-02 | Thermal | Thermal chamber | Pass |  | 171 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00476 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0004 | ST-03 | Network | Link flap test | Pass |  | 54 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00477 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0006 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2828 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00478 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0002 | ST-09 | Memory | ECC injection | Pass |  | 768 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00479 | 2026-06-30 | Night | ORION-2U | EVT | ORI-E-0017 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 115 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00480 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0014 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00481 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0007 | ST-10 | Storage | NVMe hot-plug | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00482 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0015 | ST-08 | Network | NIC throughput 100G | Pass |  | 65 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00483 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0012 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2628 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00484 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0012 | ST-04 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00485 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0022 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00486 | 2026-06-30 | Day | ORION-2U | EVT | ORI-E-0012 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00487 | 2026-06-30 | Night | ORION-2U | EVT | ORI-E-0017 | TC-01 | Thermal | Thermal chamber | Pass |  | 172 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00488 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0002 | ST-03 | Memory | Memtest stress 12h | Pass |  | 745 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00489 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-02 | Storage | NVMe hot-plug | Pass |  | 62 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00490 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00491 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-05 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00492 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2601 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00493 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3001 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00494 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-05 | Network | NIC throughput 100G | Pass |  | 61 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00495 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00496 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-05 | Network | Link flap test | Pass |  | 65 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00497 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-05 | Memory | Memtest stress 12h | Pass |  | 694 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00498 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-02 | Memory | Memtest stress 12h | Pass |  | 649 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00499 | 2026-06-30 | Night | VEGA-1U | EVT | VEG-E-0015 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00500 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00501 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-04 | Network | Link flap test | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00502 | 2026-06-30 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-03 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1923 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00503 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0011 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00504 | 2026-07-01 | Night | ORION-2U | EVT | ORI-E-0005 | ST-03 | Network | Link flap test | Pass |  | 64 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00505 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0009 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3083 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00506 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0024 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2982 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00507 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0020 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00508 | 2026-07-01 | Night | ORION-2U | EVT | ORI-E-0004 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00509 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0008 | ST-07 | Memory | Memtest stress 12h | Pass |  | 755 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00510 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0011 | ST-10 | Storage | NVMe hot-plug | Pass |  | 58 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00511 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0014 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00512 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0018 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00513 | 2026-07-01 | Night | ORION-2U | EVT | ORI-E-0014 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 55 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00514 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0004 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 259 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00515 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0022 | ST-02 | Network | Link flap test | Pass |  | 62 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00516 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0014 | ST-07 | Memory | Memtest stress 12h | Pass |  | 683 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00517 | 2026-07-01 | Day | ORION-2U | EVT | ORI-E-0013 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00518 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-09 | Network | Link flap test | Pass |  | 59 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00519 | 2026-07-01 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-01 | Memory | ECC injection | Fail | Error not logged in SEL | 363 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00520 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 65 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00521 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | CPU throttling | 90 | 35 | 2.2.8 | V1.02 | MemCo-B | B2607
R00522 | 2026-07-01 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-06 | Storage | NVMe hot-plug | Pass |  | 64 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00523 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-04 | Memory | Memtest stress 12h | Pass |  | 725 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00524 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-05 | Network | Link flap test | Pass |  | 62 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00525 | 2026-07-01 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2643 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00526 | 2026-07-01 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2893 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00527 | 2026-07-01 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-03 | Storage | NVMe hot-plug | Pass |  | 57 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00528 | 2026-07-01 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00529 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-05 | Network | Link flap test | Pass |  | 58 | 22 | 2.2.8 | L1.02 | Dramtek | D2606
R00530 | 2026-07-01 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 223 | 23 | 2.2.8 | L1.02 | MemCo-B | B2607
R00531 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2788 | 24 | 2.2.8 | L1.02 | MemCo-A | A2605
R00532 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2619 | 24 | 2.2.8 | L1.02 | Dramtek | D2606
R00533 | 2026-07-01 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 221 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00534 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 30 | 2.2.8 | L1.02 | MemCo-A | A2605
R00535 | 2026-07-01 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 23 | 2.2.8 | L1.02 | MemCo-A | A2607
R00536 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 184 | 35 | 2.2.8 | L1.02 | MemCo-A | A2607
R00537 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.2.8 | L1.02 | MemCo-A | A2607
R00538 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-03 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.2.8 | L1.02 | MemCo-B | B2607
R00539 | 2026-07-01 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-06 | Memory | ECC injection | Fail | Error not logged in SEL | 268 | 25 | 2.2.8 | L1.02 | MemCo-B | B2607
R00540 | 2026-07-02 | Night | ORION-2U | EVT | ORI-E-0017 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3096 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00541 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0016 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00542 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0023 | ST-01 | PCIe/GPU | PCIe link training | Pass |  | 257 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00543 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0013 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00544 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0023 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00545 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0010 | ST-06 | Memory | Memtest stress 12h | Pass |  | 742 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00546 | 2026-07-02 | Night | ORION-2U | EVT | ORI-E-0018 | ST-01 | Storage | FIO random R/W | Pass |  | 62 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00547 | 2026-07-02 | Night | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00548 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0013 | ST-07 | Memory | ECC injection | Pass |  | 748 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00549 | 2026-07-02 | Night | ORION-2U | EVT | ORI-E-0016 | ST-09 | Memory | ECC injection | Pass |  | 714 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00550 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0018 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2780 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00551 | 2026-07-02 | Night | ORION-2U | EVT | ORI-E-0024 | ST-01 | Network | Link flap test | Pass |  | 64 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00552 | 2026-07-02 | Day | ORION-2U | EVT | ORI-E-0002 | ST-09 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 26 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00553 | 2026-07-02 | Night | VEGA-1U | EVT | VEG-E-0002 | ST-09 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 143 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00554 | 2026-07-02 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-04 | Memory | Memtest stress 12h | Pass |  | 678 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00555 | 2026-07-02 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00556 | 2026-07-02 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00557 | 2026-07-02 | Night | VEGA-1U | EVT | VEG-E-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 35 | 2.2.8 | V1.02 | MemCo-A | A2607
R00558 | 2026-07-02 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 229 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00559 | 2026-07-02 | Night | VEGA-1U | EVT | VEG-E-0024 | ST-10 | Memory | ECC injection | Pass |  | 766 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00560 | 2026-07-02 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-10 | Memory | Memtest stress 12h | Pass |  | 758 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00561 | 2026-07-02 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00562 | 2026-07-02 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-05 | Network | NIC throughput 100G | Pass |  | 65 | 25 | 2.2.8 | L1.02 | MemCo-B | B2604
R00563 | 2026-07-02 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00564 | 2026-07-02 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00565 | 2026-07-02 | Day | LYRA-4U | EVT | LYR-E-0011 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 35 | 2.2.8 | L1.02 | MemCo-B | B2607
R00566 | 2026-07-02 | Day | LYRA-4U | EVT | LYR-E-0014 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2747 | 24 | 2.2.8 | L1.02 | MemCo-B | B2604
R00567 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0017 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00568 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0016 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00569 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0004 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00570 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0012 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3068 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00571 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0006 | ST-09 | Network | Link flap test | Pass |  | 57 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00572 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0005 | TC-02 | Thermal | Thermal chamber | Pass |  | 179 | 35 | 2.2.8 | O1.02 | MemCo-A | A2607
R00573 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0002 | ST-07 | Memory | ECC injection | Pass |  | 761 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00574 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0006 | ST-03 | Storage | NVMe hot-plug | Pass |  | 60 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00575 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0010 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 237 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00576 | 2026-07-03 | Night | ORION-2U | EVT | ORI-E-0020 | ST-03 | Network | Link flap test | Pass |  | 55 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00577 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0005 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2927 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00578 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0022 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 174 | 35 | 2.2.8 | O1.02 | MemCo-A | A2607
R00579 | 2026-07-03 | Day | ORION-2U | EVT | ORI-E-0021 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 54 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00580 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00581 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-02 | Storage | NVMe hot-plug | Pass |  | 64 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00582 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 59 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00583 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2966 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00584 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00585 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00586 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00587 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-06 | Network | NIC throughput 100G | Pass |  | 65 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00588 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00589 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0007 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00590 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-02 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 38 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00591 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 65 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00592 | 2026-07-03 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-06 | Storage | FIO random R/W | Fail | IOPS below spec | 32 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00593 | 2026-07-03 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00594 | 2026-07-03 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 252 | 24 | 2.2.8 | L1.02 | MemCo-A | A2605
R00595 | 2026-07-03 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-05 | Memory | Memtest stress 12h | Pass |  | 672 | 23 | 2.2.8 | L1.02 | MemCo-A | A2605
R00596 | 2026-07-03 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 241 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00597 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0002 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 217 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00598 | 2026-07-04 | Night | ORION-2U | EVT | ORI-E-0013 | ST-02 | Network | NIC throughput 100G | Pass |  | 56 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00599 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0018 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 35 | 2.2.8 | O1.02 | MemCo-A | A2605
R00600 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0015 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00601 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0014 | ST-06 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00602 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0005 | ST-04 | Memory | ECC injection | Pass |  | 764 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00603 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0017 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00604 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0015 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 188 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00605 | 2026-07-04 | Day | ORION-2U | EVT | ORI-E-0019 | ST-04 | Storage | FIO random R/W | Pass |  | 62 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00606 | 2026-07-04 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-04 | Memory | Memtest stress 12h | Pass |  | 745 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00607 | 2026-07-04 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-09 | Storage | FIO random R/W | Pass |  | 65 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00608 | 2026-07-04 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-08 | Storage | NVMe hot-plug | Pass |  | 56 | 22 | 2.2.8 | V1.02 | MemCo-B | B2604
R00609 | 2026-07-04 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-03 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 103 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00610 | 2026-07-04 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-09 | Storage | FIO random R/W | Pass |  | 58 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00611 | 2026-07-04 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00612 | 2026-07-04 | Night | LYRA-4U | EVT | LYR-E-0009 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.2.8 | L1.02 | Dramtek | D2606
R00613 | 2026-07-04 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | L1.02 | MemCo-B | B2607
R00614 | 2026-07-04 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 229 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00615 | 2026-07-04 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.2.8 | L1.02 | MemCo-A | A2605
R00616 | 2026-07-04 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 262 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00617 | 2026-07-04 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00618 | 2026-07-04 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-02 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | L1.02 | MemCo-A | A2607
R00619 | 2026-07-04 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 218 | 22 | 2.2.8 | L1.02 | MemCo-B | B2607
R00620 | 2026-07-05 | Day | ORION-2U | EVT | ORI-E-0017 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00621 | 2026-07-05 | Day | ORION-2U | EVT | ORI-E-0022 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00622 | 2026-07-05 | Day | ORION-2U | EVT | ORI-E-0024 | ST-02 | Storage | NVMe hot-plug | Pass |  | 64 | 22 | 2.2.8 | O1.02 | Dramtek | D2606
R00623 | 2026-07-05 | Day | ORION-2U | EVT | ORI-E-0006 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 228 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00624 | 2026-07-05 | Night | ORION-2U | EVT | ORI-E-0008 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 242 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00625 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00626 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-04 | Memory | ECC injection | Pass |  | 769 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00627 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 262 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00628 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0020 | ST-05 | Network | NIC throughput 100G | Pass |  | 59 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00629 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3129 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00630 | 2026-07-05 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 58 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00631 | 2026-07-05 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00632 | 2026-07-05 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-03 | Memory | ECC injection | Pass |  | 763 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00633 | 2026-07-05 | Day | LYRA-4U | EVT | LYR-E-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.2.8 | L1.02 | Dramtek | D2606
R00634 | 2026-07-06 | Night | ORION-2U | EVT | ORI-E-0008 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00635 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0016 | ST-01 | Storage | NVMe hot-plug | Pass |  | 58 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00636 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0004 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2844 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00637 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0005 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00638 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0023 | ST-01 | Storage | FIO random R/W | Pass |  | 62 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00639 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0019 | ST-10 | Memory | Memtest stress 12h | Pass |  | 766 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00640 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0021 | ST-02 | Burn-in | Burn-in 48h | Fail | Kernel panic | 657 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00641 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0010 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00642 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0002 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00643 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0011 | ST-03 | Memory | Memtest stress 12h | Pass |  | 737 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00644 | 2026-07-06 | Night | ORION-2U | EVT | ORI-E-0002 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2981 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00645 | 2026-07-06 | Night | ORION-2U | EVT | ORI-E-0007 | TC-01 | Thermal | Thermal chamber | Pass |  | 171 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00646 | 2026-07-06 | Day | ORION-2U | EVT | ORI-E-0012 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2814 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00647 | 2026-07-06 | Night | ORION-2U | EVT | ORI-E-0008 | TC-02 | Thermal | Thermal chamber | Pass |  | 166 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00648 | 2026-07-06 | Night | VEGA-1U | EVT | VEG-E-0024 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 252 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00649 | 2026-07-06 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-03 | Memory | Memtest stress 12h | Pass |  | 774 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00650 | 2026-07-06 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-02 | Memory | Memtest stress 12h | Pass |  | 672 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00651 | 2026-07-06 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 228 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00652 | 2026-07-06 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00653 | 2026-07-06 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-09 | Memory | ECC injection | Pass |  | 678 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00654 | 2026-07-06 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00655 | 2026-07-06 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-10 | Power-on/POST | DC cycle 500x | Fail | System stuck in S5 | 34 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00656 | 2026-07-06 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3158 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00657 | 2026-07-06 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 25 | 2.2.8 | L1.02 | MemCo-B | B2604
R00658 | 2026-07-06 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.2.8 | L1.02 | MemCo-A | A2607
R00659 | 2026-07-06 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.2.8 | L1.02 | MemCo-B | B2604
R00660 | 2026-07-06 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-08 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.2.8 | L1.02 | MemCo-B | B2604
R00661 | 2026-07-06 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-01 | Power-on/POST | DC cycle 500x | Fail | System stuck in S5 | 27 | 23 | 2.2.8 | L1.02 | MemCo-B | B2604
R00662 | 2026-07-06 | Night | LYRA-4U | EVT | LYR-E-0015 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 185 | 35 | 2.2.8 | L1.02 | Dramtek | D2606
R00663 | 2026-07-06 | Night | LYRA-4U | EVT | LYR-E-0009 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 63 | 35 | 2.2.8 | L1.02 | Dramtek | D2606
R00664 | 2026-07-07 | Day | ORION-2U | EVT | ORI-E-0022 | ST-08 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.2.8 | O1.02 | MemCo-A | A2607
R00665 | 2026-07-07 | Day | ORION-2U | EVT | ORI-E-0023 | ST-05 | Network | Link flap test | Pass |  | 60 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00666 | 2026-07-07 | Night | ORION-2U | EVT | ORI-E-0012 | TC-01 | Thermal | Thermal chamber | Pass |  | 193 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00667 | 2026-07-07 | Day | ORION-2U | EVT | ORI-E-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 173 | 25 | 2.2.8 | O1.02 | Dramtek | D2606
R00668 | 2026-07-07 | Night | ORION-2U | EVT | ORI-E-0003 | ST-06 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00669 | 2026-07-07 | Night | ORION-2U | EVT | ORI-E-0019 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00670 | 2026-07-07 | Night | ORION-2U | EVT | ORI-E-0013 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00671 | 2026-07-07 | Night | ORION-2U | EVT | ORI-E-0023 | ST-10 | Network | Link flap test | Pass |  | 59 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00672 | 2026-07-07 | Day | ORION-2U | EVT | ORI-E-0013 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 175 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00673 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0001 | ST-03 | Storage | FIO random R/W | Fail | IOPS below spec | 37 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00674 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00675 | 2026-07-07 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-03 | Memory | ECC injection | Pass |  | 690 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00676 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-05 | Storage | NVMe hot-plug | Pass |  | 63 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00677 | 2026-07-07 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-04 | Memory | Memtest stress 12h | Pass |  | 758 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00678 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-06 | Storage | FIO random R/W | Pass |  | 54 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00679 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 64 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00680 | 2026-07-07 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00681 | 2026-07-07 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-05 | Memory | ECC injection | Pass |  | 759 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00682 | 2026-07-07 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3158 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00683 | 2026-07-07 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-05 | Memory | Memtest stress 12h | Pass |  | 665 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00684 | 2026-07-07 | Night | LYRA-4U | EVT | LYR-E-0004 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 53 | 30 | 2.2.8 | L1.02 | MemCo-A | A2605
R00685 | 2026-07-07 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-09 | Storage | FIO random R/W | Pass |  | 64 | 23 | 2.2.8 | L1.02 | MemCo-B | B2607
R00686 | 2026-07-07 | Day | LYRA-4U | EVT | LYR-E-0020 | TC-01 | Thermal | Thermal chamber | Pass |  | 196 | 35 | 2.2.8 | L1.02 | MemCo-A | A2605
R00687 | 2026-07-07 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00688 | 2026-07-07 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 231 | 23 | 2.2.8 | L1.02 | MemCo-A | A2605
R00689 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0013 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3136 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00690 | 2026-07-08 | Day | ORION-2U | EVT | ORI-E-0023 | ST-07 | Memory | ECC injection | Pass |  | 650 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00691 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0008 | ST-03 | Network | Link flap test | Pass |  | 60 | 22 | 2.2.8 | O1.02 | MemCo-A | A2605
R00692 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0019 | ST-04 | Storage | FIO random R/W | Pass |  | 61 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00693 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0014 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 3049 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00694 | 2026-07-08 | Day | ORION-2U | EVT | ORI-E-0015 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00695 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0015 | ST-03 | Storage | NVMe hot-plug | Pass |  | 65 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00696 | 2026-07-08 | Night | ORION-2U | EVT | ORI-E-0007 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 245 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00697 | 2026-07-08 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 65 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00698 | 2026-07-08 | Night | VEGA-1U | EVT | VEG-E-0006 | ST-03 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 412 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00699 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-05 | Memory | Memtest stress 12h | Pass |  | 772 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00700 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-01 | Network | NIC throughput 100G | Pass |  | 59 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00701 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-08 | Memory | Memtest stress 12h | Pass |  | 746 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00702 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 54 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00703 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-08 | Memory | Memtest stress 12h | Pass |  | 750 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00704 | 2026-07-08 | Night | VEGA-1U | EVT | VEG-E-0007 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2817 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00705 | 2026-07-08 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-01 | Storage | NVMe hot-plug | Pass |  | 64 | 23 | 2.2.8 | V1.02 | MemCo-A | A2607
R00706 | 2026-07-08 | Day | VEGA-1U | EVT | VEG-E-0020 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 197 | 35 | 2.2.8 | V1.02 | MemCo-A | A2605
R00707 | 2026-07-08 | Night | VEGA-1U | EVT | VEG-E-0015 | ST-07 | Memory | Memtest stress 12h | Pass |  | 704 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00708 | 2026-07-08 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-07 | Memory | ECC injection | Pass |  | 779 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00709 | 2026-07-08 | Night | LYRA-4U | EVT | LYR-E-0013 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 30 | 2.2.8 | L1.02 | MemCo-A | A2605
R00710 | 2026-07-08 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 61 | 23 | 2.2.8 | L1.02 | MemCo-B | B2607
R00711 | 2026-07-08 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.2.8 | L1.02 | MemCo-A | A2605
R00712 | 2026-07-08 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.2.8 | L1.02 | MemCo-A | A2607
R00713 | 2026-07-08 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 24 | 2.2.8 | L1.02 | MemCo-A | A2607
R00714 | 2026-07-08 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2866 | 24 | 2.2.8 | L1.02 | MemCo-A | A2605
R00715 | 2026-07-08 | Night | LYRA-4U | EVT | LYR-E-0022 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 59 | 35 | 2.2.8 | L1.02 | MemCo-B | B2607
R00716 | 2026-07-08 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00717 | 2026-07-09 | Night | ORION-2U | EVT | ORI-E-0013 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00718 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0004 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00719 | 2026-07-09 | Night | ORION-2U | EVT | ORI-E-0005 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00720 | 2026-07-09 | Night | ORION-2U | EVT | ORI-E-0023 | ST-07 | Memory | Memtest stress 12h | Pass |  | 713 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00721 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0011 | ST-06 | Memory | Memtest stress 12h | Pass |  | 784 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00722 | 2026-07-09 | Night | ORION-2U | EVT | ORI-E-0015 | ST-10 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00723 | 2026-07-09 | Night | ORION-2U | EVT | ORI-E-0013 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2984 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00724 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0012 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00725 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0020 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.2.8 | O1.02 | Dramtek | D2606
R00726 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0013 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00727 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0006 | ST-05 | Storage | FIO random R/W | Pass |  | 58 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00728 | 2026-07-09 | Day | ORION-2U | EVT | ORI-E-0022 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00729 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-06 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00730 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0017 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 56 | 30 | 2.2.8 | V1.02 | MemCo-A | A2605
R00731 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-06 | Storage | NVMe hot-plug | Pass |  | 62 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00732 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-06 | Memory | ECC injection | Pass |  | 692 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00733 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00734 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-02 | Memory | ECC injection | Pass |  | 691 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00735 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-05 | Memory | Memtest stress 12h | Pass |  | 745 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00736 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 3021 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00737 | 2026-07-09 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00738 | 2026-07-09 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-07 | Storage | NVMe hot-plug | Pass |  | 59 | 25 | 2.2.8 | L1.02 | MemCo-B | B2607
R00739 | 2026-07-09 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 227 | 22 | 2.2.8 | L1.02 | MemCo-A | A2605
R00740 | 2026-07-09 | Night | LYRA-4U | EVT | LYR-E-0010 | TC-02 | Thermal | Thermal chamber | Pass |  | 197 | 25 | 2.2.8 | L1.02 | MemCo-B | B2604
R00741 | 2026-07-09 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 30 | 2.2.8 | L1.02 | MemCo-A | A2607
R00742 | 2026-07-09 | Night | LYRA-4U | EVT | LYR-E-0004 | TC-02 | Thermal | Thermal chamber | Pass |  | 194 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00743 | 2026-07-09 | Night | LYRA-4U | EVT | LYR-E-0021 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 60 | 35 | 2.2.8 | L1.02 | MemCo-A | A2605
R00744 | 2026-07-09 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 60 | 22 | 2.2.8 | L1.02 | MemCo-A | A2605
R00745 | 2026-07-09 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-03 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 180 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00746 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0022 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 65 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00747 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0014 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 232 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00748 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0012 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2980 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00749 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0018 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 233 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00750 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0016 | ST-07 | Storage | NVMe hot-plug | Pass |  | 64 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00751 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0019 | ST-10 | Memory | ECC injection | Pass |  | 697 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00752 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0017 | ST-08 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00753 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0021 | ST-10 | Network | Link flap test | Pass |  | 64 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00754 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0022 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 247 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00755 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0016 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 23 | 2.2.8 | O1.02 | MemCo-A | A2605
R00756 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0001 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00757 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0013 | ST-05 | Network | NIC throughput 100G | Pass |  | 54 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00758 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0020 | ST-09 | Storage | FIO random R/W | Pass |  | 56 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00759 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0006 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 23 | 2.2.8 | O1.02 | MemCo-B | B2604
R00760 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 165 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00761 | 2026-07-10 | Night | ORION-2U | EVT | ORI-E-0006 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00762 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0017 | ST-03 | Network | NIC throughput 100G | Pass |  | 58 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00763 | 2026-07-10 | Day | ORION-2U | EVT | ORI-E-0019 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00764 | 2026-07-10 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-06 | Network | Link flap test | Pass |  | 64 | 22 | 2.2.8 | V1.02 | MemCo-B | B2607
R00765 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-05 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 25 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00766 | 2026-07-10 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2961 | 22 | 2.2.8 | V1.02 | MemCo-B | B2604
R00767 | 2026-07-10 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-02 | Storage | FIO random R/W | Pass |  | 64 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00768 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3136 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00769 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-05 | Memory | ECC injection | Pass |  | 765 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00770 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-10 | Network | Link flap test | Pass |  | 58 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00771 | 2026-07-10 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-02 | Storage | FIO random R/W | Fail | IOPS below spec | 30 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00772 | 2026-07-10 | Night | VEGA-1U | EVT | VEG-E-0016 | TC-02 | Thermal | Thermal chamber | Pass |  | 191 | 35 | 2.2.8 | V1.02 | MemCo-A | A2607
R00773 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 64 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00774 | 2026-07-10 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00775 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-08 | Network | NIC throughput 100G | Pass |  | 54 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00776 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00777 | 2026-07-10 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 248 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00778 | 2026-07-10 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-10 | Network | Link flap test | Pass |  | 55 | 24 | 2.2.8 | L1.02 | MemCo-B | B2607
R00779 | 2026-07-10 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00780 | 2026-07-10 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-07 | Storage | FIO random R/W | Pass |  | 54 | 23 | 2.2.8 | L1.02 | MemCo-A | A2605
R00781 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0018 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 24 | 2.2.8 | L1.02 | MemCo-A | A2607
R00782 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 57 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00783 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0010 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 35 | 2.2.8 | L1.02 | MemCo-B | B2604
R00784 | 2026-07-10 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00785 | 2026-07-11 | Night | ORION-2U | DVT | ORI-D-0016 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00786 | 2026-07-11 | Night | ORION-2U | DVT | ORI-D-0007 | ST-09 | Memory | Memtest stress 12h | Pass |  | 704 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00787 | 2026-07-11 | Day | ORION-2U | DVT | ORI-D-0001 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2942 | 24 | 2.2.8 | O1.02 | MemCo-A | A2605
R00788 | 2026-07-11 | Day | ORION-2U | DVT | ORI-D-0007 | ST-09 | Memory | Memtest stress 12h | Pass |  | 778 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00789 | 2026-07-11 | Day | ORION-2U | DVT | ORI-D-0017 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2784 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00790 | 2026-07-11 | Day | ORION-2U | DVT | ORI-D-0040 | ST-04 | Network | Link flap test | Pass |  | 55 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00791 | 2026-07-11 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2632 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00792 | 2026-07-11 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 57 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00793 | 2026-07-11 | Day | VEGA-1U | EVT | VEG-E-0019 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 30 | 2.2.8 | V1.02 | MemCo-B | B2604
R00794 | 2026-07-11 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 58 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00795 | 2026-07-11 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-08 | Memory | Memtest stress 12h | Pass |  | 660 | 23 | 2.2.8 | V1.02 | MemCo-B | B2604
R00796 | 2026-07-11 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2978 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00797 | 2026-07-11 | Night | LYRA-4U | EVT | LYR-E-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 25 | 2.2.8 | L1.02 | Dramtek | D2606
R00798 | 2026-07-11 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-09 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 22 | 2.2.8 | L1.02 | MemCo-A | A2607
R00799 | 2026-07-11 | Night | LYRA-4U | EVT | LYR-E-0007 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 120 | 30 | 2.2.8 | L1.02 | MemCo-B | B2607
R00800 | 2026-07-11 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00801 | 2026-07-11 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 23 | 2.2.8 | L1.02 | MemCo-B | B2607
R00802 | 2026-07-11 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-10 | Power-on/POST | AC cycle 500x | Fail | No POST | 24 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00803 | 2026-07-12 | Night | ORION-2U | DVT | ORI-D-0021 | ST-01 | Network | Link flap test | Pass |  | 59 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00804 | 2026-07-12 | Day | ORION-2U | DVT | ORI-D-0028 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2717 | 24 | 2.2.8 | O1.02 | MemCo-B | B2607
R00805 | 2026-07-12 | Night | ORION-2U | DVT | ORI-D-0016 | ST-09 | Network | NIC throughput 100G | Pass |  | 57 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00806 | 2026-07-12 | Day | ORION-2U | DVT | ORI-D-0007 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 35 | 2.2.8 | O1.02 | MemCo-B | B2604
R00807 | 2026-07-12 | Night | VEGA-1U | EVT | VEG-E-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00808 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0014 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 170 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00809 | 2026-07-12 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-07 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 7 | 22 | 2.2.8 | V1.02 | MemCo-B | B2604
R00810 | 2026-07-12 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2806 | 24 | 2.2.8 | V1.02 | MemCo-B | B2607
R00811 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2647 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00812 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-05 | Memory | Memtest stress 12h | Pass |  | 673 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00813 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-09 | Network | Link flap test | Pass |  | 58 | 23 | 2.2.8 | V1.02 | Dramtek | D2606
R00814 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0016 | TC-01 | Thermal | Thermal chamber | Pass |  | 177 | 25 | 2.2.8 | V1.02 | MemCo-A | A2607
R00815 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0011 | TC-02 | Thermal | Thermal chamber | Pass |  | 189 | 30 | 2.2.8 | V1.02 | MemCo-A | A2605
R00816 | 2026-07-12 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-06 | Network | Link flap test | Pass |  | 58 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00817 | 2026-07-12 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-09 | Storage | NVMe hot-plug | Pass |  | 64 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00818 | 2026-07-12 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2868 | 22 | 2.2.8 | L1.02 | MemCo-A | A2605
R00819 | 2026-07-12 | Night | LYRA-4U | EVT | LYR-E-0007 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 30 | 2.2.8 | L1.02 | MemCo-B | B2607
R00820 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0028 | ST-07 | Memory | Memtest stress 12h | Pass |  | 703 | 24 | 2.2.8 | O1.02 | MemCo-B | B2607
R00821 | 2026-07-13 | Night | ORION-2U | DVT | ORI-D-0026 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00822 | 2026-07-13 | Night | ORION-2U | DVT | ORI-D-0038 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2593 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00823 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0040 | ST-08 | Storage | NVMe hot-plug | Pass |  | 59 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00824 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0006 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 30 | 2.2.8 | O1.02 | MemCo-B | B2604
R00825 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0008 | ST-10 | Memory | ECC injection | Pass |  | 707 | 25 | 2.2.8 | O1.02 | MemCo-B | B2607
R00826 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0030 | ST-07 | Memory | Memtest stress 12h | Pass |  | 769 | 25 | 2.2.8 | O1.02 | MemCo-B | B2604
R00827 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0034 | ST-08 | Memory | ECC injection | Pass |  | 683 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00828 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0021 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00829 | 2026-07-13 | Day | ORION-2U | DVT | ORI-D-0004 | ST-08 | Storage | FIO random R/W | Pass |  | 63 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00830 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0008 | TC-01 | Thermal | Thermal chamber | Pass |  | 163 | 25 | 2.2.8 | V1.02 | MemCo-A | A2605
R00831 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00832 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-09 | Storage | FIO random R/W | Pass |  | 63 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00833 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00834 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-09 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00835 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-01 | Memory | Memtest stress 12h | Pass |  | 733 | 23 | 2.2.8 | V1.02 | MemCo-B | B2607
R00836 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.2.8 | V1.02 | MemCo-A | A2607
R00837 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0004 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 197 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00838 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-07 | Memory | ECC injection | Pass |  | 688 | 25 | 2.2.8 | V1.02 | MemCo-B | B2604
R00839 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0004 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | CPU throttling | 87 | 35 | 2.2.8 | V1.02 | Dramtek | D2606
R00840 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2622 | 24 | 2.2.8 | V1.02 | Dramtek | D2606
R00841 | 2026-07-13 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2895 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00842 | 2026-07-13 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-10 | Network | Link flap test | Pass |  | 65 | 24 | 2.2.8 | V1.02 | MemCo-A | A2605
R00843 | 2026-07-13 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-08 | Memory | Memtest stress 12h | Pass |  | 731 | 23 | 2.2.8 | L1.02 | Dramtek | D2606
R00844 | 2026-07-13 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 24 | 2.2.8 | L1.02 | MemCo-B | B2607
R00845 | 2026-07-13 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 218 | 22 | 2.2.8 | L1.02 | MemCo-B | B2607
R00846 | 2026-07-13 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 220 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00847 | 2026-07-13 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-05 | Memory | ECC injection | Pass |  | 702 | 24 | 2.2.8 | L1.02 | MemCo-A | A2605
R00848 | 2026-07-13 | Day | LYRA-4U | EVT | LYR-E-0015 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 190 | 25 | 2.2.8 | L1.02 | Dramtek | D2606
R00849 | 2026-07-14 | Night | ORION-2U | DVT | ORI-D-0011 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2675 | 24 | 2.2.8 | O1.02 | MemCo-A | A2607
R00850 | 2026-07-14 | Night | ORION-2U | DVT | ORI-D-0026 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00851 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0022 | ST-03 | Storage | NVMe hot-plug | Pass |  | 55 | 23 | 2.2.8 | O1.02 | MemCo-A | A2607
R00852 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0036 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 25 | 2.2.8 | O1.02 | MemCo-A | A2605
R00853 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0010 | ST-10 | Memory | ECC injection | Fail | Error not logged in SEL | 79 | 24 | 2.2.8 | O1.02 | MemCo-B | B2604
R00854 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0015 | ST-03 | Network | NIC throughput 100G | Pass |  | 64 | 25 | 2.2.8 | O1.02 | MemCo-A | A2607
R00855 | 2026-07-14 | Night | ORION-2U | DVT | ORI-D-0007 | ST-10 | Network | Link flap test | Pass |  | 61 | 22 | 2.2.8 | O1.02 | MemCo-B | B2604
R00856 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0039 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.2.8 | O1.02 | Dramtek | D2606
R00857 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0024 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 30 | 2.2.8 | O1.02 | MemCo-A | A2605
R00858 | 2026-07-14 | Day | ORION-2U | DVT | ORI-D-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | CPU throttling | 63 | 35 | 2.2.8 | O1.02 | MemCo-A | A2607
R00859 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-09 | Memory | Memtest stress 12h | Pass |  | 761 | 24 | 2.2.8 | V1.02 | MemCo-B | B2604
R00860 | 2026-07-14 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-09 | Network | NIC throughput 100G | Pass |  | 61 | 22 | 2.2.8 | V1.02 | MemCo-B | B2604
R00861 | 2026-07-14 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00862 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2780 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00863 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2869 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00864 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-08 | Power-on/POST | AC cycle 500x | Fail | No POST | 40 | 22 | 2.2.8 | V1.02 | MemCo-A | A2605
R00865 | 2026-07-14 | Night | VEGA-1U | EVT | VEG-E-0017 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 261 | 23 | 2.2.8 | V1.02 | MemCo-A | A2605
R00866 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 25 | 2.2.8 | V1.02 | Dramtek | D2606
R00867 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.2.8 | V1.02 | Dramtek | D2606
R00868 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0014 | TC-01 | Thermal | Thermal chamber | Pass |  | 190 | 25 | 2.2.8 | V1.02 | MemCo-B | B2607
R00869 | 2026-07-14 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.2.8 | V1.02 | MemCo-A | A2607
R00870 | 2026-07-14 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-07 | Network | NIC throughput 100G | Pass |  | 55 | 24 | 2.2.8 | L1.02 | MemCo-A | A2607
R00871 | 2026-07-14 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.2.8 | L1.02 | MemCo-A | A2605
R00872 | 2026-07-14 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-06 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1276 | 25 | 2.2.8 | L1.02 | MemCo-A | A2607
R00873 | 2026-07-14 | Night | LYRA-4U | EVT | LYR-E-0014 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 30 | 2.2.8 | L1.02 | MemCo-B | B2604
R00874 | 2026-07-14 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-07 | Network | NIC throughput 100G | Pass |  | 58 | 25 | 2.2.8 | L1.02 | MemCo-A | A2605
R00875 | 2026-07-14 | Day | LYRA-4U | EVT | LYR-E-0017 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 44 | 35 | 2.2.8 | L1.02 | MemCo-B | B2607
R00876 | 2026-07-15 | Day | ORION-2U | DVT | ORI-D-0001 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R00877 | 2026-07-15 | Night | ORION-2U | DVT | ORI-D-0026 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R00878 | 2026-07-15 | Day | ORION-2U | DVT | ORI-D-0031 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 238 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R00879 | 2026-07-15 | Night | ORION-2U | DVT | ORI-D-0027 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | O1.02 | Dramtek | D2606
R00880 | 2026-07-15 | Day | ORION-2U | DVT | ORI-D-0032 | ST-09 | Memory | Memtest stress 12h | Pass |  | 711 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R00881 | 2026-07-15 | Day | ORION-2U | DVT | ORI-D-0025 | ST-05 | Memory | ECC injection | Fail | Error not logged in SEL | 551 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R00882 | 2026-07-15 | Day | ORION-2U | DVT | ORI-D-0005 | ST-01 | Storage | NVMe hot-plug | Pass |  | 57 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R00883 | 2026-07-15 | Night | ORION-2U | DVT | ORI-D-0003 | ST-02 | Network | NIC throughput 100G | Pass |  | 63 | 22 | 2.3.1 | O1.02 | Dramtek | D2606
R00884 | 2026-07-15 | Night | ORION-2U | DVT | ORI-D-0032 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R00885 | 2026-07-15 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | V1.02 | Dramtek | D2606
R00886 | 2026-07-15 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-05 | Network | Link flap test | Pass |  | 55 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R00887 | 2026-07-15 | Night | VEGA-1U | EVT | VEG-E-0020 | ST-03 | Network | NIC throughput 100G | Pass |  | 54 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R00888 | 2026-07-15 | Night | VEGA-1U | EVT | VEG-E-0012 | TC-02 | Thermal | Thermal chamber | Pass |  | 184 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R00889 | 2026-07-15 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R00890 | 2026-07-15 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R00891 | 2026-07-15 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-05 | Memory | ECC injection | Pass |  | 766 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R00892 | 2026-07-15 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-04 | Network | Link flap test | Pass |  | 59 | 24 | 2.3.1 | V1.02 | Dramtek | D2606
R00893 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 64 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R00894 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0006 | TC-01 | Thermal | Thermal chamber | Pass |  | 163 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R00895 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-10 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 361 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R00896 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0010 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 194 | 25 | 2.3.1 | L1.02 | MemCo-B | B2604
R00897 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-01 | Memory | Memtest stress 12h | Pass |  | 719 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R00898 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0022 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R00899 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 62 | 22 | 2.3.1 | L1.02 | MemCo-B | B2607
R00900 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 22 | 2.3.1 | L1.02 | MemCo-B | B2607
R00901 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0008 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R00902 | 2026-07-15 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-07 | Memory | ECC injection | Pass |  | 741 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R00903 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R00904 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-01 | Memory | Memtest stress 12h | Fail | DIMM not detected | 315 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R00905 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0019 | TC-02 | Thermal | Thermal chamber | Pass |  | 185 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R00906 | 2026-07-15 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R00907 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0032 | ST-01 | Memory | ECC injection | Fail | Error not logged in SEL | 198 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R00908 | 2026-07-16 | Night | ORION-2U | DVT | ORI-D-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 30 | 2.3.1 | O1.02 | MemCo-B | B2604
R00909 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0015 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 255 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R00910 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0023 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 64 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R00911 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0018 | ST-04 | Network | NIC throughput 100G | Pass |  | 61 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R00912 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0008 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2903 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R00913 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0018 | TC-02 | Thermal | Thermal chamber | Pass |  | 162 | 30 | 2.3.1 | O1.02 | MemCo-A | A2607
R00914 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0038 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 35 | 2.3.1 | O1.02 | MemCo-B | B2604
R00915 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0021 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R00916 | 2026-07-16 | Night | ORION-2U | DVT | ORI-D-0032 | ST-02 | Storage | NVMe hot-plug | Pass |  | 59 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R00917 | 2026-07-16 | Night | ORION-2U | DVT | ORI-D-0016 | ST-07 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R00918 | 2026-07-16 | Night | ORION-2U | DVT | ORI-D-0026 | ST-01 | Storage | NVMe hot-plug | Pass |  | 64 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R00919 | 2026-07-16 | Day | ORION-2U | DVT | ORI-D-0032 | ST-06 | Memory | ECC injection | Fail | Error not logged in SEL | 575 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R00920 | 2026-07-16 | Night | ORION-2U | DVT | ORI-D-0016 | ST-05 | Storage | NVMe hot-plug | Pass |  | 58 | 23 | 2.3.1 | O1.02 | Dramtek | D2606
R00921 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R00922 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-04 | Network | NIC throughput 100G | Pass |  | 65 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R00923 | 2026-07-16 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 24 | 2.3.1 | V1.02 | MemCo-B | B2607
R00924 | 2026-07-16 | Night | VEGA-1U | EVT | VEG-E-0024 | ST-08 | Memory | ECC injection | Pass |  | 661 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R00925 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-01 | Memory | ECC injection | Pass |  | 748 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R00926 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 63 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R00927 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-10 | Network | NIC throughput 100G | Pass |  | 60 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R00928 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0013 | TC-01 | Thermal | Thermal chamber | Pass |  | 190 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R00929 | 2026-07-16 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00930 | 2026-07-16 | Night | VEGA-1U | EVT | VEG-E-0011 | ST-07 | Storage | FIO random R/W | Pass |  | 60 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00931 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2789 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R00932 | 2026-07-16 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 60 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R00933 | 2026-07-16 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-03 | Storage | NVMe hot-plug | Pass |  | 63 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R00934 | 2026-07-16 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 228 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R00935 | 2026-07-16 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 254 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R00936 | 2026-07-16 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-05 | Storage | NVMe hot-plug | Pass |  | 61 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R00937 | 2026-07-16 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-03 | Memory | Memtest stress 12h | Pass |  | 780 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R00938 | 2026-07-16 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 240 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R00939 | 2026-07-16 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-08 | Storage | FIO random R/W | Pass |  | 63 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R00940 | 2026-07-16 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 61 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R00941 | 2026-07-16 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 242 | 22 | 2.3.1 | L1.02 | Dramtek | D2606
R00942 | 2026-07-16 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R00943 | 2026-07-17 | Night | ORION-2U | DVT | ORI-D-0030 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 248 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R00944 | 2026-07-17 | Day | ORION-2U | DVT | ORI-D-0010 | ST-05 | Network | NIC throughput 100G | Pass |  | 54 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R00945 | 2026-07-17 | Day | ORION-2U | DVT | ORI-D-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 37 | 35 | 2.3.1 | O1.02 | Dramtek | D2606
R00946 | 2026-07-17 | Day | ORION-2U | DVT | ORI-D-0012 | ST-04 | Storage | NVMe hot-plug | Pass |  | 65 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R00947 | 2026-07-17 | Day | ORION-2U | DVT | ORI-D-0004 | ST-06 | Storage | NVMe hot-plug | Pass |  | 56 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R00948 | 2026-07-17 | Day | ORION-2U | DVT | ORI-D-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 185 | 35 | 2.3.1 | O1.02 | MemCo-B | B2604
R00949 | 2026-07-17 | Night | ORION-2U | DVT | ORI-D-0023 | ST-08 | Memory | ECC injection | Fail | Error not logged in SEL | 230 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R00950 | 2026-07-17 | Night | ORION-2U | DVT | ORI-D-0009 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 72 | 30 | 2.3.1 | O1.02 | MemCo-A | A2605
R00951 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0001 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 162 | 35 | 2.3.1 | V1.02 | Dramtek | D2606
R00952 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-04 | Memory | ECC injection | Pass |  | 673 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00953 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3085 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R00954 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0004 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 68 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R00955 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0020 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 30 | 2.3.1 | V1.02 | MemCo-A | A2605
R00956 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R00957 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-06 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R00958 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R00959 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3085 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R00960 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00961 | 2026-07-17 | Night | VEGA-1U | EVT | VEG-E-0013 | ST-03 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 997 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R00962 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 58 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R00963 | 2026-07-17 | Day | VEGA-1U | EVT | VEG-E-0022 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 188 | 35 | 2.3.1 | V1.02 | Dramtek | D2606
R00964 | 2026-07-17 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 251 | 22 | 2.3.1 | L1.02 | MemCo-B | B2607
R00965 | 2026-07-17 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R00966 | 2026-07-17 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-05 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 175 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R00967 | 2026-07-17 | Night | LYRA-4U | EVT | LYR-E-0001 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 164 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R00968 | 2026-07-17 | Night | LYRA-4U | EVT | LYR-E-0003 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 35 | 2.3.1 | L1.02 | MemCo-A | A2607
R00969 | 2026-07-17 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 228 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R00970 | 2026-07-18 | Day | ORION-2U | DVT | ORI-D-0008 | ST-07 | Network | NIC throughput 100G | Pass |  | 59 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R00971 | 2026-07-18 | Night | ORION-2U | DVT | ORI-D-0027 | TC-02 | Thermal | Thermal chamber | Pass |  | 162 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R00972 | 2026-07-18 | Night | ORION-2U | DVT | ORI-D-0001 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R00973 | 2026-07-18 | Night | ORION-2U | DVT | ORI-D-0035 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R00974 | 2026-07-18 | Day | ORION-2U | DVT | ORI-D-0038 | ST-02 | Network | NIC throughput 100G | Pass |  | 63 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R00975 | 2026-07-18 | Night | ORION-2U | DVT | ORI-D-0029 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 40 | 35 | 2.3.1 | O1.02 | MemCo-A | A2605
R00976 | 2026-07-18 | Day | ORION-2U | DVT | ORI-D-0021 | ST-07 | Memory | Memtest stress 12h | Pass |  | 751 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R00977 | 2026-07-18 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-08 | Network | Link flap test | Pass |  | 56 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R00978 | 2026-07-18 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-04 | Memory | Memtest stress 12h | Pass |  | 665 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R00979 | 2026-07-18 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3060 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R00980 | 2026-07-18 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-02 | Memory | ECC injection | Pass |  | 775 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00981 | 2026-07-18 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R00982 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 242 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R00983 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 218 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R00984 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 24 | 2.3.1 | L1.02 | MemCo-A | A2605
R00985 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 261 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R00986 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-02 | Power-on/POST | AC cycle 500x | Fail | No POST | 9 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R00987 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-04 | Network | NIC throughput 100G | Pass |  | 55 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R00988 | 2026-07-18 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 54 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R00989 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0014 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2757 | 23 | 2.3.1 | L1.02 | MemCo-B | B2604
R00990 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R00991 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-06 | Memory | ECC injection | Pass |  | 774 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R00992 | 2026-07-18 | Day | LYRA-4U | EVT | LYR-E-0010 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 98 | 30 | 2.3.1 | L1.02 | MemCo-B | B2604
R00993 | 2026-07-19 | Day | ORION-2U | DVT | ORI-D-0007 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2638 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R00994 | 2026-07-19 | Day | ORION-2U | DVT | ORI-D-0030 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 250 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R00995 | 2026-07-19 | Day | ORION-2U | DVT | ORI-D-0018 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 64 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R00996 | 2026-07-19 | Night | ORION-2U | DVT | ORI-D-0020 | ST-02 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 18 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R00997 | 2026-07-19 | Night | ORION-2U | DVT | ORI-D-0006 | ST-10 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R00998 | 2026-07-19 | Day | ORION-2U | DVT | ORI-D-0032 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R00999 | 2026-07-19 | Night | ORION-2U | DVT | ORI-D-0027 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 61 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R01000 | 2026-07-19 | Night | ORION-2U | DVT | ORI-D-0016 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R01001 | 2026-07-19 | Day | ORION-2U | DVT | ORI-D-0022 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 261 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01002 | 2026-07-19 | Night | VEGA-1U | EVT | VEG-E-0004 | ST-10 | Memory | Memtest stress 12h | Pass |  | 719 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01003 | 2026-07-19 | Night | VEGA-1U | EVT | VEG-E-0013 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 59 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01004 | 2026-07-19 | Day | VEGA-1U | EVT | VEG-E-0013 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 82 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R01005 | 2026-07-19 | Night | VEGA-1U | EVT | VEG-E-0007 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01006 | 2026-07-19 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-03 | Network | NIC throughput 100G | Pass |  | 63 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01007 | 2026-07-19 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-01 | Memory | Memtest stress 12h | Pass |  | 692 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01008 | 2026-07-19 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01009 | 2026-07-19 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-09 | Network | Link flap test | Pass |  | 62 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R01010 | 2026-07-19 | Night | LYRA-4U | EVT | LYR-E-0021 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 240 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01011 | 2026-07-19 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-06 | Network | NIC throughput 100G | Pass |  | 63 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01012 | 2026-07-19 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 257 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01013 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0007 | ST-08 | Network | Link flap test | Fail | Link down | 45 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01014 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0023 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 195 | 35 | 2.3.1 | O1.02 | MemCo-A | A2605
R01015 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0018 | ST-04 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01016 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0015 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 113 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01017 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0019 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3039 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01018 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0031 | ST-05 | Network | Link flap test | Pass |  | 56 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01019 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0006 | ST-10 | Memory | Memtest stress 12h | Pass |  | 755 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01020 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0040 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 35 | 2.3.1 | O1.02 | MemCo-B | B2604
R01021 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0002 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 245 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01022 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0019 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01023 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0027 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2695 | 23 | 2.3.1 | O1.02 | Dramtek | D2606
R01024 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0028 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 24 | 2.3.1 | O1.02 | MemCo-B | B2607
R01025 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0017 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01026 | 2026-07-20 | Night | ORION-2U | DVT | ORI-D-0033 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 54 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01027 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0021 | TC-02 | Thermal | Thermal chamber | Pass |  | 186 | 35 | 2.3.1 | O1.02 | MemCo-A | A2605
R01028 | 2026-07-20 | Day | ORION-2U | DVT | ORI-D-0018 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 87 | 35 | 2.3.1 | O1.02 | MemCo-A | A2607
R01029 | 2026-07-20 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-07 | Memory | ECC injection | Pass |  | 659 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01030 | 2026-07-20 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2944 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R01031 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0004 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 30 | 2.3.1 | V1.02 | Dramtek | D2606
R01032 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0020 | TC-01 | Thermal | Thermal chamber | Pass |  | 163 | 30 | 2.3.1 | V1.02 | MemCo-A | A2605
R01033 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-10 | Memory | Memtest stress 12h | Pass |  | 770 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01034 | 2026-07-20 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2826 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01035 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-07 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.3.1 | V1.02 | MemCo-B | B2604
R01036 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 57 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01037 | 2026-07-20 | Day | VEGA-1U | EVT | VEG-E-0013 | TC-02 | Thermal | Thermal chamber | Pass |  | 189 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01038 | 2026-07-20 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 55 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01039 | 2026-07-20 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01040 | 2026-07-20 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 229 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01041 | 2026-07-20 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01042 | 2026-07-20 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R01043 | 2026-07-20 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 54 | 22 | 2.3.1 | L1.02 | Dramtek | D2606
R01044 | 2026-07-20 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-09 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 38 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01045 | 2026-07-20 | Night | LYRA-4U | EVT | LYR-E-0018 | ST-04 | Network | NIC throughput 100G | Pass |  | 60 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01046 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0020 | ST-05 | Memory | Memtest stress 12h | Pass |  | 690 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01047 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0026 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 217 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R01048 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0036 | ST-06 | Memory | Memtest stress 12h | Pass |  | 754 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01049 | 2026-07-21 | Night | ORION-2U | DVT | ORI-D-0002 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01050 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0008 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2963 | 24 | 2.3.1 | O1.02 | MemCo-B | B2607
R01051 | 2026-07-21 | Night | ORION-2U | DVT | ORI-D-0027 | TC-01 | Thermal | Thermal chamber | Pass |  | 183 | 35 | 2.3.1 | O1.02 | Dramtek | D2606
R01052 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0004 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01053 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0027 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 38 | 35 | 2.3.1 | O1.02 | Dramtek | D2606
R01054 | 2026-07-21 | Night | ORION-2U | DVT | ORI-D-0029 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3074 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01055 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0021 | ST-07 | Memory | Memtest stress 12h | Pass |  | 766 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R01056 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0023 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01057 | 2026-07-21 | Night | ORION-2U | DVT | ORI-D-0025 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 59 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01058 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0027 | ST-02 | Network | Link flap test | Pass |  | 62 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R01059 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0017 | ST-06 | Network | Link flap test | Pass |  | 64 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01060 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0001 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 185 | 35 | 2.3.1 | O1.02 | MemCo-A | A2605
R01061 | 2026-07-21 | Day | ORION-2U | DVT | ORI-D-0031 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2945 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01062 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-01 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1582 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01063 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01064 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-04 | Memory | Memtest stress 12h | Pass |  | 691 | 24 | 2.3.1 | V1.02 | MemCo-B | B2604
R01065 | 2026-07-21 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-01 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 2193 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01066 | 2026-07-21 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-05 | Memory | ECC injection | Pass |  | 660 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R01067 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0013 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 128 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R01068 | 2026-07-21 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-09 | Network | Link flap test | Pass |  | 54 | 23 | 2.3.1 | V1.02 | MemCo-B | B2607
R01069 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 25 | 2.3.1 | V1.02 | MemCo-B | B2607
R01070 | 2026-07-21 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-08 | Network | NIC throughput 100G | Pass |  | 55 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01071 | 2026-07-21 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-06 | Memory | Memtest stress 12h | Pass |  | 782 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01072 | 2026-07-21 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-07 | Power-on/POST | AC cycle 500x | Fail | No POST | 27 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R01073 | 2026-07-21 | Night | LYRA-4U | EVT | LYR-E-0024 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 223 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01074 | 2026-07-21 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2973 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R01075 | 2026-07-21 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-05 | Network | Link flap test | Pass |  | 54 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01076 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0008 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | O1.02 | MemCo-B | B2607
R01077 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0035 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01078 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0001 | ST-09 | Storage | NVMe hot-plug | Pass |  | 55 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01079 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0015 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01080 | 2026-07-22 | Night | ORION-2U | DVT | ORI-D-0027 | ST-07 | Storage | FIO random R/W | Pass |  | 62 | 24 | 2.3.1 | O1.02 | Dramtek | D2606
R01081 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0017 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 64 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R01082 | 2026-07-22 | Night | ORION-2U | DVT | ORI-D-0024 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2941 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R01083 | 2026-07-22 | Night | ORION-2U | DVT | ORI-D-0022 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 182 | 35 | 2.3.1 | O1.02 | MemCo-A | A2607
R01084 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0003 | ST-04 | Memory | ECC injection | Pass |  | 773 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R01085 | 2026-07-22 | Day | ORION-2U | DVT | ORI-D-0018 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01086 | 2026-07-22 | Night | VEGA-1U | EVT | VEG-E-0007 | TC-02 | Thermal | Thermal chamber | Pass |  | 181 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R01087 | 2026-07-22 | Night | VEGA-1U | EVT | VEG-E-0004 | TC-01 | Thermal | Thermal chamber | Pass |  | 193 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01088 | 2026-07-22 | Night | VEGA-1U | EVT | VEG-E-0018 | ST-01 | Storage | NVMe hot-plug | Pass |  | 56 | 22 | 2.3.1 | V1.02 | MemCo-B | B2607
R01089 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0016 | TC-02 | Thermal | Thermal chamber | Pass |  | 164 | 30 | 2.3.1 | V1.02 | MemCo-A | A2607
R01090 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-01 | Memory | Memtest stress 12h | Pass |  | 755 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01091 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01092 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-09 | Network | Link flap test | Pass |  | 58 | 24 | 2.3.1 | V1.02 | MemCo-B | B2607
R01093 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-03 | Network | NIC throughput 100G | Pass |  | 59 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01094 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2722 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01095 | 2026-07-22 | Night | VEGA-1U | EVT | VEG-E-0020 | ST-10 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 44 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01096 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-07 | Memory | ECC injection | Pass |  | 702 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01097 | 2026-07-22 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2771 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01098 | 2026-07-22 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-06 | Memory | ECC injection | Pass |  | 664 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01099 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-01 | Network | Link flap test | Pass |  | 58 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R01100 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R01101 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01102 | 2026-07-22 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-04 | Network | Link flap test | Pass |  | 63 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01103 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2609 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01104 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 170 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01105 | 2026-07-22 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2702 | 22 | 2.3.1 | L1.02 | MemCo-B | B2607
R01106 | 2026-07-23 | Day | ORION-2U | DVT | ORI-D-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 23 | 35 | 2.3.1 | O1.02 | MemCo-A | A2605
R01107 | 2026-07-23 | Night | ORION-2U | DVT | ORI-D-0021 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01108 | 2026-07-23 | Day | ORION-2U | DVT | ORI-D-0015 | ST-10 | Memory | ECC injection | Pass |  | 762 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R01109 | 2026-07-23 | Day | ORION-2U | DVT | ORI-D-0006 | ST-08 | Network | Link flap test | Pass |  | 62 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01110 | 2026-07-23 | Night | ORION-2U | DVT | ORI-D-0036 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01111 | 2026-07-23 | Day | ORION-2U | DVT | ORI-D-0004 | ST-03 | Memory | Memtest stress 12h | Pass |  | 750 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01112 | 2026-07-23 | Night | ORION-2U | DVT | ORI-D-0020 | ST-01 | Memory | Memtest stress 12h | Pass |  | 670 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01113 | 2026-07-23 | Day | ORION-2U | DVT | ORI-D-0023 | ST-05 | Memory | Memtest stress 12h | Pass |  | 733 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01114 | 2026-07-23 | Night | ORION-2U | DVT | ORI-D-0017 | TC-02 | Thermal | Thermal chamber | Pass |  | 172 | 30 | 2.3.1 | O1.02 | MemCo-A | A2607
R01115 | 2026-07-23 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | V1.02 | MemCo-B | B2607
R01116 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0012 | ST-04 | Network | NIC throughput 100G | Pass |  | 60 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01117 | 2026-07-23 | Day | VEGA-1U | EVT | VEG-E-0005 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R01118 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0021 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3085 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01119 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0014 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.3.1 | V1.02 | MemCo-B | B2607
R01120 | 2026-07-23 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-08 | Network | NIC throughput 100G | Pass |  | 58 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01121 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0013 | ST-07 | Network | NIC throughput 100G | Pass |  | 57 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01122 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 243 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01123 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0017 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 237 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01124 | 2026-07-23 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2702 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01125 | 2026-07-23 | Night | LYRA-4U | EVT | LYR-E-0016 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 128 | 35 | 2.3.1 | L1.02 | MemCo-B | B2604
R01126 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0006 | TC-01 | Thermal | Thermal chamber | Pass |  | 184 | 30 | 2.3.1 | L1.02 | MemCo-A | A2607
R01127 | 2026-07-23 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R01128 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-09 | Memory | ECC injection | Pass |  | 740 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01129 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-04 | Memory | Memtest stress 12h | Pass |  | 768 | 23 | 2.3.1 | L1.02 | Dramtek | D2606
R01130 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-02 | Network | NIC throughput 100G | Pass |  | 58 | 23 | 2.3.1 | L1.02 | Dramtek | D2606
R01131 | 2026-07-23 | Night | LYRA-4U | EVT | LYR-E-0009 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R01132 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3044 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R01133 | 2026-07-23 | Day | LYRA-4U | EVT | LYR-E-0015 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 80 | 35 | 2.3.1 | L1.02 | Dramtek | D2606
R01134 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0024 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2875 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01135 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0029 | ST-07 | Network | Link flap test | Fail | Link down | 27 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01136 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0028 | TC-01 | Thermal | Thermal chamber | Pass |  | 195 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R01137 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0025 | ST-07 | Network | Link flap test | Pass |  | 56 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01138 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0023 | TC-02 | Thermal | Thermal chamber | Pass |  | 165 | 30 | 2.3.1 | O1.02 | MemCo-A | A2605
R01139 | 2026-07-24 | Day | ORION-2U | DVT | ORI-D-0023 | ST-06 | Network | Link flap test | Pass |  | 63 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01140 | 2026-07-24 | Night | ORION-2U | DVT | ORI-D-0032 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01141 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-08 | Memory | Memtest stress 12h | Pass |  | 749 | 23 | 2.3.1 | V1.02 | Dramtek | D2606
R01142 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2641 | 24 | 2.3.1 | V1.02 | MemCo-B | B2604
R01143 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01144 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0002 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 22 | 2.3.1 | V1.02 | MemCo-B | B2604
R01145 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-10 | Memory | ECC injection | Pass |  | 676 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01146 | 2026-07-24 | Night | VEGA-1U | EVT | VEG-E-0006 | ST-02 | Storage | FIO random R/W | Fail | IOPS below spec | 24 | 24 | 2.3.1 | V1.02 | MemCo-B | B2607
R01147 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0021 | TC-01 | Thermal | Thermal chamber | Pass |  | 165 | 30 | 2.3.1 | V1.02 | MemCo-A | A2605
R01148 | 2026-07-24 | Day | VEGA-1U | EVT | VEG-E-0017 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 186 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01149 | 2026-07-24 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 235 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R01150 | 2026-07-24 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-06 | Memory | Memtest stress 12h | Pass |  | 652 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01151 | 2026-07-24 | Day | LYRA-4U | EVT | LYR-E-0014 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 233 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01152 | 2026-07-24 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-08 | Memory | Memtest stress 12h | Pass |  | 741 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01153 | 2026-07-24 | Day | LYRA-4U | EVT | LYR-E-0004 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 41 | 30 | 2.3.1 | L1.02 | MemCo-A | A2605
R01154 | 2026-07-24 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 13 | 23 | 2.3.1 | L1.02 | MemCo-B | B2604
R01155 | 2026-07-24 | Night | LYRA-4U | EVT | LYR-E-0018 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 256 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01156 | 2026-07-24 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-01 | Memory | Memtest stress 12h | Pass |  | 748 | 24 | 2.3.1 | L1.02 | MemCo-A | A2605
R01157 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 187 | 30 | 2.3.1 | O1.02 | MemCo-A | A2605
R01158 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0031 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 169 | 30 | 2.3.1 | O1.02 | MemCo-B | B2604
R01159 | 2026-07-25 | Day | ORION-2U | DVT | ORI-D-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 197 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01160 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0036 | ST-07 | Memory | Memtest stress 12h | Pass |  | 711 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01161 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0035 | ST-07 | Power-on/POST | AC cycle 500x | Fail | No POST | 45 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01162 | 2026-07-25 | Day | ORION-2U | DVT | ORI-D-0038 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01163 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0008 | TC-02 | Thermal | Thermal chamber | Pass |  | 171 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R01164 | 2026-07-25 | Night | ORION-2U | DVT | ORI-D-0008 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.3.1 | O1.02 | MemCo-B | B2607
R01165 | 2026-07-25 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R01166 | 2026-07-25 | Day | VEGA-1U | EVT | VEG-E-0021 | ST-10 | Memory | Memtest stress 12h | Pass |  | 742 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01167 | 2026-07-25 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-07 | Power-on/POST | AC cycle 500x | Fail | No POST | 40 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R01168 | 2026-07-25 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-06 | Storage | FIO random R/W | Pass |  | 61 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01169 | 2026-07-25 | Night | VEGA-1U | EVT | VEG-E-0009 | ST-05 | Storage | FIO random R/W | Pass |  | 58 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01170 | 2026-07-25 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R01171 | 2026-07-25 | Night | LYRA-4U | EVT | LYR-E-0001 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R01172 | 2026-07-25 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 57 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R01173 | 2026-07-25 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2888 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01174 | 2026-07-25 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2952 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01175 | 2026-07-25 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-04 | Storage | FIO random R/W | Pass |  | 63 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01176 | 2026-07-25 | Night | LYRA-4U | EVT | LYR-E-0021 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 35 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01177 | 2026-07-26 | Night | ORION-2U | DVT | ORI-D-0037 | ST-10 | Network | Link flap test | Pass |  | 57 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01178 | 2026-07-26 | Night | ORION-2U | DVT | ORI-D-0034 | ST-06 | Memory | Memtest stress 12h | Pass |  | 700 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01179 | 2026-07-26 | Day | ORION-2U | DVT | ORI-D-0026 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 30 | 2.3.1 | O1.02 | MemCo-A | A2607
R01180 | 2026-07-26 | Night | ORION-2U | DVT | ORI-D-0023 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01181 | 2026-07-26 | Day | ORION-2U | DVT | ORI-D-0010 | ST-03 | Memory | Memtest stress 12h | Pass |  | 757 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01182 | 2026-07-26 | Day | ORION-2U | DVT | ORI-D-0023 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 228 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01183 | 2026-07-26 | Day | ORION-2U | DVT | ORI-D-0004 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 261 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01184 | 2026-07-26 | Night | ORION-2U | DVT | ORI-D-0010 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01185 | 2026-07-26 | Day | ORION-2U | DVT | ORI-D-0016 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 24 | 2.3.1 | O1.02 | Dramtek | D2606
R01186 | 2026-07-26 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01187 | 2026-07-26 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01188 | 2026-07-26 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-01 | Network | Link flap test | Fail | Link down | 9 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01189 | 2026-07-26 | Night | VEGA-1U | EVT | VEG-E-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01190 | 2026-07-26 | Night | VEGA-1U | EVT | VEG-E-0016 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 171 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01191 | 2026-07-26 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-06 | Storage | FIO random R/W | Pass |  | 59 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01192 | 2026-07-26 | Day | LYRA-4U | EVT | LYR-E-0011 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 83 | 30 | 2.3.1 | L1.02 | MemCo-B | B2607
R01193 | 2026-07-26 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-04 | Network | Link flap test | Pass |  | 62 | 24 | 2.3.1 | L1.02 | MemCo-A | A2607
R01194 | 2026-07-26 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 105 | 35 | 2.3.1 | L1.02 | MemCo-A | A2607
R01195 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0011 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01196 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0036 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3145 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01197 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0038 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01198 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0031 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2744 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01199 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0032 | TC-01 | Thermal | Thermal chamber | Pass |  | 190 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01200 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0025 | ST-06 | Memory | ECC injection | Pass |  | 707 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01201 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0021 | TC-02 | Thermal | Thermal chamber | Pass |  | 192 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01202 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0014 | ST-10 | Memory | Memtest stress 12h | Pass |  | 727 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R01203 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0008 | ST-10 | Storage | FIO random R/W | Pass |  | 61 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R01204 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0038 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01205 | 2026-07-27 | Day | ORION-2U | DVT | ORI-D-0035 | ST-07 | Power-on/POST | AC cycle 500x | Fail | No POST | 24 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01206 | 2026-07-27 | Night | ORION-2U | DVT | ORI-D-0022 | ST-08 | Memory | Memtest stress 12h | Pass |  | 790 | 24 | 2.3.1 | O1.02 | MemCo-A | A2607
R01207 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3068 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01208 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0017 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 22 | 2.3.1 | V1.02 | MemCo-A | A2605
R01209 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.1 | V1.02 | MemCo-B | B2604
R01210 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 23 | 2.3.1 | V1.02 | MemCo-B | B2607
R01211 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0006 | ST-01 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 146 | 25 | 2.3.1 | V1.02 | MemCo-B | B2607
R01212 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0019 | ST-08 | Network | Link flap test | Pass |  | 61 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R01213 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 172 | 35 | 2.3.1 | V1.02 | MemCo-A | A2605
R01214 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-09 | Network | Link flap test | Pass |  | 56 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01215 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0009 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01216 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-01 | Storage | FIO random R/W | Pass |  | 54 | 24 | 2.3.1 | V1.02 | Dramtek | D2606
R01217 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-02 | Memory | ECC injection | Pass |  | 757 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01218 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0014 | ST-08 | Network | NIC throughput 100G | Pass |  | 54 | 23 | 2.3.1 | V1.02 | MemCo-B | B2607
R01219 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 219 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01220 | 2026-07-27 | Day | VEGA-1U | EVT | VEG-E-0022 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 172 | 35 | 2.3.1 | V1.02 | Dramtek | D2606
R01221 | 2026-07-27 | Night | VEGA-1U | EVT | VEG-E-0008 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 30 | 2.3.1 | V1.02 | MemCo-A | A2605
R01222 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-06 | Storage | NVMe hot-plug | Pass |  | 57 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01223 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-04 | Network | Link flap test | Pass |  | 55 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01224 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-04 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 178 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01225 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0013 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 126 | 35 | 2.3.1 | L1.02 | MemCo-A | A2605
R01226 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 251 | 25 | 2.3.1 | L1.02 | MemCo-B | B2604
R01227 | 2026-07-27 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-01 | PCIe/GPU | PCIe link training | Pass |  | 232 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01228 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0011 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 92 | 35 | 2.3.1 | L1.02 | MemCo-B | B2607
R01229 | 2026-07-27 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3099 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01230 | 2026-07-27 | Night | LYRA-4U | EVT | LYR-E-0017 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 188 | 30 | 2.3.1 | L1.02 | MemCo-B | B2607
R01231 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-01 | Memory | ECC injection | Pass |  | 687 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R01232 | 2026-07-27 | Day | LYRA-4U | EVT | LYR-E-0001 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 94 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R01233 | 2026-07-28 | Day | ORION-2U | DVT | ORI-D-0020 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 65 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01234 | 2026-07-28 | Day | ORION-2U | DVT | ORI-D-0020 | ST-09 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 17 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01235 | 2026-07-28 | Day | ORION-2U | DVT | ORI-D-0038 | ST-02 | Storage | NVMe hot-plug | Pass |  | 62 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01236 | 2026-07-28 | Night | ORION-2U | DVT | ORI-D-0003 | ST-09 | Memory | ECC injection | Pass |  | 745 | 22 | 2.3.1 | O1.02 | Dramtek | D2606
R01237 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0001 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 30 | 2.3.1 | V1.02 | Dramtek | D2606
R01238 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-06 | Network | NIC throughput 100G | Pass |  | 54 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01239 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01240 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-02 | Network | Link flap test | Pass |  | 60 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01241 | 2026-07-28 | Night | VEGA-1U | EVT | VEG-E-0006 | TC-01 | Thermal | Thermal chamber | Pass |  | 163 | 35 | 2.3.1 | V1.02 | MemCo-B | B2607
R01242 | 2026-07-28 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-10 | Network | Link flap test | Pass |  | 61 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01243 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 3040 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01244 | 2026-07-28 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2911 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01245 | 2026-07-28 | Night | VEGA-1U | EVT | VEG-E-0008 | ST-08 | Network | Link flap test | Pass |  | 60 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01246 | 2026-07-28 | Night | VEGA-1U | EVT | VEG-E-0020 | ST-07 | Memory | ECC injection | Pass |  | 715 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01247 | 2026-07-28 | Night | VEGA-1U | EVT | VEG-E-0011 | ST-04 | Memory | ECC injection | Pass |  | 715 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01248 | 2026-07-28 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-10 | Network | Link flap test | Pass |  | 60 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01249 | 2026-07-28 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 217 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R01250 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0022 | TC-02 | Thermal | Thermal chamber | Pass |  | 187 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R01251 | 2026-07-28 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 223 | 25 | 2.3.1 | L1.02 | MemCo-A | A2607
R01252 | 2026-07-28 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-10 | Storage | FIO random R/W | Pass |  | 57 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01253 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R01254 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-10 | Storage | NVMe hot-plug | Pass |  | 58 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R01255 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 115 | 35 | 2.3.1 | L1.02 | MemCo-A | A2607
R01256 | 2026-07-28 | Day | LYRA-4U | EVT | LYR-E-0016 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 162 | 25 | 2.3.1 | L1.02 | MemCo-B | B2604
R01257 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0024 | ST-10 | Memory | ECC injection | Pass |  | 718 | 24 | 2.3.1 | L1.02 | MemCo-A | A2605
R01258 | 2026-07-28 | Night | LYRA-4U | EVT | LYR-E-0022 | ST-02 | Memory | ECC injection | Pass |  | 701 | 23 | 2.3.1 | L1.02 | MemCo-B | B2607
R01259 | 2026-07-29 | Day | ORION-2U | DVT | ORI-D-0040 | ST-02 | Memory | ECC injection | Pass |  | 693 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01260 | 2026-07-29 | Day | ORION-2U | DVT | ORI-D-0023 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01261 | 2026-07-29 | Night | ORION-2U | DVT | ORI-D-0028 | TC-02 | Thermal | Thermal chamber | Pass |  | 186 | 25 | 2.3.1 | O1.02 | MemCo-B | B2607
R01262 | 2026-07-29 | Day | ORION-2U | DVT | ORI-D-0035 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2899 | 22 | 2.3.1 | O1.02 | MemCo-A | A2607
R01263 | 2026-07-29 | Night | ORION-2U | DVT | ORI-D-0016 | ST-06 | Storage | NVMe hot-plug | Pass |  | 56 | 23 | 2.3.1 | O1.02 | Dramtek | D2606
R01264 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0004 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01265 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0003 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01266 | 2026-07-29 | Night | VEGA-1U | EVT | VEG-E-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01267 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3121 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01268 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01269 | 2026-07-29 | Night | VEGA-1U | EVT | VEG-E-0003 | ST-09 | Memory | Memtest stress 12h | Pass |  | 723 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01270 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-07 | Memory | Memtest stress 12h | Pass |  | 790 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01271 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3166 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01272 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-06 | Memory | ECC injection | Pass |  | 777 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01273 | 2026-07-29 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-07 | Memory | Memtest stress 12h | Pass |  | 698 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01274 | 2026-07-29 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 22 | 2.3.1 | L1.02 | Dramtek | D2606
R01275 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2975 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01276 | 2026-07-29 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 218 | 22 | 2.3.1 | L1.02 | MemCo-A | A2607
R01277 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 61 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R01278 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 24 | 2.3.1 | L1.02 | MemCo-A | A2605
R01279 | 2026-07-29 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 61 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R01280 | 2026-07-29 | Night | LYRA-4U | EVT | LYR-E-0004 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 184 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01281 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-07 | Memory | Memtest stress 12h | Pass |  | 701 | 24 | 2.3.1 | L1.02 | Dramtek | D2606
R01282 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-02 | Memory | ECC injection | Pass |  | 682 | 23 | 2.3.1 | L1.02 | MemCo-A | A2607
R01283 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-07 | Network | NIC throughput 100G | Fail | Link down | 27 | 25 | 2.3.1 | L1.02 | Dramtek | D2606
R01284 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | L1.02 | MemCo-A | A2605
R01285 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 56 | 24 | 2.3.1 | L1.02 | MemCo-A | A2607
R01286 | 2026-07-29 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3007 | 23 | 2.3.1 | L1.02 | MemCo-B | B2604
R01287 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01288 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2888 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R01289 | 2026-07-29 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 237 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R01290 | 2026-07-30 | Night | ORION-2U | DVT | ORI-D-0020 | ST-09 | Memory | Memtest stress 12h | Pass |  | 786 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01291 | 2026-07-30 | Day | ORION-2U | DVT | ORI-D-0033 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 30 | 2.3.1 | O1.02 | MemCo-A | A2605
R01292 | 2026-07-30 | Day | ORION-2U | DVT | ORI-D-0024 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01293 | 2026-07-30 | Night | ORION-2U | DVT | ORI-D-0034 | ST-06 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 46 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01294 | 2026-07-30 | Night | ORION-2U | DVT | ORI-D-0002 | ST-07 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 126 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01295 | 2026-07-30 | Day | ORION-2U | DVT | ORI-D-0023 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01296 | 2026-07-30 | Day | ORION-2U | DVT | ORI-D-0006 | ST-06 | Storage | NVMe hot-plug | Pass |  | 63 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01297 | 2026-07-30 | Night | ORION-2U | DVT | ORI-D-0018 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01298 | 2026-07-30 | Day | ORION-2U | DVT | ORI-D-0004 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3127 | 22 | 2.3.1 | O1.02 | MemCo-B | B2604
R01299 | 2026-07-30 | Night | ORION-2U | DVT | ORI-D-0011 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 138 | 30 | 2.3.1 | O1.02 | MemCo-A | A2607
R01300 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0023 | ST-10 | Memory | ECC injection | Pass |  | 692 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01301 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0006 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 10 | 25 | 2.3.1 | V1.02 | MemCo-B | B2607
R01302 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-07 | Network | Link flap test | Fail | Link down | 37 | 24 | 2.3.1 | V1.02 | Dramtek | D2606
R01303 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0002 | TC-01 | Thermal | Thermal chamber | Pass |  | 197 | 30 | 2.3.1 | V1.02 | MemCo-B | B2604
R01304 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 63 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01305 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-08 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 15 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01306 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0013 | ST-09 | Memory | Memtest stress 12h | Pass |  | 664 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01307 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0011 | ST-02 | Storage | FIO random R/W | Pass |  | 55 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01308 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0005 | ST-06 | Storage | NVMe hot-plug | Pass |  | 60 | 22 | 2.3.1 | V1.02 | MemCo-B | B2604
R01309 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | V1.02 | Dramtek | D2606
R01310 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 184 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01311 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0020 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01312 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-05 | Memory | ECC injection | Pass |  | 763 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01313 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0022 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01314 | 2026-07-30 | Day | VEGA-1U | EVT | VEG-E-0018 | ST-03 | Memory | ECC injection | Pass |  | 665 | 23 | 2.3.1 | V1.02 | MemCo-B | B2607
R01315 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-08 | Storage | FIO random R/W | Pass |  | 64 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01316 | 2026-07-30 | Night | VEGA-1U | EVT | VEG-E-0016 | ST-06 | Network | Link flap test | Pass |  | 63 | 22 | 2.3.1 | V1.02 | MemCo-A | A2607
R01317 | 2026-07-30 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01318 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 24 | 2.3.1 | L1.02 | MemCo-A | A2607
R01319 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.1 | L1.02 | MemCo-B | B2607
R01320 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-10 | Network | NIC throughput 100G | Pass |  | 56 | 22 | 2.3.1 | L1.02 | MemCo-A | A2605
R01321 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0003 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 40 | 30 | 2.3.1 | L1.02 | MemCo-A | A2607
R01322 | 2026-07-30 | Night | LYRA-4U | EVT | LYR-E-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 186 | 30 | 2.3.1 | L1.02 | MemCo-A | A2607
R01323 | 2026-07-30 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01324 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-01 | Memory | Memtest stress 12h | Pass |  | 665 | 23 | 2.3.1 | L1.02 | Dramtek | D2606
R01325 | 2026-07-30 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 126 | 35 | 2.3.1 | L1.02 | MemCo-A | A2607
R01326 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0024 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 190 | 25 | 2.3.1 | L1.02 | MemCo-A | A2605
R01327 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R01328 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 25 | 2.3.1 | L1.02 | MemCo-B | B2604
R01329 | 2026-07-30 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 229 | 25 | 2.3.1 | L1.02 | MemCo-B | B2604
R01330 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0010 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01331 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0030 | ST-04 | Storage | NVMe hot-plug | Pass |  | 55 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01332 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0014 | ST-02 | Memory | ECC injection | Pass |  | 712 | 22 | 2.3.1 | O1.02 | MemCo-A | A2605
R01333 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0003 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 25 | 2.3.1 | O1.02 | Dramtek | D2606
R01334 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0034 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 222 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01335 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0021 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 3072 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R01336 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0008 | ST-05 | Memory | Memtest stress 12h | Pass |  | 756 | 24 | 2.3.1 | O1.02 | MemCo-B | B2607
R01337 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0010 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 36 | 25 | 2.3.1 | O1.02 | MemCo-B | B2604
R01338 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0034 | ST-03 | Memory | Memtest stress 12h | Pass |  | 738 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01339 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0009 | ST-03 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 20 | 24 | 2.3.1 | O1.02 | MemCo-A | A2605
R01340 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0023 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 105 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01341 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 175 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01342 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0009 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 23 | 2.3.1 | O1.02 | MemCo-A | A2605
R01343 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0010 | ST-04 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.3.1 | O1.02 | MemCo-B | B2604
R01344 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0019 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | O1.02 | MemCo-A | A2607
R01345 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 170 | 25 | 2.3.1 | O1.02 | MemCo-A | A2605
R01346 | 2026-07-31 | Night | ORION-2U | DVT | ORI-D-0004 | TC-02 | Thermal | Thermal chamber | Pass |  | 179 | 30 | 2.3.1 | O1.02 | MemCo-B | B2604
R01347 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0006 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.3.1 | O1.02 | MemCo-B | B2604
R01348 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0039 | TC-02 | Thermal | Thermal chamber | Pass |  | 187 | 30 | 2.3.1 | O1.02 | Dramtek | D2606
R01349 | 2026-07-31 | Day | ORION-2U | DVT | ORI-D-0017 | ST-09 | Memory | Memtest stress 12h | Pass |  | 787 | 25 | 2.3.1 | O1.02 | MemCo-A | A2607
R01350 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0010 | ST-03 | Network | NIC throughput 100G | Fail | Throughput below spec | 34 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01351 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0022 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 59 | 25 | 2.3.1 | V1.02 | Dramtek | D2606
R01352 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2626 | 24 | 2.3.1 | V1.02 | Dramtek | D2606
R01353 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0008 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01354 | 2026-07-31 | Night | VEGA-1U | EVT | VEG-E-0023 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01355 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0009 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 166 | 25 | 2.3.1 | V1.02 | MemCo-A | A2605
R01356 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-02 | Network | NIC throughput 100G | Pass |  | 61 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01357 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0001 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.3.1 | V1.02 | Dramtek | D2606
R01358 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0005 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 263 | 23 | 2.3.1 | V1.02 | MemCo-B | B2604
R01359 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0015 | ST-03 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.3.1 | V1.02 | MemCo-A | A2607
R01360 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0024 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 227 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01361 | 2026-07-31 | Night | VEGA-1U | EVT | VEG-E-0016 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 180 | 35 | 2.3.1 | V1.02 | MemCo-A | A2607
R01362 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0007 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 62 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01363 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0012 | ST-09 | Network | NIC throughput 100G | Pass |  | 54 | 25 | 2.3.1 | V1.02 | MemCo-A | A2607
R01364 | 2026-07-31 | Night | VEGA-1U | EVT | VEG-E-0024 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2688 | 22 | 2.3.1 | V1.02 | Dramtek | D2606
R01365 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0019 | ST-08 | Memory | ECC injection | Pass |  | 746 | 25 | 2.3.1 | V1.02 | MemCo-B | B2604
R01366 | 2026-07-31 | Night | VEGA-1U | EVT | VEG-E-0010 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.3.1 | V1.02 | MemCo-A | A2605
R01367 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0004 | ST-08 | Storage | NVMe hot-plug | Pass |  | 65 | 24 | 2.3.1 | V1.02 | Dramtek | D2606
R01368 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0016 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2874 | 23 | 2.3.1 | V1.02 | MemCo-A | A2607
R01369 | 2026-07-31 | Day | VEGA-1U | EVT | VEG-E-0017 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | V1.02 | MemCo-A | A2605
R01370 | 2026-07-31 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-04 | Memory | Memtest stress 12h | Pass |  | 764 | 24 | 2.3.1 | L1.02 | MemCo-A | A2605
R01371 | 2026-07-31 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-07 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 42 | 24 | 2.3.1 | L1.02 | MemCo-B | B2604
R01372 | 2026-07-31 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.1 | L1.02 | MemCo-B | B2607
R01373 | 2026-07-31 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 22 | 2.3.1 | L1.02 | MemCo-B | B2607
R01374 | 2026-07-31 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-09 | Memory | ECC injection | Pass |  | 678 | 22 | 2.3.1 | L1.02 | MemCo-B | B2604
R01375 | 2026-07-31 | Day | LYRA-4U | EVT | LYR-E-0015 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 35 | 2.3.1 | L1.02 | Dramtek | D2606
R01376 | 2026-08-01 | Day | ORION-2U | DVT | ORI-D-0001 | ST-10 | Storage | FIO random R/W | Pass |  | 63 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01377 | 2026-08-01 | Day | ORION-2U | DVT | ORI-D-0035 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01378 | 2026-08-01 | Night | ORION-2U | DVT | ORI-D-0017 | ST-02 | Network | Link flap test | Pass |  | 57 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01379 | 2026-08-01 | Day | ORION-2U | DVT | ORI-D-0036 | ST-07 | Network | NIC throughput 100G | Pass |  | 56 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01380 | 2026-08-01 | Night | ORION-2U | DVT | ORI-D-0012 | ST-03 | Memory | ECC injection | Pass |  | 737 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01381 | 2026-08-01 | Night | VEGA-1U | DVT | VEG-D-0010 | ST-05 | Network | Link flap test | Pass |  | 62 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01382 | 2026-08-01 | Night | VEGA-1U | DVT | VEG-D-0025 | ST-05 | Network | Link flap test | Pass |  | 62 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01383 | 2026-08-01 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01384 | 2026-08-01 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-04 | Memory | ECC injection | Pass |  | 743 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01385 | 2026-08-01 | Night | VEGA-1U | DVT | VEG-D-0027 | ST-06 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 1107 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01386 | 2026-08-01 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-03 | Storage | NVMe hot-plug | Pass |  | 55 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01387 | 2026-08-01 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-03 | Network | NIC throughput 100G | Pass |  | 64 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01388 | 2026-08-01 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01389 | 2026-08-01 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 245 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01390 | 2026-08-02 | Day | ORION-2U | DVT | ORI-D-0003 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01391 | 2026-08-02 | Day | ORION-2U | DVT | ORI-D-0010 | ST-06 | Memory | ECC injection | Pass |  | 746 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01392 | 2026-08-02 | Day | ORION-2U | DVT | ORI-D-0034 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01393 | 2026-08-02 | Day | ORION-2U | DVT | ORI-D-0029 | ST-01 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01394 | 2026-08-02 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-03 | Memory | Memtest stress 12h | Pass |  | 693 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01395 | 2026-08-02 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.3.1 | V1.05 | MemCo-A | A2605
R01396 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01397 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0024 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01398 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0025 | ST-01 | Network | Link flap test | Pass |  | 59 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01399 | 2026-08-02 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 263 | 25 | 2.3.1 | V1.05 | MemCo-B | B2604
R01400 | 2026-08-02 | Day | VEGA-1U | DVT | VEG-D-0025 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01401 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01402 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-10 | Storage | NVMe hot-plug | Pass |  | 61 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01403 | 2026-08-02 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-01 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01404 | 2026-08-02 | Night | LYRA-4U | EVT | LYR-E-0024 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 221 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01405 | 2026-08-02 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-10 | Network | Link flap test | Pass |  | 65 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01406 | 2026-08-02 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-07 | Network | NIC throughput 100G | Fail | Link down | 32 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01407 | 2026-08-02 | Night | LYRA-4U | EVT | LYR-E-0008 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 35 | 2.3.1 | L1.05 | MemCo-B | B2607
R01408 | 2026-08-02 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2903 | 24 | 2.3.1 | L1.05 | MemCo-B | B2604
R01409 | 2026-08-02 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-02 | Storage | FIO random R/W | Pass |  | 54 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01410 | 2026-08-02 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01411 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0023 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01412 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0007 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01413 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0035 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 58 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01414 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0029 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01415 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0020 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01416 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0020 | ST-03 | Memory | ECC injection | Pass |  | 731 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01417 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0019 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01418 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0024 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 162 | 35 | 2.3.1 | O1.05 | MemCo-A | A2605
R01419 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0034 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01420 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0004 | TC-02 | Thermal | Thermal chamber | Pass |  | 164 | 30 | 2.3.1 | O1.05 | MemCo-B | B2604
R01421 | 2026-08-03 | Day | ORION-2U | DVT | ORI-D-0031 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01422 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0033 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01423 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0032 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01424 | 2026-08-03 | Night | ORION-2U | DVT | ORI-D-0002 | ST-02 | Storage | NVMe hot-plug | Pass |  | 54 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01425 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-06 | Storage | FIO random R/W | Pass |  | 64 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01426 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01427 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0027 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01428 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-07 | Network | Link flap test | Fail | Link down | 30 | 24 | 2.3.1 | V1.05 | MemCo-A | A2605
R01429 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 235 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01430 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0006 | ST-09 | Network | NIC throughput 100G | Pass |  | 64 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01431 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01432 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0010 | ST-04 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 462 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01433 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0026 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 30 | 2.3.1 | V1.05 | MemCo-A | A2607
R01434 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-08 | Network | Link flap test | Pass |  | 65 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01435 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0002 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01436 | 2026-08-03 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2693 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01437 | 2026-08-03 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-08 | Memory | ECC injection | Pass |  | 664 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01438 | 2026-08-03 | Night | LYRA-4U | EVT | LYR-E-0024 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01439 | 2026-08-03 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-10 | Storage | FIO random R/W | Pass |  | 64 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01440 | 2026-08-03 | Night | LYRA-4U | EVT | LYR-E-0024 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 229 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01441 | 2026-08-03 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-09 | Power-on/POST | AC cycle 500x | Fail | No POST | 33 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01442 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0018 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 30 | 2.3.1 | O1.05 | MemCo-A | A2607
R01443 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0026 | ST-01 | Memory | Memtest stress 12h | Pass |  | 704 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01444 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0040 | ST-02 | Storage | NVMe hot-plug | Pass |  | 59 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01445 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0021 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01446 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0007 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01447 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0036 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01448 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0013 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01449 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0009 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 3151 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01450 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0025 | ST-01 | Network | NIC throughput 100G | Pass |  | 54 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01451 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0036 | ST-09 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01452 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0027 | TC-02 | Thermal | Thermal chamber | Pass |  | 179 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01453 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0035 | ST-02 | Storage | FIO random R/W | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01454 | 2026-08-04 | Night | ORION-2U | DVT | ORI-D-0016 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 261 | 23 | 2.3.1 | O1.05 | Dramtek | D2606
R01455 | 2026-08-04 | Day | ORION-2U | DVT | ORI-D-0033 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01456 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01457 | 2026-08-04 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 54 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01458 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-01 | Storage | FIO random R/W | Pass |  | 59 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01459 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-06 | Memory | Memtest stress 12h | Pass |  | 718 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01460 | 2026-08-04 | Night | VEGA-1U | DVT | VEG-D-0018 | ST-02 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01461 | 2026-08-04 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 233 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01462 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0035 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 188 | 30 | 2.3.1 | V1.05 | MemCo-B | B2607
R01463 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 22 | 2.3.1 | V1.05 | MemCo-B | B2604
R01464 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-02 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01465 | 2026-08-04 | Day | VEGA-1U | DVT | VEG-D-0011 | ST-01 | PCIe/GPU | PCIe link training | Pass |  | 218 | 25 | 2.3.1 | V1.05 | MemCo-A | A2605
R01466 | 2026-08-04 | Day | LYRA-4U | EVT | LYR-E-0005 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 97 | 35 | 2.3.1 | L1.05 | MemCo-A | A2607
R01467 | 2026-08-04 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-06 | Network | Link flap test | Pass |  | 63 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01468 | 2026-08-04 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01469 | 2026-08-04 | Night | LYRA-4U | EVT | LYR-E-0022 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01470 | 2026-08-04 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-02 | Storage | NVMe hot-plug | Pass |  | 57 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01471 | 2026-08-04 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3158 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01472 | 2026-08-04 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 257 | 24 | 2.3.1 | L1.05 | MemCo-B | B2604
R01473 | 2026-08-04 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 260 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01474 | 2026-08-04 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 240 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01475 | 2026-08-04 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3119 | 23 | 2.3.1 | L1.05 | MemCo-B | B2607
R01476 | 2026-08-05 | Day | ORION-2U | DVT | ORI-D-0003 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 239 | 23 | 2.3.1 | O1.05 | Dramtek | D2606
R01477 | 2026-08-05 | Day | ORION-2U | DVT | ORI-D-0020 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01478 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0023 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 64 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01479 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0012 | ST-06 | Memory | ECC injection | Pass |  | 728 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01480 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0020 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 30 | 2.3.1 | O1.05 | MemCo-B | B2604
R01481 | 2026-08-05 | Day | ORION-2U | DVT | ORI-D-0002 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01482 | 2026-08-05 | Day | ORION-2U | DVT | ORI-D-0006 | ST-09 | Storage | NVMe hot-plug | Pass |  | 54 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01483 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0030 | ST-03 | Network | Link flap test | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01484 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0013 | ST-01 | Network | NIC throughput 100G | Pass |  | 65 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01485 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0033 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01486 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0023 | ST-10 | Storage | FIO random R/W | Pass |  | 62 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01487 | 2026-08-05 | Day | ORION-2U | DVT | ORI-D-0018 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01488 | 2026-08-05 | Night | ORION-2U | DVT | ORI-D-0010 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01489 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01490 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-02 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 88 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01491 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 57 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01492 | 2026-08-05 | Night | VEGA-1U | DVT | VEG-D-0010 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 19 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01493 | 2026-08-05 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01494 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-06 | Network | NIC throughput 100G | Pass |  | 59 | 23 | 2.3.1 | V1.05 | Dramtek | D2606
R01495 | 2026-08-05 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01496 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0036 | ST-09 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 46 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01497 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.3.1 | V1.05 | Dramtek | D2606
R01498 | 2026-08-05 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 7 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01499 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-04 | Storage | FIO random R/W | Pass |  | 57 | 23 | 2.3.1 | V1.05 | Dramtek | D2606
R01500 | 2026-08-05 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-06 | Memory | ECC injection | Pass |  | 737 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01501 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0001 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 46 | 35 | 2.3.1 | L1.05 | MemCo-A | A2607
R01502 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-06 | Network | Link flap test | Pass |  | 58 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01503 | 2026-08-05 | Night | LYRA-4U | EVT | LYR-E-0021 | TC-01 | Thermal | Thermal chamber | Pass |  | 168 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01504 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-09 | Memory | ECC injection | Pass |  | 686 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01505 | 2026-08-05 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-10 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 969 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01506 | 2026-08-05 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-01 | Memory | ECC injection | Pass |  | 729 | 24 | 2.3.1 | L1.05 | MemCo-B | B2607
R01507 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01508 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2914 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01509 | 2026-08-05 | Day | LYRA-4U | EVT | LYR-E-0024 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 175 | 35 | 2.3.1 | L1.05 | MemCo-A | A2605
R01510 | 2026-08-05 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 220 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01511 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0014 | ST-10 | Network | Link flap test | Pass |  | 57 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01512 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0007 | ST-03 | Network | Link flap test | Pass |  | 57 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01513 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0008 | ST-03 | Memory | Memtest stress 12h | Pass |  | 654 | 23 | 2.3.1 | O1.05 | MemCo-B | B2607
R01514 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0016 | ST-09 | Network | Link flap test | Pass |  | 62 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01515 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0003 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 23 | 2.3.1 | O1.05 | Dramtek | D2606
R01516 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0031 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01517 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0015 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2833 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01518 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0013 | ST-08 | Network | Link flap test | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01519 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0033 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 30 | 2.3.1 | O1.05 | MemCo-A | A2605
R01520 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0015 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2689 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01521 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0001 | ST-07 | Power-on/POST | AC cycle 500x | Fail | No POST | 38 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01522 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0024 | ST-02 | Storage | NVMe hot-plug | Pass |  | 63 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01523 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0037 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 35 | 2.3.1 | O1.05 | MemCo-A | A2605
R01524 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0023 | ST-04 | Network | Link flap test | Pass |  | 65 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01525 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0019 | TC-02 | Thermal | Thermal chamber | Pass |  | 177 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01526 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0027 | ST-02 | Memory | Memtest stress 12h | Pass |  | 688 | 22 | 2.3.1 | O1.05 | Dramtek | D2606
R01527 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0006 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01528 | 2026-08-06 | Day | ORION-2U | DVT | ORI-D-0035 | ST-02 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 20 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01529 | 2026-08-06 | Night | ORION-2U | DVT | ORI-D-0013 | ST-09 | Memory | Memtest stress 12h | Pass |  | 757 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01530 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0010 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01531 | 2026-08-06 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-06 | Network | Link flap test | Pass |  | 64 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01532 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 255 | 23 | 2.3.1 | V1.05 | MemCo-A | A2605
R01533 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01534 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-01 | Network | NIC throughput 100G | Pass |  | 57 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01535 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-10 | Memory | ECC injection | Pass |  | 699 | 22 | 2.3.1 | V1.05 | MemCo-A | A2605
R01536 | 2026-08-06 | Night | VEGA-1U | DVT | VEG-D-0022 | TC-01 | Thermal | Thermal chamber | Pass |  | 180 | 30 | 2.3.1 | V1.05 | MemCo-A | A2607
R01537 | 2026-08-06 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2998 | 24 | 2.3.1 | V1.05 | Dramtek | D2606
R01538 | 2026-08-06 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-03 | Storage | FIO random R/W | Pass |  | 55 | 22 | 2.3.1 | V1.05 | MemCo-A | A2605
R01539 | 2026-08-06 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 237 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01540 | 2026-08-06 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | L1.05 | MemCo-B | B2604
R01541 | 2026-08-06 | Night | LYRA-4U | EVT | LYR-E-0020 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 30 | 2.3.1 | L1.05 | MemCo-A | A2605
R01542 | 2026-08-06 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01543 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0037 | ST-03 | Network | Link flap test | Pass |  | 61 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01544 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0007 | ST-02 | Storage | NVMe hot-plug | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01545 | 2026-08-07 | Day | ORION-2U | DVT | ORI-D-0017 | ST-08 | Memory | Memtest stress 12h | Pass |  | 728 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01546 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0030 | ST-05 | Storage | NVMe hot-plug | Pass |  | 60 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01547 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0027 | ST-09 | Memory | Memtest stress 12h | Pass |  | 720 | 22 | 2.3.1 | O1.05 | Dramtek | D2606
R01548 | 2026-08-07 | Day | ORION-2U | DVT | ORI-D-0028 | ST-01 | Storage | FIO random R/W | Pass |  | 65 | 24 | 2.3.1 | O1.05 | MemCo-B | B2607
R01549 | 2026-08-07 | Day | ORION-2U | DVT | ORI-D-0027 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01550 | 2026-08-07 | Day | ORION-2U | DVT | ORI-D-0007 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01551 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0021 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01552 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0036 | ST-08 | Storage | NVMe hot-plug | Pass |  | 58 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01553 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0020 | ST-09 | Memory | ECC injection | Fail | Error not logged in SEL | 436 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01554 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0006 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01555 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0034 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01556 | 2026-08-07 | Night | ORION-2U | DVT | ORI-D-0014 | ST-01 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01557 | 2026-08-07 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-09 | Storage | FIO random R/W | Pass |  | 63 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01558 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0018 | ST-09 | Memory | ECC injection | Pass |  | 778 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01559 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2722 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01560 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0005 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 54 | 24 | 2.3.1 | V1.05 | MemCo-B | B2604
R01561 | 2026-08-07 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 234 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01562 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-08 | Storage | NVMe hot-plug | Pass |  | 54 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01563 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0034 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 64 | 35 | 2.3.1 | V1.05 | MemCo-A | A2607
R01564 | 2026-08-07 | Day | VEGA-1U | DVT | VEG-D-0003 | ST-05 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 25 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01565 | 2026-08-07 | Day | VEGA-1U | DVT | VEG-D-0016 | TC-01 | Thermal | Thermal chamber | Pass |  | 163 | 35 | 2.3.1 | V1.05 | MemCo-A | A2605
R01566 | 2026-08-07 | Night | VEGA-1U | DVT | VEG-D-0029 | ST-06 | Network | Link flap test | Pass |  | 62 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01567 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0005 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 90 | 35 | 2.3.1 | L1.05 | MemCo-A | A2607
R01568 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-04 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01569 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01570 | 2026-08-07 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-08 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 38 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01571 | 2026-08-07 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3126 | 24 | 2.3.1 | L1.05 | MemCo-B | B2607
R01572 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 219 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01573 | 2026-08-07 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01574 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0021 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 41 | 35 | 2.3.1 | L1.05 | MemCo-A | A2605
R01575 | 2026-08-07 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-05 | Network | NIC throughput 100G | Pass |  | 61 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01576 | 2026-08-07 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2842 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01577 | 2026-08-08 | Day | ORION-2U | DVT | ORI-D-0034 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 171 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01578 | 2026-08-08 | Day | ORION-2U | DVT | ORI-D-0040 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 252 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01579 | 2026-08-08 | Night | ORION-2U | DVT | ORI-D-0012 | ST-04 | Storage | NVMe hot-plug | Pass |  | 57 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01580 | 2026-08-08 | Day | ORION-2U | DVT | ORI-D-0018 | ST-03 | Memory | ECC injection | Pass |  | 767 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01581 | 2026-08-08 | Day | ORION-2U | DVT | ORI-D-0013 | TC-02 | Thermal | Thermal chamber | Pass |  | 191 | 35 | 2.3.1 | O1.05 | MemCo-B | B2604
R01582 | 2026-08-08 | Day | VEGA-1U | DVT | VEG-D-0017 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 70 | 30 | 2.3.1 | V1.05 | MemCo-B | B2607
R01583 | 2026-08-08 | Night | VEGA-1U | DVT | VEG-D-0001 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01584 | 2026-08-08 | Day | VEGA-1U | DVT | VEG-D-0007 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2937 | 24 | 2.3.1 | V1.05 | MemCo-B | B2604
R01585 | 2026-08-08 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.1 | V1.05 | MemCo-B | B2604
R01586 | 2026-08-08 | Day | VEGA-1U | DVT | VEG-D-0003 | ST-09 | Burn-in | Burn-in 48h | Fail | Kernel panic | 2285 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01587 | 2026-08-08 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-04 | Network | NIC throughput 100G | Pass |  | 55 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01588 | 2026-08-08 | Day | VEGA-1U | DVT | VEG-D-0005 | ST-01 | Memory | ECC injection | Pass |  | 733 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01589 | 2026-08-08 | Night | VEGA-1U | DVT | VEG-D-0006 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01590 | 2026-08-08 | Night | VEGA-1U | DVT | VEG-D-0005 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 35 | 2.3.1 | V1.05 | MemCo-B | B2604
R01591 | 2026-08-08 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-10 | Network | Link flap test | Pass |  | 64 | 23 | 2.3.1 | V1.05 | MemCo-A | A2605
R01592 | 2026-08-08 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 251 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01593 | 2026-08-08 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2948 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01594 | 2026-08-08 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2915 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01595 | 2026-08-08 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3110 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01596 | 2026-08-08 | Night | LYRA-4U | EVT | LYR-E-0021 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01597 | 2026-08-08 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2605 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01598 | 2026-08-09 | Night | ORION-2U | DVT | ORI-D-0001 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01599 | 2026-08-09 | Day | ORION-2U | DVT | ORI-D-0014 | ST-04 | Storage | NVMe hot-plug | Pass |  | 64 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01600 | 2026-08-09 | Night | ORION-2U | DVT | ORI-D-0024 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01601 | 2026-08-09 | Night | ORION-2U | DVT | ORI-D-0031 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01602 | 2026-08-09 | Day | ORION-2U | DVT | ORI-D-0035 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01603 | 2026-08-09 | Day | ORION-2U | DVT | ORI-D-0003 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2640 | 22 | 2.3.1 | O1.05 | Dramtek | D2606
R01604 | 2026-08-09 | Day | ORION-2U | DVT | ORI-D-0017 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01605 | 2026-08-09 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 16 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01606 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-05 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01607 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-05 | Network | Link flap test | Pass |  | 54 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01608 | 2026-08-09 | Night | VEGA-1U | DVT | VEG-D-0031 | ST-09 | Memory | ECC injection | Pass |  | 751 | 22 | 2.3.1 | V1.05 | Dramtek | D2606
R01609 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0017 | TC-01 | Thermal | Thermal chamber | Pass |  | 165 | 35 | 2.3.1 | V1.05 | MemCo-B | B2607
R01610 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-05 | Network | Link flap test | Pass |  | 59 | 25 | 2.3.1 | V1.05 | MemCo-B | B2604
R01611 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01612 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0006 | ST-09 | Network | Link flap test | Pass |  | 60 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01613 | 2026-08-09 | Day | VEGA-1U | DVT | VEG-D-0005 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 24 | 2.3.1 | V1.05 | MemCo-B | B2604
R01614 | 2026-08-09 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 25 | 2.3.1 | L1.05 | Dramtek | D2606
R01615 | 2026-08-09 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 259 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01616 | 2026-08-09 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-01 | Network | Link flap test | Pass |  | 56 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01617 | 2026-08-09 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 248 | 24 | 2.3.1 | L1.05 | MemCo-B | B2607
R01618 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0040 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2842 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01619 | 2026-08-10 | Night | ORION-2U | DVT | ORI-D-0036 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 80 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01620 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0016 | ST-06 | Storage | FIO random R/W | Pass |  | 61 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01621 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0003 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 23 | 2.3.1 | O1.05 | Dramtek | D2606
R01622 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0035 | ST-08 | Memory | Memtest stress 12h | Pass |  | 749 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01623 | 2026-08-10 | Night | ORION-2U | DVT | ORI-D-0005 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3073 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01624 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0026 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01625 | 2026-08-10 | Night | ORION-2U | DVT | ORI-D-0035 | ST-07 | Memory | ECC injection | Pass |  | 774 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01626 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0020 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01627 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0021 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01628 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0036 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01629 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0029 | ST-10 | Network | NIC throughput 100G | Pass |  | 65 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01630 | 2026-08-10 | Day | ORION-2U | DVT | ORI-D-0028 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 61 | 25 | 2.3.1 | O1.05 | MemCo-B | B2607
R01631 | 2026-08-10 | Night | ORION-2U | DVT | ORI-D-0033 | ST-09 | Network | Link flap test | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01632 | 2026-08-10 | Night | ORION-2U | DVT | ORI-D-0007 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 180 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01633 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0002 | TC-01 | Thermal | Thermal chamber | Pass |  | 169 | 35 | 2.3.1 | V1.05 | MemCo-A | A2607
R01634 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-10 | Network | Link flap test | Pass |  | 57 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01635 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0030 | TC-02 | Thermal | Thermal chamber | Pass |  | 196 | 35 | 2.3.1 | V1.05 | MemCo-A | A2605
R01636 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0018 | TC-01 | Thermal | Thermal chamber | Pass |  | 175 | 30 | 2.3.1 | V1.05 | MemCo-B | B2607
R01637 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0036 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 38 | 35 | 2.3.1 | V1.05 | MemCo-B | B2607
R01638 | 2026-08-10 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-09 | Network | NIC throughput 100G | Pass |  | 58 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01639 | 2026-08-10 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-09 | Memory | Memtest stress 12h | Pass |  | 650 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01640 | 2026-08-10 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01641 | 2026-08-10 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 22 | 2.3.1 | L1.05 | Dramtek | D2606
R01642 | 2026-08-10 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-10 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.3.1 | L1.05 | MemCo-B | B2604
R01643 | 2026-08-10 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-09 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 70 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01644 | 2026-08-10 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 109 | 35 | 2.3.1 | L1.05 | MemCo-A | A2607
R01645 | 2026-08-10 | Night | LYRA-4U | EVT | LYR-E-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 35 | 2.3.1 | L1.05 | Dramtek | D2606
R01646 | 2026-08-11 | Night | ORION-2U | DVT | ORI-D-0025 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01647 | 2026-08-11 | Day | ORION-2U | DVT | ORI-D-0034 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 30 | 2.3.1 | O1.05 | MemCo-A | A2607
R01648 | 2026-08-11 | Day | ORION-2U | DVT | ORI-D-0005 | ST-06 | Storage | FIO random R/W | Pass |  | 61 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01649 | 2026-08-11 | Night | ORION-2U | DVT | ORI-D-0021 | ST-06 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01650 | 2026-08-11 | Night | ORION-2U | DVT | ORI-D-0022 | ST-02 | Network | NIC throughput 100G | Pass |  | 62 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01651 | 2026-08-11 | Day | ORION-2U | DVT | ORI-D-0037 | ST-05 | Memory | ECC injection | Pass |  | 742 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01652 | 2026-08-11 | Night | ORION-2U | DVT | ORI-D-0010 | ST-07 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 15 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01653 | 2026-08-11 | Night | ORION-2U | DVT | ORI-D-0039 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 49 | 35 | 2.3.1 | O1.05 | Dramtek | D2606
R01654 | 2026-08-11 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-08 | Network | Link flap test | Pass |  | 54 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01655 | 2026-08-11 | Night | VEGA-1U | DVT | VEG-D-0018 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01656 | 2026-08-11 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-02 | Memory | ECC injection | Pass |  | 735 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01657 | 2026-08-11 | Day | VEGA-1U | DVT | VEG-D-0010 | ST-03 | Memory | ECC injection | Pass |  | 681 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01658 | 2026-08-11 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-10 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01659 | 2026-08-11 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-08 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 224 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01660 | 2026-08-11 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-07 | PCIe/GPU | GPU burn 24h | Fail | Link trained at Gen4 instead of Gen5 | 153 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01661 | 2026-08-11 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-01 | Storage | NVMe hot-plug | Pass |  | 59 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01662 | 2026-08-11 | Night | LYRA-4U | EVT | LYR-E-0008 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3082 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01663 | 2026-08-11 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 245 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01664 | 2026-08-11 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01665 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0037 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 114 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01666 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0039 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 238 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01667 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0016 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 58 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01668 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0025 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01669 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0010 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01670 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0010 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 164 | 30 | 2.3.1 | O1.05 | MemCo-B | B2604
R01671 | 2026-08-12 | Night | ORION-2U | DVT | ORI-D-0022 | ST-09 | Memory | ECC injection | Pass |  | 701 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01672 | 2026-08-12 | Night | VEGA-1U | DVT | VEG-D-0002 | ST-09 | Network | Link flap test | Pass |  | 60 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01673 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 61 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01674 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-06 | Storage | FIO random R/W | Pass |  | 54 | 23 | 2.3.1 | V1.05 | MemCo-A | A2605
R01675 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-07 | Network | Link flap test | Fail | Link down | 38 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01676 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01677 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0002 | TC-01 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01678 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0040 | TC-02 | Thermal | Thermal chamber | Pass |  | 168 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01679 | 2026-08-12 | Night | VEGA-1U | DVT | VEG-D-0014 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 57 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01680 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2664 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01681 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | V1.05 | MemCo-A | A2605
R01682 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-03 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.1 | V1.05 | MemCo-B | B2604
R01683 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01684 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-08 | Storage | NVMe hot-plug | Pass |  | 55 | 22 | 2.3.1 | V1.05 | MemCo-B | B2604
R01685 | 2026-08-12 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2932 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01686 | 2026-08-12 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-08 | Storage | NVMe hot-plug | Pass |  | 61 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01687 | 2026-08-12 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 242 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01688 | 2026-08-12 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 225 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01689 | 2026-08-12 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2963 | 24 | 2.3.1 | L1.05 | Dramtek | D2606
R01690 | 2026-08-12 | Night | LYRA-4U | EVT | LYR-E-0021 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 256 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01691 | 2026-08-12 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-04 | Network | Link flap test | Pass |  | 60 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01692 | 2026-08-13 | Day | ORION-2U | DVT | ORI-D-0005 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 112 | 30 | 2.3.1 | O1.05 | MemCo-A | A2607
R01693 | 2026-08-13 | Day | ORION-2U | DVT | ORI-D-0002 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01694 | 2026-08-13 | Night | ORION-2U | DVT | ORI-D-0008 | ST-10 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1004 | 25 | 2.3.1 | O1.05 | MemCo-B | B2607
R01695 | 2026-08-13 | Night | ORION-2U | DVT | ORI-D-0010 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 35 | 2.3.1 | O1.05 | MemCo-B | B2604
R01696 | 2026-08-13 | Day | ORION-2U | DVT | ORI-D-0004 | ST-07 | Storage | NVMe hot-plug | Pass |  | 64 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01697 | 2026-08-13 | Day | ORION-2U | DVT | ORI-D-0032 | TC-02 | Thermal | Thermal chamber | Fail | Fan speed not responding | 112 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01698 | 2026-08-13 | Day | ORION-2U | DVT | ORI-D-0015 | ST-04 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01699 | 2026-08-13 | Night | ORION-2U | DVT | ORI-D-0035 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01700 | 2026-08-13 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-05 | Memory | ECC injection | Pass |  | 651 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01701 | 2026-08-13 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01702 | 2026-08-13 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-07 | Storage | FIO random R/W | Pass |  | 65 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01703 | 2026-08-13 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-10 | Network | Link flap test | Pass |  | 56 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01704 | 2026-08-13 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-07 | Memory | ECC injection | Pass |  | 738 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01705 | 2026-08-13 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01706 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-09 | Memory | Memtest stress 12h | Pass |  | 770 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01707 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-05 | Network | NIC throughput 100G | Pass |  | 62 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01708 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 22 | 2.3.1 | L1.05 | MemCo-B | B2607
R01709 | 2026-08-13 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-02 | Storage | FIO random R/W | Pass |  | 57 | 24 | 2.3.1 | L1.05 | Dramtek | D2606
R01710 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 65 | 24 | 2.3.1 | L1.05 | Dramtek | D2606
R01711 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0018 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 117 | 35 | 2.3.1 | L1.05 | MemCo-A | A2607
R01712 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01713 | 2026-08-13 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 253 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01714 | 2026-08-14 | Night | ORION-2U | DVT | ORI-D-0006 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01715 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0036 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 59 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01716 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0033 | ST-09 | Network | Link flap test | Pass |  | 54 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01717 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0027 | ST-08 | Network | Link flap test | Pass |  | 54 | 23 | 2.3.1 | O1.05 | Dramtek | D2606
R01718 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0037 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3029 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01719 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0028 | ST-01 | Storage | NVMe hot-plug | Pass |  | 60 | 25 | 2.3.1 | O1.05 | MemCo-B | B2607
R01720 | 2026-08-14 | Night | ORION-2U | DVT | ORI-D-0027 | ST-09 | Network | Link flap test | Fail | Link down | 14 | 24 | 2.3.1 | O1.05 | Dramtek | D2606
R01721 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0030 | ST-01 | Storage | NVMe hot-plug | Pass |  | 56 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01722 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0038 | ST-05 | Memory | Memtest stress 12h | Pass |  | 735 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01723 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0021 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2937 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01724 | 2026-08-14 | Night | ORION-2U | DVT | ORI-D-0022 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01725 | 2026-08-14 | Day | ORION-2U | DVT | ORI-D-0024 | ST-02 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01726 | 2026-08-14 | Night | ORION-2U | DVT | ORI-D-0002 | TC-02 | Thermal | Thermal chamber | Pass |  | 167 | 35 | 2.3.1 | O1.05 | MemCo-B | B2604
R01727 | 2026-08-14 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-02 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01728 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-05 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 188 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01729 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 57 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01730 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0006 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 219 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01731 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-04 | Memory | ECC injection | Pass |  | 718 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01732 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0031 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 30 | 2.3.1 | V1.05 | Dramtek | D2606
R01733 | 2026-08-14 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 226 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01734 | 2026-08-14 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 55 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01735 | 2026-08-14 | Day | LYRA-4U | EVT | LYR-E-0014 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 118 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01736 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 236 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01737 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 246 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01738 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-07 | Power-on/POST | DC cycle 500x | Fail | No POST | 11 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01739 | 2026-08-14 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-03 | Memory | ECC injection | Pass |  | 716 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01740 | 2026-08-14 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-07 | PCIe/GPU | GPU burn 24h | Fail | Link trained at Gen4 instead of Gen5 | 88 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01741 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01742 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0007 | TC-02 | Thermal | Thermal chamber | Pass |  | 171 | 30 | 2.3.1 | L1.05 | MemCo-B | B2607
R01743 | 2026-08-14 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01744 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-03 | Memory | ECC injection | Pass |  | 671 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01745 | 2026-08-14 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-10 | Network | Link flap test | Pass |  | 55 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01746 | 2026-08-14 | Day | LYRA-4U | EVT | LYR-E-0009 | TC-01 | Thermal | Thermal chamber | Pass |  | 186 | 30 | 2.3.1 | L1.05 | Dramtek | D2606
R01747 | 2026-08-15 | Day | ORION-2U | DVT | ORI-D-0019 | ST-09 | Storage | FIO random R/W | Pass |  | 56 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01748 | 2026-08-15 | Night | ORION-2U | DVT | ORI-D-0022 | ST-03 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 769 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01749 | 2026-08-15 | Day | ORION-2U | DVT | ORI-D-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 186 | 30 | 2.3.1 | O1.05 | MemCo-B | B2604
R01750 | 2026-08-15 | Day | ORION-2U | DVT | ORI-D-0024 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01751 | 2026-08-15 | Day | ORION-2U | DVT | ORI-D-0002 | ST-10 | Storage | FIO random R/W | Pass |  | 60 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01752 | 2026-08-15 | Night | ORION-2U | DVT | ORI-D-0010 | ST-02 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01753 | 2026-08-15 | Day | VEGA-1U | DVT | VEG-D-0005 | ST-04 | Memory | ECC injection | Pass |  | 769 | 25 | 2.3.1 | V1.05 | MemCo-B | B2604
R01754 | 2026-08-15 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-07 | Memory | Memtest stress 12h | Pass |  | 703 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01755 | 2026-08-15 | Night | VEGA-1U | DVT | VEG-D-0024 | ST-10 | Memory | ECC injection | Pass |  | 750 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01756 | 2026-08-15 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-03 | Memory | ECC injection | Pass |  | 767 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01757 | 2026-08-15 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2808 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01758 | 2026-08-15 | Night | VEGA-1U | DVT | VEG-D-0037 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 96 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01759 | 2026-08-15 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-03 | Memory | Memtest stress 12h | Pass |  | 660 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01760 | 2026-08-15 | Night | VEGA-1U | DVT | VEG-D-0032 | ST-09 | Storage | FIO random R/W | Pass |  | 65 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01761 | 2026-08-15 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01762 | 2026-08-15 | Day | LYRA-4U | EVT | LYR-E-0004 | TC-01 | Thermal | Thermal chamber | Pass |  | 189 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01763 | 2026-08-15 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01764 | 2026-08-15 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-07 | Memory | ECC injection | Pass |  | 661 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01765 | 2026-08-15 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3063 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01766 | 2026-08-15 | Night | LYRA-4U | EVT | LYR-E-0018 | ST-01 | Storage | NVMe hot-plug | Pass |  | 62 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01767 | 2026-08-15 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-02 | Power-on/POST | AC cycle 500x | Fail | No POST | 30 | 22 | 2.3.1 | L1.05 | MemCo-B | B2607
R01768 | 2026-08-15 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.1 | L1.05 | MemCo-B | B2607
R01769 | 2026-08-15 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-01 | Thermal | Thermal chamber | Pass |  | 168 | 30 | 2.3.1 | L1.05 | MemCo-A | A2607
R01770 | 2026-08-15 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 249 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01771 | 2026-08-16 | Day | ORION-2U | DVT | ORI-D-0035 | ST-05 | Storage | FIO random R/W | Pass |  | 55 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01772 | 2026-08-16 | Night | ORION-2U | DVT | ORI-D-0031 | ST-09 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01773 | 2026-08-16 | Day | ORION-2U | DVT | ORI-D-0037 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01774 | 2026-08-16 | Night | ORION-2U | DVT | ORI-D-0020 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01775 | 2026-08-16 | Night | ORION-2U | DVT | ORI-D-0035 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01776 | 2026-08-16 | Day | ORION-2U | DVT | ORI-D-0017 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01777 | 2026-08-16 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01778 | 2026-08-16 | Night | VEGA-1U | DVT | VEG-D-0006 | TC-02 | Thermal | Thermal chamber | Pass |  | 163 | 35 | 2.3.1 | V1.05 | MemCo-B | B2607
R01779 | 2026-08-16 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.1 | V1.05 | Dramtek | D2606
R01780 | 2026-08-16 | Day | VEGA-1U | DVT | VEG-D-0029 | TC-02 | Thermal | Thermal chamber | Pass |  | 192 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01781 | 2026-08-16 | Night | VEGA-1U | DVT | VEG-D-0026 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01782 | 2026-08-16 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-05 | Network | Link flap test | Pass |  | 57 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01783 | 2026-08-16 | Day | LYRA-4U | EVT | LYR-E-0013 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 38 | 30 | 2.3.1 | L1.05 | MemCo-A | A2605
R01784 | 2026-08-16 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 245 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01785 | 2026-08-16 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 64 | 23 | 2.3.1 | L1.05 | MemCo-A | A2607
R01786 | 2026-08-16 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-07 | Network | Link flap test | Pass |  | 62 | 22 | 2.3.1 | L1.05 | MemCo-A | A2605
R01787 | 2026-08-16 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.3.1 | L1.05 | MemCo-B | B2607
R01788 | 2026-08-16 | Night | LYRA-4U | EVT | LYR-E-0009 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 62 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01789 | 2026-08-17 | Night | ORION-2U | DVT | ORI-D-0019 | ST-03 | Network | NIC throughput 100G | Pass |  | 56 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01790 | 2026-08-17 | Day | ORION-2U | DVT | ORI-D-0012 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01791 | 2026-08-17 | Night | ORION-2U | DVT | ORI-D-0029 | ST-08 | Memory | ECC injection | Pass |  | 764 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01792 | 2026-08-17 | Night | ORION-2U | DVT | ORI-D-0031 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 60 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01793 | 2026-08-17 | Day | ORION-2U | DVT | ORI-D-0004 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 54 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01794 | 2026-08-17 | Day | ORION-2U | DVT | ORI-D-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 172 | 35 | 2.3.1 | O1.05 | MemCo-A | A2607
R01795 | 2026-08-17 | Night | VEGA-1U | DVT | VEG-D-0025 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 113 | 35 | 2.3.1 | V1.05 | MemCo-A | A2607
R01796 | 2026-08-17 | Night | VEGA-1U | DVT | VEG-D-0039 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 35 | 2.3.1 | V1.05 | MemCo-B | B2604
R01797 | 2026-08-17 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01798 | 2026-08-17 | Day | VEGA-1U | DVT | VEG-D-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 35 | 2.3.1 | V1.05 | MemCo-A | A2607
R01799 | 2026-08-17 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-02 | Network | NIC throughput 100G | Pass |  | 57 | 25 | 2.3.1 | V1.05 | MemCo-A | A2605
R01800 | 2026-08-17 | Day | VEGA-1U | DVT | VEG-D-0001 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 30 | 2.3.1 | V1.05 | MemCo-B | B2607
R01801 | 2026-08-17 | Night | VEGA-1U | DVT | VEG-D-0009 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 256 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01802 | 2026-08-17 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01803 | 2026-08-17 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-03 | Storage | FIO random R/W | Pass |  | 55 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01804 | 2026-08-17 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2646 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01805 | 2026-08-17 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 64 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01806 | 2026-08-17 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.3.1 | L1.05 | MemCo-B | B2607
R01807 | 2026-08-17 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.3.1 | L1.05 | Dramtek | D2606
R01808 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0022 | ST-09 | Network | Link flap test | Pass |  | 55 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01809 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0004 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 228 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01810 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0022 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01811 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0031 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 35 | 2.3.1 | O1.05 | MemCo-B | B2604
R01812 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0001 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01813 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0024 | ST-07 | Storage | NVMe hot-plug | Pass |  | 61 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01814 | 2026-08-18 | Night | ORION-2U | DVT | ORI-D-0017 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01815 | 2026-08-18 | Night | ORION-2U | DVT | ORI-D-0004 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 54 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01816 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0022 | ST-01 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.3.1 | O1.05 | MemCo-A | A2607
R01817 | 2026-08-18 | Night | ORION-2U | DVT | ORI-D-0039 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 113 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01818 | 2026-08-18 | Night | ORION-2U | DVT | ORI-D-0035 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01819 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0029 | ST-06 | Network | NIC throughput 100G | Pass |  | 62 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01820 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0014 | ST-06 | Network | Link flap test | Pass |  | 56 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01821 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0039 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 25 | 2.3.1 | O1.05 | Dramtek | D2606
R01822 | 2026-08-18 | Day | ORION-2U | DVT | ORI-D-0002 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 261 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01823 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0016 | ST-08 | Memory | Memtest stress 12h | Pass |  | 721 | 25 | 2.3.1 | V1.05 | MemCo-A | A2605
R01824 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-08 | Network | Link flap test | Pass |  | 64 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01825 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0036 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2679 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01826 | 2026-08-18 | Night | VEGA-1U | DVT | VEG-D-0037 | ST-06 | Network | Link flap test | Pass |  | 61 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01827 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 241 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01828 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-02 | Memory | Memtest stress 12h | Pass |  | 697 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01829 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-06 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 38 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01830 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0036 | TC-02 | Thermal | Thermal chamber | Pass |  | 164 | 30 | 2.3.1 | V1.05 | MemCo-B | B2607
R01831 | 2026-08-18 | Night | VEGA-1U | DVT | VEG-D-0019 | ST-07 | Network | Link flap test | Fail | Link down | 27 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01832 | 2026-08-18 | Day | VEGA-1U | DVT | VEG-D-0020 | TC-01 | Thermal | Thermal chamber | Pass |  | 175 | 30 | 2.3.1 | V1.05 | MemCo-A | A2607
R01833 | 2026-08-18 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3088 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01834 | 2026-08-18 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-06 | Memory | Memtest stress 12h | Pass |  | 779 | 25 | 2.3.1 | L1.05 | MemCo-B | B2604
R01835 | 2026-08-18 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-09 | Memory | ECC injection | Pass |  | 773 | 23 | 2.3.1 | L1.05 | MemCo-B | B2607
R01836 | 2026-08-18 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-04 | Network | Link flap test | Pass |  | 61 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01837 | 2026-08-18 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2920 | 24 | 2.3.1 | L1.05 | MemCo-A | A2605
R01838 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0023 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01839 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0025 | ST-04 | Memory | Memtest stress 12h | Pass |  | 744 | 22 | 2.3.1 | O1.05 | MemCo-A | A2607
R01840 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0030 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.1 | O1.05 | MemCo-B | B2604
R01841 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0022 | ST-05 | Memory | ECC injection | Pass |  | 749 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01842 | 2026-08-19 | Night | ORION-2U | DVT | ORI-D-0009 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 22 | 2.3.1 | O1.05 | MemCo-A | A2605
R01843 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0033 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2770 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01844 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0017 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 263 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01845 | 2026-08-19 | Night | ORION-2U | DVT | ORI-D-0021 | ST-09 | Network | NIC throughput 100G | Pass |  | 60 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01846 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0035 | ST-07 | Network | NIC throughput 100G | Pass |  | 64 | 25 | 2.3.1 | O1.05 | MemCo-A | A2607
R01847 | 2026-08-19 | Night | ORION-2U | DVT | ORI-D-0007 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2984 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01848 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0006 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 24 | 2.3.1 | O1.05 | MemCo-B | B2604
R01849 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0026 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 188 | 35 | 2.3.1 | O1.05 | MemCo-A | A2607
R01850 | 2026-08-19 | Night | ORION-2U | DVT | ORI-D-0013 | ST-04 | Memory | Memtest stress 12h | Pass |  | 786 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01851 | 2026-08-19 | Day | ORION-2U | DVT | ORI-D-0009 | ST-04 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.3.1 | O1.05 | MemCo-A | A2605
R01852 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0026 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 35 | 2.3.1 | V1.05 | MemCo-A | A2607
R01853 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 22 | 2.3.1 | V1.05 | MemCo-B | B2607
R01854 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.1 | V1.05 | MemCo-A | A2607
R01855 | 2026-08-19 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 54 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01856 | 2026-08-19 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2664 | 23 | 2.3.1 | V1.05 | MemCo-A | A2605
R01857 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-09 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.3.1 | V1.05 | MemCo-A | A2607
R01858 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 217 | 25 | 2.3.1 | V1.05 | MemCo-B | B2607
R01859 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 35 | 2.3.1 | V1.05 | MemCo-B | B2607
R01860 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-08 | Memory | Memtest stress 12h | Pass |  | 693 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01861 | 2026-08-19 | Day | VEGA-1U | DVT | VEG-D-0037 | ST-10 | Memory | ECC injection | Pass |  | 771 | 24 | 2.3.1 | V1.05 | MemCo-B | B2607
R01862 | 2026-08-19 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 236 | 24 | 2.3.1 | L1.05 | MemCo-A | A2607
R01863 | 2026-08-19 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 249 | 25 | 2.3.1 | L1.05 | MemCo-A | A2605
R01864 | 2026-08-19 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-04 | Memory | Memtest stress 12h | Pass |  | 712 | 25 | 2.3.1 | L1.05 | MemCo-B | B2607
R01865 | 2026-08-19 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01866 | 2026-08-19 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 54 | 22 | 2.3.1 | L1.05 | MemCo-B | B2607
R01867 | 2026-08-19 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-10 | Storage | FIO random R/W | Fail | IOPS below spec | 20 | 22 | 2.3.1 | L1.05 | MemCo-B | B2604
R01868 | 2026-08-20 | Day | ORION-2U | DVT | ORI-D-0001 | ST-07 | Memory | Memtest stress 12h | Pass |  | 670 | 25 | 2.3.1 | O1.05 | MemCo-A | A2605
R01869 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0022 | ST-04 | Network | Link flap test | Pass |  | 63 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01870 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0021 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2991 | 23 | 2.3.1 | O1.05 | MemCo-A | A2605
R01871 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0008 | ST-01 | Memory | ECC injection | Pass |  | 748 | 24 | 2.3.1 | O1.05 | MemCo-B | B2607
R01872 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0028 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 190 | 30 | 2.3.1 | O1.05 | MemCo-B | B2607
R01873 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0020 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01874 | 2026-08-20 | Day | ORION-2U | DVT | ORI-D-0030 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.3.1 | O1.05 | MemCo-B | B2604
R01875 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0012 | ST-10 | Network | Link flap test | Pass |  | 60 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01876 | 2026-08-20 | Night | ORION-2U | DVT | ORI-D-0032 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 242 | 22 | 2.3.1 | O1.05 | MemCo-B | B2604
R01877 | 2026-08-20 | Day | ORION-2U | DVT | ORI-D-0026 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.3.1 | O1.05 | MemCo-A | A2607
R01878 | 2026-08-20 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-04 | Memory | ECC injection | Pass |  | 774 | 23 | 2.3.1 | V1.05 | MemCo-A | A2607
R01879 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0015 | ST-09 | Storage | FIO random R/W | Pass |  | 57 | 22 | 2.3.1 | V1.05 | Dramtek | D2606
R01880 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-08 | Storage | NVMe hot-plug | Pass |  | 57 | 24 | 2.3.1 | V1.05 | MemCo-B | B2604
R01881 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-09 | Network | Link flap test | Pass |  | 54 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01882 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0024 | ST-08 | Network | Link flap test | Pass |  | 59 | 24 | 2.3.1 | V1.05 | MemCo-A | A2607
R01883 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-05 | Memory | ECC injection | Pass |  | 656 | 23 | 2.3.1 | V1.05 | MemCo-B | B2607
R01884 | 2026-08-20 | Day | VEGA-1U | DVT | VEG-D-0007 | TC-01 | Thermal | Thermal chamber | Fail | Fan speed not responding | 104 | 35 | 2.3.1 | V1.05 | MemCo-B | B2604
R01885 | 2026-08-20 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2786 | 23 | 2.3.1 | V1.05 | MemCo-B | B2604
R01886 | 2026-08-20 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-04 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 41 | 23 | 2.3.1 | L1.05 | MemCo-A | A2605
R01887 | 2026-08-20 | Night | LYRA-4U | EVT | LYR-E-0023 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2648 | 22 | 2.3.1 | L1.05 | MemCo-A | A2607
R01888 | 2026-08-20 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.1 | L1.05 | Dramtek | D2606
R01889 | 2026-08-20 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 236 | 25 | 2.3.1 | L1.05 | MemCo-A | A2607
R01890 | 2026-08-20 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 22 | 2.3.1 | L1.05 | Dramtek | D2606
R01891 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0038 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01892 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0013 | ST-01 | Memory | ECC injection | Pass |  | 696 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01893 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0002 | ST-04 | Network | NIC throughput 100G | Pass |  | 62 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R01894 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0030 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2883 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R01895 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0031 | ST-08 | Memory | ECC injection | Pass |  | 667 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R01896 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 30 | 2.3.4 | O1.05 | MemCo-B | B2604
R01897 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0014 | ST-10 | Network | NIC throughput 100G | Pass |  | 55 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R01898 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0030 | ST-06 | Storage | NVMe hot-plug | Pass |  | 56 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01899 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0014 | ST-08 | Storage | FIO random R/W | Pass |  | 59 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R01900 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0027 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R01901 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0024 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 58 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R01902 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0006 | ST-02 | Storage | NVMe hot-plug | Pass |  | 59 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R01903 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0023 | ST-01 | Power-on/POST | AC cycle 500x | Fail | No POST | 15 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R01904 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0037 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R01905 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0013 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R01906 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0023 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 218 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R01907 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0031 | ST-07 | Memory | Memtest stress 12h | Pass |  | 656 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R01908 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0004 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R01909 | 2026-08-21 | Day | ORION-2U | DVT | ORI-D-0011 | TC-01 | Thermal | Thermal chamber | Pass |  | 170 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R01910 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0001 | ST-03 | Network | Link flap test | Pass |  | 56 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R01911 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0001 | ST-10 | Storage | FIO random R/W | Pass |  | 62 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R01912 | 2026-08-21 | Night | ORION-2U | DVT | ORI-D-0017 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R01913 | 2026-08-21 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R01914 | 2026-08-21 | Night | VEGA-1U | DVT | VEG-D-0015 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.3.4 | V1.05 | Dramtek | D2606
R01915 | 2026-08-21 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R01916 | 2026-08-21 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R01917 | 2026-08-21 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-01 | Storage | FIO random R/W | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R01918 | 2026-08-21 | Day | VEGA-1U | DVT | VEG-D-0037 | TC-02 | Thermal | Thermal chamber | Pass |  | 193 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R01919 | 2026-08-21 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-02 | Memory | ECC injection | Pass |  | 767 | 25 | 2.3.4 | V1.05 | Dramtek | D2606
R01920 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-08 | Network | NIC throughput 100G | Pass |  | 57 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R01921 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0010 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 98 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R01922 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-07 | Memory | ECC injection | Pass |  | 768 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R01923 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-10 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R01924 | 2026-08-21 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 235 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R01925 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 222 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R01926 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-09 | Storage | NVMe hot-plug | Pass |  | 55 | 24 | 2.3.4 | L1.05 | Dramtek | D2606
R01927 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 261 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R01928 | 2026-08-21 | Night | LYRA-4U | EVT | LYR-E-0007 | ST-07 | Network | Link flap test | Fail | Link down | 22 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R01929 | 2026-08-21 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 246 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R01930 | 2026-08-21 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 217 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R01931 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2785 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R01932 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0015 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 228 | 24 | 2.3.4 | L1.05 | Dramtek | D2606
R01933 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 231 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R01934 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R01935 | 2026-08-21 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 239 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R01936 | 2026-08-21 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 58 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R01937 | 2026-08-22 | Day | ORION-2U | DVT | ORI-D-0030 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R01938 | 2026-08-22 | Night | ORION-2U | DVT | ORI-D-0020 | ST-01 | Memory | ECC injection | Pass |  | 675 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R01939 | 2026-08-22 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-06 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 22 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R01940 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2680 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R01941 | 2026-08-22 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R01942 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-06 | Network | NIC throughput 100G | Pass |  | 60 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R01943 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-07 | Storage | NVMe hot-plug | Pass |  | 61 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R01944 | 2026-08-22 | Night | VEGA-1U | DVT | VEG-D-0039 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R01945 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0036 | ST-07 | Memory | Memtest stress 12h | Pass |  | 748 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R01946 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0039 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 174 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R01947 | 2026-08-22 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-05 | Memory | Memtest stress 12h | Pass |  | 780 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R01948 | 2026-08-22 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R01949 | 2026-08-22 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-02 | Network | NIC throughput 100G | Pass |  | 64 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R01950 | 2026-08-22 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 263 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R01951 | 2026-08-23 | Day | ORION-2U | DVT | ORI-D-0017 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R01952 | 2026-08-23 | Day | ORION-2U | DVT | ORI-D-0021 | ST-02 | Memory | Memtest stress 12h | Pass |  | 776 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R01953 | 2026-08-23 | Day | ORION-2U | DVT | ORI-D-0004 | ST-01 | Storage | NVMe hot-plug | Pass |  | 65 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R01954 | 2026-08-23 | Night | ORION-2U | DVT | ORI-D-0035 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 65 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R01955 | 2026-08-23 | Day | ORION-2U | DVT | ORI-D-0032 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01956 | 2026-08-23 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-06 | Network | Link flap test | Pass |  | 59 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R01957 | 2026-08-23 | Day | VEGA-1U | DVT | VEG-D-0016 | TC-02 | Thermal | Thermal chamber | Pass |  | 164 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R01958 | 2026-08-23 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3021 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R01959 | 2026-08-23 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-09 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R01960 | 2026-08-23 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2822 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R01961 | 2026-08-23 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R01962 | 2026-08-23 | Day | LYRA-4U | EVT | LYR-E-0020 | TC-02 | Thermal | Thermal chamber | Pass |  | 177 | 35 | 2.3.4 | L1.05 | MemCo-A | A2605
R01963 | 2026-08-24 | Night | ORION-2U | DVT | ORI-D-0025 | ST-10 | Memory | ECC injection | Pass |  | 728 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R01964 | 2026-08-24 | Night | ORION-2U | DVT | ORI-D-0015 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 35 | 2.3.4 | O1.05 | MemCo-A | A2607
R01965 | 2026-08-24 | Day | ORION-2U | DVT | ORI-D-0006 | ST-10 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01966 | 2026-08-24 | Day | ORION-2U | DVT | ORI-D-0012 | ST-08 | Network | Link flap test | Pass |  | 65 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R01967 | 2026-08-24 | Night | ORION-2U | DVT | ORI-D-0002 | ST-10 | Storage | FIO random R/W | Pass |  | 60 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R01968 | 2026-08-24 | Day | ORION-2U | DVT | ORI-D-0022 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 253 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R01969 | 2026-08-24 | Day | ORION-2U | DVT | ORI-D-0025 | ST-01 | Storage | FIO random R/W | Fail | IOPS below spec | 37 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R01970 | 2026-08-24 | Day | ORION-2U | DVT | ORI-D-0007 | ST-01 | Memory | ECC injection | Pass |  | 711 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R01971 | 2026-08-24 | Night | ORION-2U | DVT | ORI-D-0022 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R01972 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3106 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R01973 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-06 | Memory | Memtest stress 12h | Pass |  | 674 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R01974 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2738 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R01975 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-03 | Network | Link flap test | Pass |  | 59 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R01976 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 22 | 2.3.4 | V1.05 | Dramtek | D2606
R01977 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R01978 | 2026-08-24 | Night | VEGA-1U | DVT | VEG-D-0037 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R01979 | 2026-08-24 | Night | VEGA-1U | DVT | VEG-D-0003 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3104 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R01980 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 189 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R01981 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0034 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 166 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R01982 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R01983 | 2026-08-24 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-09 | Network | NIC throughput 100G | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R01984 | 2026-08-24 | Day | VEGA-1U | DVT | VEG-D-0033 | TC-01 | Thermal | Thermal chamber | Pass |  | 190 | 35 | 2.3.4 | V1.05 | MemCo-A | A2607
R01985 | 2026-08-24 | Day | LYRA-4U | EVT | LYR-E-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 91 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R01986 | 2026-08-24 | Day | LYRA-4U | EVT | LYR-E-0017 | TC-02 | Thermal | Thermal chamber | Pass |  | 195 | 35 | 2.3.4 | L1.05 | MemCo-B | B2607
R01987 | 2026-08-24 | Night | LYRA-4U | EVT | LYR-E-0008 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 174 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R01988 | 2026-08-24 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 239 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R01989 | 2026-08-24 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 228 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R01990 | 2026-08-24 | Day | LYRA-4U | EVT | LYR-E-0008 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 169 | 30 | 2.3.4 | L1.05 | MemCo-B | B2607
R01991 | 2026-08-24 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R01992 | 2026-08-24 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-10 | Memory | ECC injection | Pass |  | 787 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R01993 | 2026-08-24 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-04 | Memory | ECC injection | Fail | Error not logged in SEL | 178 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R01994 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0013 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R01995 | 2026-08-25 | Night | ORION-2U | DVT | ORI-D-0027 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R01996 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0006 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2756 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R01997 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0018 | ST-10 | Network | NIC throughput 100G | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R01998 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0021 | ST-01 | Network | NIC throughput 100G | Pass |  | 61 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R01999 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0033 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2680 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02000 | 2026-08-25 | Night | ORION-2U | DVT | ORI-D-0013 | TC-01 | Thermal | Thermal chamber | Pass |  | 177 | 35 | 2.3.4 | O1.05 | MemCo-B | B2604
R02001 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0008 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 54 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02002 | 2026-08-25 | Day | ORION-2U | DVT | ORI-D-0029 | ST-01 | Memory | Memtest stress 12h | Pass |  | 768 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02003 | 2026-08-25 | Night | ORION-2U | DVT | ORI-D-0026 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 60 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02004 | 2026-08-25 | Night | ORION-2U | DVT | ORI-D-0010 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02005 | 2026-08-25 | Night | VEGA-1U | DVT | VEG-D-0010 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02006 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-06 | Network | Link flap test | Pass |  | 55 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02007 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0037 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02008 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-04 | Memory | ECC injection | Pass |  | 699 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02009 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-07 | PCIe/GPU | GPU burn 24h | Fail | Link trained at Gen4 instead of Gen5 | 154 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02010 | 2026-08-25 | Night | VEGA-1U | DVT | VEG-D-0006 | ST-06 | Memory | ECC injection | Pass |  | 767 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02011 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-01 | Storage | FIO random R/W | Pass |  | 65 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02012 | 2026-08-25 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-08 | Memory | ECC injection | Pass |  | 727 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02013 | 2026-08-25 | Night | VEGA-1U | DVT | VEG-D-0003 | ST-08 | Storage | NVMe hot-plug | Pass |  | 57 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02014 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 231 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02015 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-07 | Network | NIC throughput 100G | Fail | Link down | 28 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02016 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0014 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02017 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02018 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-08 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02019 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 61 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02020 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-02 | Memory | Memtest stress 12h | Pass |  | 666 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02021 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-10 | Network | Link flap test | Pass |  | 63 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02022 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-07 | Power-on/POST | DC cycle 500x | Fail | System stuck in S5 | 33 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02023 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-04 | Storage | FIO random R/W | Pass |  | 54 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02024 | 2026-08-25 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-06 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02025 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0019 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02026 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0032 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02027 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0027 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 59 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02028 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0024 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 190 | 30 | 2.3.4 | O1.05 | MemCo-A | A2605
R02029 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0014 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02030 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0012 | ST-01 | Network | Link flap test | Pass |  | 57 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02031 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0025 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 255 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02032 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0030 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02033 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0001 | TC-01 | Thermal | Thermal chamber | Pass |  | 187 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02034 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 182 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02035 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0009 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 3007 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02036 | 2026-08-26 | Day | ORION-2U | DVT | ORI-D-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02037 | 2026-08-26 | Night | ORION-2U | DVT | ORI-D-0014 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2792 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02038 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2860 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02039 | 2026-08-26 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-06 | Memory | ECC injection | Pass |  | 695 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02040 | 2026-08-26 | Day | VEGA-1U | DVT | VEG-D-0013 | ST-07 | Network | Link flap test | Pass |  | 57 | 22 | 2.3.4 | V1.05 | Dramtek | D2606
R02041 | 2026-08-26 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-08 | Storage | NVMe hot-plug | Pass |  | 57 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02042 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0009 | ST-02 | Network | NIC throughput 100G | Pass |  | 56 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02043 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2822 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02044 | 2026-08-26 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-01 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 192 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02045 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-10 | Memory | ECC injection | Pass |  | 713 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02046 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0038 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02047 | 2026-08-26 | Night | VEGA-1U | DVT | VEG-D-0006 | ST-10 | Memory | ECC injection | Pass |  | 690 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02048 | 2026-08-26 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 242 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02049 | 2026-08-26 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-09 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1171 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02050 | 2026-08-26 | Night | LYRA-4U | EVT | LYR-E-0009 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2639 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02051 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02052 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0017 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02053 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-05 | Memory | Memtest stress 12h | Pass |  | 651 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02054 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0015 | TC-01 | Thermal | Thermal chamber | Pass |  | 170 | 30 | 2.3.4 | L1.05 | Dramtek | D2606
R02055 | 2026-08-26 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-03 | Storage | FIO random R/W | Pass |  | 58 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02056 | 2026-08-26 | Night | LYRA-4U | EVT | LYR-E-0023 | TC-02 | Thermal | Thermal chamber | Pass |  | 180 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02057 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 262 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02058 | 2026-08-26 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02059 | 2026-08-27 | Night | ORION-2U | DVT | ORI-D-0030 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02060 | 2026-08-27 | Night | ORION-2U | DVT | ORI-D-0008 | ST-08 | Power-on/POST | DC cycle 500x | Fail | No POST | 17 | 24 | 2.3.4 | O1.05 | MemCo-B | B2607
R02061 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0028 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 24 | 2.3.4 | O1.05 | MemCo-B | B2607
R02062 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0028 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 175 | 30 | 2.3.4 | O1.05 | MemCo-B | B2607
R02063 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0001 | ST-02 | Memory | Memtest stress 12h | Pass |  | 657 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02064 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0034 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02065 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0023 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02066 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0012 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02067 | 2026-08-27 | Day | ORION-2U | DVT | ORI-D-0007 | ST-01 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02068 | 2026-08-27 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-02 | Memory | Memtest stress 12h | Pass |  | 662 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02069 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02070 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02071 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-01 | PCIe/GPU | PCIe link training | Pass |  | 223 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02072 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02073 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02074 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-03 | Storage | FIO random R/W | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02075 | 2026-08-27 | Night | VEGA-1U | DVT | VEG-D-0020 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 235 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02076 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-05 | Memory | ECC injection | Pass |  | 786 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02077 | 2026-08-27 | Night | VEGA-1U | DVT | VEG-D-0014 | ST-03 | Network | Link flap test | Pass |  | 54 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02078 | 2026-08-27 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 257 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02079 | 2026-08-27 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02080 | 2026-08-27 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 65 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02081 | 2026-08-27 | Night | LYRA-4U | EVT | LYR-E-0014 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02082 | 2026-08-27 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 235 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02083 | 2026-08-27 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-06 | Memory | Memtest stress 12h | Pass |  | 706 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02084 | 2026-08-27 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-05 | Network | NIC throughput 100G | Pass |  | 54 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02085 | 2026-08-27 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-07 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 102 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02086 | 2026-08-27 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02087 | 2026-08-27 | Night | LYRA-4U | EVT | LYR-E-0006 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 55 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02088 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0020 | ST-09 | Network | Link flap test | Pass |  | 64 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02089 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0035 | ST-01 | Memory | ECC injection | Pass |  | 670 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02090 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0023 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 63 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02091 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0019 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2955 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02092 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0021 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02093 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0020 | ST-03 | Storage | NVMe hot-plug | Pass |  | 58 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02094 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0033 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | Fan speed not responding | 69 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02095 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0033 | ST-03 | Network | NIC throughput 100G | Pass |  | 61 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02096 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0018 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02097 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0009 | ST-06 | Network | Link flap test | Pass |  | 58 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02098 | 2026-08-28 | Night | ORION-2U | DVT | ORI-D-0004 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2844 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02099 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0026 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02100 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 35 | 2.3.4 | O1.05 | MemCo-B | B2604
R02101 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0006 | ST-07 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 117 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02102 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0011 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02103 | 2026-08-28 | Day | ORION-2U | DVT | ORI-D-0022 | ST-03 | Memory | ECC injection | Pass |  | 745 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02104 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0023 | ST-08 | Memory | ECC injection | Pass |  | 765 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02105 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0032 | TC-01 | Thermal | Thermal chamber | Pass |  | 189 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02106 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02107 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-07 | BMC/Firmware | Redfish API check | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02108 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0009 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2886 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02109 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-09 | Memory | ECC injection | Pass |  | 729 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02110 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02111 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0029 | ST-02 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 186 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02112 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0027 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02113 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-04 | Storage | FIO random R/W | Pass |  | 61 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02114 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0032 | ST-08 | Memory | ECC injection | Pass |  | 686 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02115 | 2026-08-28 | Day | VEGA-1U | DVT | VEG-D-0020 | TC-01 | Thermal | Thermal chamber | Pass |  | 178 | 35 | 2.3.4 | V1.05 | MemCo-A | A2607
R02116 | 2026-08-28 | Night | VEGA-1U | DVT | VEG-D-0007 | ST-03 | Network | NIC throughput 100G | Pass |  | 55 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02117 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-02 | Storage | NVMe hot-plug | Pass |  | 64 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02118 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0016 | TC-01 | Thermal | Thermal chamber | Pass |  | 177 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02119 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-03 | Network | NIC throughput 100G | Pass |  | 59 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02120 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 263 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02121 | 2026-08-28 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-06 | BMC/Firmware | BMC FW update stress | Fail | BMC unresponsive after update | 45 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02122 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 223 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02123 | 2026-08-28 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-05 | Memory | ECC injection | Pass |  | 685 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02124 | 2026-08-28 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 256 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02125 | 2026-08-29 | Day | ORION-2U | DVT | ORI-D-0016 | ST-08 | Network | Link flap test | Pass |  | 56 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02126 | 2026-08-29 | Day | ORION-2U | DVT | ORI-D-0038 | TC-02 | Thermal | Thermal chamber | Pass |  | 164 | 30 | 2.3.4 | O1.05 | MemCo-B | B2604
R02127 | 2026-08-29 | Night | ORION-2U | DVT | ORI-D-0023 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02128 | 2026-08-29 | Night | ORION-2U | DVT | ORI-D-0020 | ST-04 | Storage | FIO random R/W | Pass |  | 64 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02129 | 2026-08-29 | Day | ORION-2U | DVT | ORI-D-0024 | ST-04 | Memory | ECC injection | Fail | Error not logged in SEL | 392 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02130 | 2026-08-29 | Night | ORION-2U | DVT | ORI-D-0028 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 226 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02131 | 2026-08-29 | Night | ORION-2U | DVT | ORI-D-0002 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02132 | 2026-08-29 | Night | ORION-2U | DVT | ORI-D-0001 | ST-05 | Memory | ECC injection | Pass |  | 765 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02133 | 2026-08-29 | Day | ORION-2U | DVT | ORI-D-0028 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 228 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02134 | 2026-08-29 | Day | VEGA-1U | DVT | VEG-D-0016 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02135 | 2026-08-29 | Day | VEGA-1U | DVT | VEG-D-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 30 | 2.3.4 | V1.05 | MemCo-A | A2607
R02136 | 2026-08-29 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02137 | 2026-08-29 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-01 | Memory | ECC injection | Pass |  | 778 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02138 | 2026-08-29 | Night | LYRA-4U | EVT | LYR-E-0010 | TC-01 | Thermal | Thermal chamber | Pass |  | 171 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02139 | 2026-08-29 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-03 | Network | Link flap test | Pass |  | 55 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02140 | 2026-08-29 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02141 | 2026-08-29 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-08 | Network | Link flap test | Fail | Link down | 39 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02142 | 2026-08-29 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 246 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02143 | 2026-08-30 | Night | ORION-2U | DVT | ORI-D-0011 | ST-07 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02144 | 2026-08-30 | Day | ORION-2U | DVT | ORI-D-0022 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02145 | 2026-08-30 | Night | ORION-2U | DVT | ORI-D-0010 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02146 | 2026-08-30 | Night | ORION-2U | DVT | ORI-D-0027 | ST-09 | Memory | Memtest stress 12h | Pass |  | 742 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02147 | 2026-08-30 | Day | ORION-2U | DVT | ORI-D-0012 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02148 | 2026-08-30 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-07 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02149 | 2026-08-30 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02150 | 2026-08-30 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 54 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02151 | 2026-08-30 | Day | VEGA-1U | DVT | VEG-D-0005 | TC-02 | Thermal | Thermal chamber | Pass |  | 170 | 30 | 2.3.4 | V1.05 | MemCo-B | B2604
R02152 | 2026-08-30 | Day | LYRA-4U | EVT | LYR-E-0007 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 35 | 30 | 2.3.4 | L1.05 | MemCo-B | B2607
R02153 | 2026-08-30 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-10 | Storage | FIO random R/W | Pass |  | 59 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02154 | 2026-08-30 | Night | LYRA-4U | EVT | LYR-E-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 197 | 35 | 2.3.4 | L1.05 | MemCo-A | A2607
R02155 | 2026-08-30 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 58 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02156 | 2026-08-30 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-07 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02157 | 2026-08-31 | Day | ORION-2U | DVT | ORI-D-0006 | ST-06 | Memory | Memtest stress 12h | Pass |  | 735 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02158 | 2026-08-31 | Day | ORION-2U | DVT | ORI-D-0020 | TC-01 | Thermal | Thermal chamber | Pass |  | 188 | 35 | 2.3.4 | O1.05 | MemCo-B | B2604
R02159 | 2026-08-31 | Day | ORION-2U | DVT | ORI-D-0017 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02160 | 2026-08-31 | Night | ORION-2U | DVT | ORI-D-0025 | ST-06 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02161 | 2026-08-31 | Day | ORION-2U | DVT | ORI-D-0038 | ST-09 | Memory | Memtest stress 12h | Pass |  | 742 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02162 | 2026-08-31 | Day | ORION-2U | DVT | ORI-D-0029 | ST-09 | Storage | FIO random R/W | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02163 | 2026-08-31 | Night | ORION-2U | DVT | ORI-D-0031 | ST-07 | Memory | Memtest stress 12h | Fail | DIMM not detected | 321 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02164 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2743 | 25 | 2.3.4 | V1.05 | Dramtek | D2606
R02165 | 2026-08-31 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 250 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02166 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02167 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02168 | 2026-08-31 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-01 | Storage | FIO random R/W | Pass |  | 56 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02169 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0007 | ST-06 | Storage | FIO random R/W | Pass |  | 56 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02170 | 2026-08-31 | Night | VEGA-1U | DVT | VEG-D-0010 | ST-04 | Network | Link flap test | Pass |  | 59 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02171 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-03 | Network | Link flap test | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02172 | 2026-08-31 | Night | VEGA-1U | DVT | VEG-D-0028 | TC-01 | Thermal | Thermal chamber | Pass |  | 169 | 30 | 2.3.4 | V1.05 | MemCo-A | A2605
R02173 | 2026-08-31 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 25 | 2.3.4 | V1.05 | Dramtek | D2606
R02174 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-04 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02175 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0024 | ST-07 | Memory | ECC injection | Pass |  | 708 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02176 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-07 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 482 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02177 | 2026-08-31 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-10 | Storage | NVMe hot-plug | Pass |  | 62 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02178 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02179 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02180 | 2026-08-31 | Night | LYRA-4U | EVT | LYR-E-0014 | ST-01 | PCIe/GPU | GPU burn 24h | Pass |  | 227 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02181 | 2026-08-31 | Day | LYRA-4U | EVT | LYR-E-0022 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02182 | 2026-09-01 | Night | ORION-2U | PVT | ORI-P-0034 | ST-09 | Network | Link flap test | Pass |  | 65 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02183 | 2026-09-01 | Day | ORION-2U | PVT | ORI-P-0040 | ST-06 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 37 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02184 | 2026-09-01 | Night | ORION-2U | PVT | ORI-P-0054 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3019 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02185 | 2026-09-01 | Night | ORION-2U | PVT | ORI-P-0021 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02186 | 2026-09-01 | Night | ORION-2U | PVT | ORI-P-0004 | ST-08 | Network | Link flap test | Pass |  | 55 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02187 | 2026-09-01 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02188 | 2026-09-01 | Night | VEGA-1U | DVT | VEG-D-0021 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 164 | 30 | 2.3.4 | V1.05 | MemCo-B | B2604
R02189 | 2026-09-01 | Night | VEGA-1U | DVT | VEG-D-0037 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 30 | 2.3.4 | V1.05 | MemCo-B | B2607
R02190 | 2026-09-01 | Night | VEGA-1U | DVT | VEG-D-0013 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.3.4 | V1.05 | Dramtek | D2606
R02191 | 2026-09-01 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-06 | Network | Link flap test | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02192 | 2026-09-01 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02193 | 2026-09-01 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-09 | Memory | ECC injection | Pass |  | 684 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02194 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0012 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 24 | 2.3.4 | L1.05 | Dramtek | D2606
R02195 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0009 | ST-10 | Memory | ECC injection | Pass |  | 760 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02196 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0009 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 174 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02197 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02198 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 64 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02199 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02200 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2871 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02201 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0003 | ST-06 | Memory | ECC injection | Pass |  | 707 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02202 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0011 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 30 | 2.3.4 | L1.05 | MemCo-B | B2607
R02203 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-06 | Memory | ECC injection | Pass |  | 674 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02204 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0021 | ST-05 | Storage | FIO random R/W | Pass |  | 58 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02205 | 2026-09-01 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-06 | Memory | ECC injection | Pass |  | 772 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02206 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0010 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 51 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02207 | 2026-09-01 | Night | LYRA-4U | EVT | LYR-E-0013 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2644 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02208 | 2026-09-02 | Night | ORION-2U | PVT | ORI-P-0045 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02209 | 2026-09-02 | Day | ORION-2U | PVT | ORI-P-0025 | TC-01 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02210 | 2026-09-02 | Day | ORION-2U | PVT | ORI-P-0026 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 262 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02211 | 2026-09-02 | Day | ORION-2U | PVT | ORI-P-0020 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 35 | 2.3.4 | O1.05 | MemCo-A | A2607
R02212 | 2026-09-02 | Night | ORION-2U | PVT | ORI-P-0015 | ST-05 | Network | Link flap test | Pass |  | 57 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02213 | 2026-09-02 | Day | ORION-2U | PVT | ORI-P-0030 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02214 | 2026-09-02 | Night | ORION-2U | PVT | ORI-P-0033 | ST-03 | Memory | ECC injection | Pass |  | 742 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02215 | 2026-09-02 | Night | ORION-2U | PVT | ORI-P-0054 | TC-01 | Thermal | Thermal chamber | Pass |  | 192 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02216 | 2026-09-02 | Day | ORION-2U | PVT | ORI-P-0017 | ST-08 | Storage | NVMe hot-plug | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02217 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-08 | Network | NIC throughput 100G | Pass |  | 60 | 24 | 2.3.4 | V1.05 | Dramtek | D2606
R02218 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 259 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02219 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0010 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2717 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02220 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0025 | ST-02 | Power-on/POST | AC cycle 500x | Fail | No POST | 6 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02221 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-05 | Memory | Memtest stress 12h | Pass |  | 744 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02222 | 2026-09-02 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-10 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02223 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 63 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02224 | 2026-09-02 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2946 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02225 | 2026-09-02 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3066 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02226 | 2026-09-02 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-10 | Memory | Memtest stress 12h | Pass |  | 772 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02227 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-09 | Network | Link flap test | Fail | Link down | 16 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02228 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-09 | Power-on/POST | AC cycle 500x | Fail | No POST | 45 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02229 | 2026-09-02 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02230 | 2026-09-02 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02231 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 224 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02232 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02233 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 227 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02234 | 2026-09-02 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02235 | 2026-09-02 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-03 | Memory | ECC injection | Fail | Error not logged in SEL | 567 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02236 | 2026-09-03 | Day | ORION-2U | PVT | ORI-P-0010 | ST-04 | Memory | Memtest stress 12h | Pass |  | 776 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02237 | 2026-09-03 | Night | ORION-2U | PVT | ORI-P-0042 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 55 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02238 | 2026-09-03 | Night | ORION-2U | PVT | ORI-P-0013 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2623 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02239 | 2026-09-03 | Night | ORION-2U | PVT | ORI-P-0016 | ST-02 | Network | NIC throughput 100G | Pass |  | 63 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02240 | 2026-09-03 | Day | ORION-2U | PVT | ORI-P-0042 | ST-05 | Memory | ECC injection | Pass |  | 784 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02241 | 2026-09-03 | Night | ORION-2U | PVT | ORI-P-0043 | ST-09 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02242 | 2026-09-03 | Night | ORION-2U | PVT | ORI-P-0051 | ST-09 | Storage | FIO random R/W | Pass |  | 56 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02243 | 2026-09-03 | Night | VEGA-1U | DVT | VEG-D-0033 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02244 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-06 | Memory | ECC injection | Pass |  | 691 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02245 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-06 | Memory | Memtest stress 12h | Pass |  | 766 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02246 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 237 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02247 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0016 | ST-10 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02248 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02249 | 2026-09-03 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-01 | Network | Link flap test | Pass |  | 62 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02250 | 2026-09-03 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02251 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 227 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02252 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2739 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02253 | 2026-09-03 | Night | LYRA-4U | EVT | LYR-E-0008 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02254 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 28 | 35 | 2.3.4 | L1.05 | MemCo-A | A2607
R02255 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 233 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02256 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-04 | PCIe/GPU | GPU burn 24h | Pass |  | 261 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02257 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 250 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02258 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02259 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-02 | Storage | FIO random R/W | Pass |  | 64 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02260 | 2026-09-03 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-01 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02261 | 2026-09-04 | Day | ORION-2U | PVT | ORI-P-0031 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 178 | 30 | 2.3.4 | O1.05 | Dramtek | D2606
R02262 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0006 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 55 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02263 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0032 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02264 | 2026-09-04 | Day | ORION-2U | PVT | ORI-P-0046 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02265 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0014 | ST-02 | Storage | NVMe hot-plug | Pass |  | 65 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02266 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0006 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 55 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02267 | 2026-09-04 | Day | ORION-2U | PVT | ORI-P-0051 | ST-10 | Memory | ECC injection | Pass |  | 688 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02268 | 2026-09-04 | Day | ORION-2U | PVT | ORI-P-0035 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2857 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02269 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0007 | ST-03 | Memory | ECC injection | Pass |  | 682 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02270 | 2026-09-04 | Night | ORION-2U | PVT | ORI-P-0042 | ST-02 | Storage | FIO random R/W | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02271 | 2026-09-04 | Day | ORION-2U | PVT | ORI-P-0059 | ST-04 | Network | NIC throughput 100G | Pass |  | 57 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02272 | 2026-09-04 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02273 | 2026-09-04 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-10 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 312 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02274 | 2026-09-04 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-03 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02275 | 2026-09-04 | Night | VEGA-1U | DVT | VEG-D-0032 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02276 | 2026-09-04 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-02 | Storage | FIO random R/W | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02277 | 2026-09-04 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-03 | Network | Link flap test | Pass |  | 64 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02278 | 2026-09-04 | Day | VEGA-1U | DVT | VEG-D-0037 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02279 | 2026-09-04 | Night | VEGA-1U | DVT | VEG-D-0003 | ST-04 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02280 | 2026-09-04 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02281 | 2026-09-04 | Night | LYRA-4U | EVT | LYR-E-0020 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02282 | 2026-09-04 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02283 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0060 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02284 | 2026-09-05 | Night | ORION-2U | PVT | ORI-P-0022 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 3125 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02285 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0035 | ST-05 | Storage | NVMe hot-plug | Pass |  | 56 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02286 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0034 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 35 | 2.3.4 | O1.05 | MemCo-B | B2607
R02287 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0031 | ST-03 | Memory | ECC injection | Pass |  | 733 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R02288 | 2026-09-05 | Night | ORION-2U | PVT | ORI-P-0046 | ST-09 | Storage | NVMe hot-plug | Pass |  | 55 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02289 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0043 | ST-09 | Storage | FIO random R/W | Pass |  | 56 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02290 | 2026-09-05 | Day | ORION-2U | PVT | ORI-P-0052 | ST-05 | Network | Link flap test | Pass |  | 61 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02291 | 2026-09-05 | Night | ORION-2U | PVT | ORI-P-0050 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R02292 | 2026-09-05 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-02 | PCIe/GPU | GPU burn 24h | Fail | GPU fell off bus | 72 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02293 | 2026-09-05 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 64 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02294 | 2026-09-05 | Night | VEGA-1U | DVT | VEG-D-0003 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02295 | 2026-09-05 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-03 | Memory | Memtest stress 12h | Pass |  | 677 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02296 | 2026-09-05 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 55 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02297 | 2026-09-05 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 247 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02298 | 2026-09-05 | Day | LYRA-4U | EVT | LYR-E-0018 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02299 | 2026-09-05 | Day | LYRA-4U | EVT | LYR-E-0017 | TC-01 | Thermal | Thermal chamber | Pass |  | 167 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02300 | 2026-09-06 | Day | ORION-2U | PVT | ORI-P-0046 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 185 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02301 | 2026-09-06 | Day | ORION-2U | PVT | ORI-P-0039 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 232 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02302 | 2026-09-06 | Day | ORION-2U | PVT | ORI-P-0060 | ST-02 | Memory | ECC injection | Pass |  | 714 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02303 | 2026-09-06 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2603 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02304 | 2026-09-06 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2721 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02305 | 2026-09-06 | Night | VEGA-1U | DVT | VEG-D-0016 | ST-05 | Memory | ECC injection | Pass |  | 711 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02306 | 2026-09-06 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-08 | Memory | Memtest stress 12h | Pass |  | 706 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02307 | 2026-09-06 | Day | LYRA-4U | EVT | LYR-E-0007 | ST-07 | Network | Link flap test | Pass |  | 56 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02308 | 2026-09-06 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-10 | PCIe/GPU | PCIe link training | Pass |  | 258 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02309 | 2026-09-06 | Day | LYRA-4U | EVT | LYR-E-0003 | ST-08 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02310 | 2026-09-06 | Day | LYRA-4U | EVT | LYR-E-0017 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02311 | 2026-09-06 | Day | LYRA-4U | EVT | LYR-E-0001 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02312 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0058 | ST-08 | Network | NIC throughput 100G | Pass |  | 60 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02313 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0003 | ST-03 | Storage | NVMe hot-plug | Pass |  | 60 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02314 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0016 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02315 | 2026-09-07 | Night | ORION-2U | PVT | ORI-P-0050 | ST-08 | Memory | Memtest stress 12h | Pass |  | 654 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02316 | 2026-09-07 | Night | ORION-2U | PVT | ORI-P-0013 | ST-09 | Network | Link flap test | Pass |  | 63 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02317 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0028 | ST-08 | Memory | Memtest stress 12h | Pass |  | 754 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02318 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0012 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 62 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02319 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0019 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 2753 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02320 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0007 | ST-06 | Memory | ECC injection | Pass |  | 651 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R02321 | 2026-09-07 | Night | ORION-2U | PVT | ORI-P-0015 | ST-01 | Network | Link flap test | Pass |  | 55 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02322 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0022 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02323 | 2026-09-07 | Night | ORION-2U | PVT | ORI-P-0014 | ST-04 | Storage | FIO random R/W | Pass |  | 55 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02324 | 2026-09-07 | Day | ORION-2U | PVT | ORI-P-0007 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02325 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0023 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 175 | 35 | 2.3.4 | V1.05 | MemCo-A | A2607
R02326 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 217 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02327 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0015 | ST-09 | Memory | Memtest stress 12h | Pass |  | 684 | 24 | 2.3.4 | V1.05 | Dramtek | D2606
R02328 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0038 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 35 | 2.3.4 | V1.05 | MemCo-B | B2607
R02329 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-04 | Storage | NVMe hot-plug | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02330 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-01 | Memory | ECC injection | Pass |  | 706 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02331 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-10 | Memory | Memtest stress 12h | Pass |  | 771 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02332 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-02 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 117 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02333 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02334 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0020 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 219 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02335 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2816 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02336 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0006 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 168 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02337 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0013 | ST-10 | Memory | ECC injection | Pass |  | 666 | 22 | 2.3.4 | V1.05 | Dramtek | D2606
R02338 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-09 | Memory | Memtest stress 12h | Pass |  | 717 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02339 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0023 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 56 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02340 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-10 | Storage | FIO random R/W | Pass |  | 61 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02341 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-09 | Storage | FIO random R/W | Pass |  | 65 | 25 | 2.3.4 | V1.05 | Dramtek | D2606
R02342 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-04 | Memory | ECC injection | Pass |  | 728 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02343 | 2026-09-07 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-02 | Memory | ECC injection | Fail | Error not logged in SEL | 288 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02344 | 2026-09-07 | Night | VEGA-1U | DVT | VEG-D-0022 | TC-02 | Thermal | Thermal chamber | Pass |  | 173 | 35 | 2.3.4 | V1.05 | MemCo-A | A2607
R02345 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0011 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2824 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02346 | 2026-09-07 | Night | LYRA-4U | EVT | LYR-E-0003 | TC-01 | Thermal | Thermal chamber | Pass |  | 196 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02347 | 2026-09-07 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-02 | Storage | FIO random R/W | Pass |  | 62 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02348 | 2026-09-07 | Night | LYRA-4U | EVT | LYR-E-0004 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02349 | 2026-09-07 | Night | LYRA-4U | EVT | LYR-E-0002 | ST-08 | Memory | ECC injection | Pass |  | 783 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02350 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-01 | Network | NIC throughput 100G | Pass |  | 57 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02351 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0005 | ST-09 | Memory | Memtest stress 12h | Pass |  | 749 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02352 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0013 | TC-01 | Thermal | Thermal chamber | Pass |  | 171 | 35 | 2.3.4 | L1.05 | MemCo-A | A2605
R02353 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0020 | TC-02 | Thermal | Thermal chamber | Pass |  | 188 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02354 | 2026-09-07 | Night | LYRA-4U | EVT | LYR-E-0021 | TC-02 | Thermal | Thermal chamber | Pass |  | 195 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02355 | 2026-09-07 | Day | LYRA-4U | EVT | LYR-E-0017 | TC-01 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 52 | 35 | 2.3.4 | L1.05 | MemCo-B | B2607
R02356 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0022 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 181 | 35 | 2.3.4 | O1.05 | MemCo-A | A2607
R02357 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0059 | ST-03 | Burn-in | Burn-in 48h | Pass |  | 2932 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02358 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0007 | ST-10 | Storage | FIO random R/W | Pass |  | 59 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02359 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0030 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02360 | 2026-09-08 | Day | ORION-2U | PVT | ORI-P-0035 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02361 | 2026-09-08 | Day | ORION-2U | PVT | ORI-P-0005 | ST-06 | Network | Link flap test | Pass |  | 62 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02362 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0025 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02363 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0037 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 191 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02364 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0044 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2924 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02365 | 2026-09-08 | Day | ORION-2U | PVT | ORI-P-0031 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02366 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0034 | ST-02 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 224 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02367 | 2026-09-08 | Day | ORION-2U | PVT | ORI-P-0014 | ST-09 | Network | Link flap test | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-B | B2607
R02368 | 2026-09-08 | Day | ORION-2U | PVT | ORI-P-0053 | ST-01 | Network | Link flap test | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02369 | 2026-09-08 | Night | ORION-2U | PVT | ORI-P-0020 | ST-09 | Network | Link flap test | Pass |  | 59 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02370 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0006 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 234 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02371 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02372 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02373 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3149 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02374 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0039 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 171 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02375 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0020 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02376 | 2026-09-08 | Night | VEGA-1U | DVT | VEG-D-0024 | ST-08 | Memory | ECC injection | Pass |  | 737 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02377 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0011 | ST-05 | Network | Link flap test | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02378 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-04 | Memory | Memtest stress 12h | Pass |  | 761 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02379 | 2026-09-08 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-05 | Storage | FIO random R/W | Pass |  | 56 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02380 | 2026-09-08 | Night | VEGA-1U | DVT | VEG-D-0028 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02381 | 2026-09-08 | Night | VEGA-1U | DVT | VEG-D-0020 | ST-09 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02382 | 2026-09-08 | Night | VEGA-1U | DVT | VEG-D-0016 | ST-10 | Network | NIC throughput 100G | Pass |  | 63 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02383 | 2026-09-08 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-02 | Network | NIC throughput 100G | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02384 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0001 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02385 | 2026-09-08 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 56 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02386 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-05 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02387 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-05 | Memory | ECC injection | Pass |  | 746 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02388 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0008 | TC-01 | Thermal | Thermal chamber | Pass |  | 179 | 30 | 2.3.4 | L1.05 | MemCo-B | B2607
R02389 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 249 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02390 | 2026-09-08 | Night | LYRA-4U | EVT | LYR-E-0001 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02391 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-03 | Network | NIC throughput 100G | Pass |  | 57 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02392 | 2026-09-08 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02393 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0006 | ST-07 | Memory | Memtest stress 12h | Pass |  | 773 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02394 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0021 | ST-10 | Network | NIC throughput 100G | Pass |  | 62 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02395 | 2026-09-08 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-07 | Storage | FIO random R/W | Fail | IOPS below spec | 11 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02396 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0032 | ST-08 | Network | Link flap test | Pass |  | 63 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02397 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0013 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2838 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02398 | 2026-09-09 | Day | ORION-2U | PVT | ORI-P-0033 | ST-03 | Memory | ECC injection | Pass |  | 789 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02399 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0004 | ST-02 | Memory | Memtest stress 12h | Pass |  | 764 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02400 | 2026-09-09 | Day | ORION-2U | PVT | ORI-P-0022 | ST-03 | Memory | ECC injection | Pass |  | 722 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02401 | 2026-09-09 | Day | ORION-2U | PVT | ORI-P-0019 | ST-09 | Memory | ECC injection | Pass |  | 701 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02402 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0043 | ST-02 | Memory | Memtest stress 12h | Pass |  | 753 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02403 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0044 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02404 | 2026-09-09 | Day | ORION-2U | PVT | ORI-P-0037 | ST-07 | Network | Link flap test | Pass |  | 58 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02405 | 2026-09-09 | Night | ORION-2U | PVT | ORI-P-0020 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 196 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02406 | 2026-09-09 | Day | ORION-2U | PVT | ORI-P-0026 | TC-01 | Thermal | Thermal chamber | Pass |  | 172 | 30 | 2.3.4 | O1.05 | MemCo-A | A2605
R02407 | 2026-09-09 | Day | VEGA-1U | DVT | VEG-D-0033 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02408 | 2026-09-09 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 3076 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02409 | 2026-09-09 | Night | VEGA-1U | DVT | VEG-D-0007 | ST-07 | Memory | Memtest stress 12h | Pass |  | 681 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02410 | 2026-09-09 | Night | VEGA-1U | DVT | VEG-D-0039 | ST-06 | Storage | NVMe hot-plug | Pass |  | 63 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02411 | 2026-09-09 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02412 | 2026-09-09 | Day | VEGA-1U | DVT | VEG-D-0010 | ST-06 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 573 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02413 | 2026-09-09 | Day | VEGA-1U | DVT | VEG-D-0013 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 24 | 2.3.4 | V1.05 | Dramtek | D2606
R02414 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0017 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 234 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02415 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0023 | ST-07 | Network | NIC throughput 100G | Fail | Throughput below spec | 18 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02416 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0019 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 258 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02417 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0010 | ST-08 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 164 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02418 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0019 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02419 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0005 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 238 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02420 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-01 | Memory | ECC injection | Pass |  | 731 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02421 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0008 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 3089 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02422 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0002 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 55 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02423 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0012 | ST-01 | Power-on/POST | AC cycle 500x | Fail | POST hang at code 0xB2 | 29 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02424 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0016 | ST-06 | Memory | ECC injection | Pass |  | 673 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02425 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0022 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 57 | 23 | 2.3.4 | L1.05 | MemCo-B | B2607
R02426 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3021 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02427 | 2026-09-09 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-10 | Memory | ECC injection | Fail | Error not logged in SEL | 262 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02428 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0024 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02429 | 2026-09-09 | Night | LYRA-4U | EVT | LYR-E-0008 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 260 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02430 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0016 | ST-02 | Memory | ECC injection | Pass |  | 674 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02431 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0016 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 223 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02432 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0051 | TC-02 | Thermal | Thermal chamber | Pass |  | 175 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02433 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0051 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02434 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0035 | TC-01 | Thermal | Thermal chamber | Pass |  | 190 | 35 | 2.3.4 | O1.05 | MemCo-B | B2604
R02435 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0033 | ST-03 | Network | Link flap test | Pass |  | 58 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02436 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0053 | ST-02 | Network | NIC throughput 100G | Pass |  | 55 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02437 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0012 | ST-08 | Network | Link flap test | Pass |  | 54 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02438 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0016 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02439 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0039 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2773 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02440 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0048 | ST-09 | Storage | FIO random R/W | Pass |  | 60 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02441 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0017 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 254 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02442 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0057 | ST-02 | Storage | FIO random R/W | Pass |  | 58 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02443 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0039 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 176 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02444 | 2026-09-10 | Night | ORION-2U | PVT | ORI-P-0048 | ST-10 | Memory | Memtest stress 12h | Pass |  | 655 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02445 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0060 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 195 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02446 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0013 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2750 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02447 | 2026-09-10 | Day | ORION-2U | PVT | ORI-P-0019 | ST-07 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 101 | 24 | 2.3.4 | O1.05 | MemCo-B | B2607
R02448 | 2026-09-10 | Night | VEGA-1U | DVT | VEG-D-0013 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2953 | 24 | 2.3.4 | V1.05 | Dramtek | D2606
R02449 | 2026-09-10 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-07 | Memory | ECC injection | Pass |  | 768 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02450 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0031 | ST-01 | Storage | NVMe hot-plug | Pass |  | 54 | 23 | 2.3.4 | V1.05 | Dramtek | D2606
R02451 | 2026-09-10 | Night | VEGA-1U | DVT | VEG-D-0031 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 23 | 2.3.4 | V1.05 | Dramtek | D2606
R02452 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-10 | Storage | NVMe hot-plug | Pass |  | 63 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02453 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-10 | Network | NIC throughput 100G | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02454 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0008 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 183 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02455 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-09 | Memory | Memtest stress 12h | Pass |  | 668 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02456 | 2026-09-10 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-01 | Network | NIC throughput 100G | Pass |  | 62 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02457 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02458 | 2026-09-10 | Day | VEGA-1U | DVT | VEG-D-0016 | ST-09 | Network | Link flap test | Pass |  | 59 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02459 | 2026-09-10 | Day | LYRA-4U | EVT | LYR-E-0020 | ST-03 | Memory | Memtest stress 12h | Pass |  | 651 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02460 | 2026-09-10 | Day | LYRA-4U | EVT | LYR-E-0009 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 226 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02461 | 2026-09-10 | Night | LYRA-4U | EVT | LYR-E-0016 | ST-08 | Network | Link flap test | Pass |  | 61 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02462 | 2026-09-10 | Day | LYRA-4U | EVT | LYR-E-0004 | ST-04 | Network | NIC throughput 100G | Pass |  | 57 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02463 | 2026-09-10 | Day | LYRA-4U | EVT | LYR-E-0013 | ST-10 | Memory | ECC injection | Pass |  | 680 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02464 | 2026-09-10 | Day | LYRA-4U | EVT | LYR-E-0010 | ST-05 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 566 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02465 | 2026-09-10 | Night | LYRA-4U | EVT | LYR-E-0011 | ST-06 | Burn-in | Burn-in 48h | Fail | Kernel panic | 1357 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02466 | 2026-09-10 | Night | LYRA-4U | EVT | LYR-E-0015 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 57 | 24 | 2.3.4 | L1.05 | Dramtek | D2606
R02467 | 2026-09-11 | Day | ORION-2U | PVT | ORI-P-0054 | ST-10 | Network | Link flap test | Pass |  | 55 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02468 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0042 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3105 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02469 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0034 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | O1.05 | MemCo-B | B2607
R02470 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0027 | TC-02 | Thermal | Thermal chamber | Pass |  | 182 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02471 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0016 | ST-08 | Network | NIC throughput 100G | Pass |  | 55 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02472 | 2026-09-11 | Day | ORION-2U | PVT | ORI-P-0004 | ST-09 | Storage | NVMe hot-plug | Pass |  | 58 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02473 | 2026-09-11 | Day | ORION-2U | PVT | ORI-P-0018 | ST-02 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02474 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0046 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02475 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0045 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02476 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0005 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 217 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02477 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0006 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 55 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02478 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0050 | ST-10 | Memory | ECC injection | Pass |  | 706 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02479 | 2026-09-11 | Day | ORION-2U | PVT | ORI-P-0027 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02480 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0059 | TC-02 | Thermal | Thermal chamber | Pass |  | 178 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02481 | 2026-09-11 | Night | ORION-2U | PVT | ORI-P-0019 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 56 | 24 | 2.3.4 | O1.05 | MemCo-B | B2607
R02482 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-01 | Memory | ECC injection | Pass |  | 674 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02483 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02484 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-07 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 41 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02485 | 2026-09-11 | Night | VEGA-1U | DVT | VEG-D-0037 | ST-01 | Memory | Memtest stress 12h | Pass |  | 693 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02486 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0011 | ST-01 | Storage | FIO random R/W | Pass |  | 60 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02487 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-06 | Network | Link flap test | Pass |  | 54 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02488 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-05 | Network | NIC throughput 100G | Pass |  | 63 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02489 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-01 | PCIe/GPU | PCIe link training | Pass |  | 225 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02490 | 2026-09-11 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02491 | 2026-09-11 | Day | LYRA-4U | DVT | LYR-D-0001 | ST-03 | Network | Link flap test | Pass |  | 55 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02492 | 2026-09-11 | Day | LYRA-4U | DVT | LYR-D-0015 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 3004 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02493 | 2026-09-11 | Night | LYRA-4U | DVT | LYR-D-0035 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02494 | 2026-09-12 | Day | ORION-2U | PVT | ORI-P-0020 | ST-08 | Storage | FIO random R/W | Pass |  | 54 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02495 | 2026-09-12 | Day | ORION-2U | PVT | ORI-P-0044 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 232 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02496 | 2026-09-12 | Night | ORION-2U | PVT | ORI-P-0013 | ST-03 | Memory | ECC injection | Pass |  | 725 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02497 | 2026-09-12 | Day | ORION-2U | PVT | ORI-P-0034 | TC-01 | Thermal | Thermal chamber | Pass |  | 180 | 35 | 2.3.4 | O1.05 | MemCo-B | B2607
R02498 | 2026-09-12 | Night | ORION-2U | PVT | ORI-P-0050 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2697 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02499 | 2026-09-12 | Night | ORION-2U | PVT | ORI-P-0058 | ST-05 | PCIe/GPU | PCIe link training | Pass |  | 237 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02500 | 2026-09-12 | Night | ORION-2U | PVT | ORI-P-0042 | ST-04 | Network | NIC throughput 100G | Pass |  | 57 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02501 | 2026-09-12 | Night | ORION-2U | PVT | ORI-P-0025 | ST-04 | Storage | NVMe hot-plug | Pass |  | 56 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02502 | 2026-09-12 | Night | VEGA-1U | DVT | VEG-D-0029 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02503 | 2026-09-12 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-01 | Storage | FIO random R/W | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02504 | 2026-09-12 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-01 | Network | Link flap test | Pass |  | 54 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02505 | 2026-09-12 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-10 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02506 | 2026-09-12 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02507 | 2026-09-12 | Night | VEGA-1U | DVT | VEG-D-0006 | TC-02 | Thermal | Thermal chamber | Pass |  | 197 | 30 | 2.3.4 | V1.05 | MemCo-B | B2607
R02508 | 2026-09-12 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-02 | Network | Link flap test | Pass |  | 59 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02509 | 2026-09-12 | Night | VEGA-1U | DVT | VEG-D-0031 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | V1.05 | Dramtek | D2606
R02510 | 2026-09-12 | Day | LYRA-4U | DVT | LYR-D-0024 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02511 | 2026-09-12 | Night | LYRA-4U | DVT | LYR-D-0021 | ST-02 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02512 | 2026-09-12 | Night | LYRA-4U | DVT | LYR-D-0022 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02513 | 2026-09-13 | Day | ORION-2U | PVT | ORI-P-0025 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02514 | 2026-09-13 | Night | ORION-2U | PVT | ORI-P-0005 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02515 | 2026-09-13 | Night | ORION-2U | PVT | ORI-P-0019 | ST-02 | Memory | ECC injection | Pass |  | 692 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02516 | 2026-09-13 | Day | ORION-2U | PVT | ORI-P-0010 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02517 | 2026-09-13 | Night | ORION-2U | PVT | ORI-P-0016 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02518 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0032 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 55 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02519 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-05 | Network | Link flap test | Pass |  | 56 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02520 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0003 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02521 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-08 | Memory | ECC injection | Pass |  | 694 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02522 | 2026-09-13 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-07 | PCIe/GPU | PCIe link training | Fail | Link trained at Gen4 instead of Gen5 | 140 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02523 | 2026-09-13 | Day | VEGA-1U | DVT | VEG-D-0025 | ST-06 | Storage | NVMe hot-plug | Pass |  | 60 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02524 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3019 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02525 | 2026-09-13 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-05 | Network | NIC throughput 100G | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02526 | 2026-09-13 | Day | VEGA-1U | DVT | VEG-D-0019 | ST-07 | Memory | Memtest stress 12h | Pass |  | 774 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02527 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-06 | Memory | ECC injection | Pass |  | 774 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02528 | 2026-09-13 | Day | VEGA-1U | DVT | VEG-D-0022 | ST-07 | Network | Link flap test | Pass |  | 61 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02529 | 2026-09-13 | Night | VEGA-1U | DVT | VEG-D-0027 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02530 | 2026-09-13 | Day | LYRA-4U | DVT | LYR-D-0011 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2634 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02531 | 2026-09-13 | Day | LYRA-4U | DVT | LYR-D-0040 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2596 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02532 | 2026-09-13 | Night | LYRA-4U | DVT | LYR-D-0004 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02533 | 2026-09-13 | Night | LYRA-4U | DVT | LYR-D-0040 | ST-08 | Power-on/POST | DC cycle 500x | Fail | System stuck in S5 | 29 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02534 | 2026-09-14 | Night | ORION-2U | PVT | ORI-P-0011 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02535 | 2026-09-14 | Night | ORION-2U | PVT | ORI-P-0046 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2785 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02536 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0041 | ST-02 | Memory | ECC injection | Pass |  | 710 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02537 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0018 | ST-03 | Network | NIC throughput 100G | Pass |  | 58 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02538 | 2026-09-14 | Night | ORION-2U | PVT | ORI-P-0011 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 236 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02539 | 2026-09-14 | Night | ORION-2U | PVT | ORI-P-0047 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02540 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0013 | ST-02 | Memory | ECC injection | Pass |  | 779 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02541 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0030 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02542 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0004 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02543 | 2026-09-14 | Night | ORION-2U | PVT | ORI-P-0019 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 25 | 2.3.4 | O1.05 | MemCo-B | B2607
R02544 | 2026-09-14 | Day | ORION-2U | PVT | ORI-P-0023 | TC-01 | Thermal | Thermal chamber | Pass |  | 179 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02545 | 2026-09-14 | Day | VEGA-1U | DVT | VEG-D-0004 | ST-08 | Network | Link flap test | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02546 | 2026-09-14 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-07 | Memory | Memtest stress 12h | Pass |  | 682 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02547 | 2026-09-14 | Night | VEGA-1U | DVT | VEG-D-0025 | ST-07 | Memory | Memtest stress 12h | Pass |  | 773 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02548 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0014 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 177 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02549 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0008 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 55 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02550 | 2026-09-14 | Night | LYRA-4U | DVT | LYR-D-0025 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 241 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02551 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0005 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02552 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0001 | ST-10 | Memory | Memtest stress 12h | Pass |  | 687 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02553 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0034 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 238 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02554 | 2026-09-14 | Day | LYRA-4U | DVT | LYR-D-0021 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 60 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02555 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0003 | TC-01 | Thermal | Thermal chamber | Pass |  | 177 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02556 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0049 | TC-02 | Thermal | Thermal chamber | Pass |  | 169 | 30 | 2.3.4 | O1.05 | MemCo-A | A2605
R02557 | 2026-09-15 | Night | ORION-2U | PVT | ORI-P-0050 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R02558 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0057 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2824 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02559 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0014 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2618 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02560 | 2026-09-15 | Night | ORION-2U | PVT | ORI-P-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02561 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0044 | TC-01 | Thermal | Thermal chamber | Pass |  | 188 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02562 | 2026-09-15 | Night | ORION-2U | PVT | ORI-P-0044 | ST-07 | Memory | Memtest stress 12h | Pass |  | 691 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02563 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0049 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 259 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02564 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0022 | TC-02 | Thermal | Thermal chamber | Pass |  | 193 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02565 | 2026-09-15 | Night | ORION-2U | PVT | ORI-P-0030 | ST-04 | Network | Link flap test | Pass |  | 63 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02566 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0020 | ST-02 | Memory | Memtest stress 12h | Pass |  | 762 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02567 | 2026-09-15 | Night | ORION-2U | PVT | ORI-P-0016 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 59 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02568 | 2026-09-15 | Day | ORION-2U | PVT | ORI-P-0047 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 63 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02569 | 2026-09-15 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-08 | Memory | Memtest stress 12h | Pass |  | 730 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02570 | 2026-09-15 | Day | VEGA-1U | DVT | VEG-D-0040 | ST-02 | Network | Link flap test | Pass |  | 59 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02571 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0028 | ST-05 | Network | Link flap test | Pass |  | 59 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02572 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 257 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02573 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-08 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 28 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02574 | 2026-09-15 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02575 | 2026-09-15 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2652 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02576 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0025 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 2694 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02577 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0011 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02578 | 2026-09-15 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-02 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02579 | 2026-09-15 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02580 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0034 | ST-06 | Memory | Memtest stress 12h | Pass |  | 696 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02581 | 2026-09-15 | Night | LYRA-4U | DVT | LYR-D-0028 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 233 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02582 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 30 | 2.3.4 | L1.05 | MemCo-B | B2604
R02583 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0032 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 63 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02584 | 2026-09-15 | Night | LYRA-4U | DVT | LYR-D-0039 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 129 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02585 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0010 | ST-07 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02586 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0006 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 243 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02587 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0026 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 64 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02588 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0040 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 63 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02589 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0030 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2637 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02590 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0019 | ST-02 | Memory | Memtest stress 12h | Pass |  | 700 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02591 | 2026-09-15 | Day | LYRA-4U | DVT | LYR-D-0003 | ST-03 | Memory | ECC injection | Pass |  | 789 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02592 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0052 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 256 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02593 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0051 | ST-06 | Memory | ECC injection | Pass |  | 788 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02594 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0032 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 2802 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02595 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0030 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 62 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02596 | 2026-09-16 | Night | ORION-2U | PVT | ORI-P-0034 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3063 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02597 | 2026-09-16 | Night | ORION-2U | PVT | ORI-P-0004 | ST-06 | Storage | FIO random R/W | Pass |  | 57 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02598 | 2026-09-16 | Night | ORION-2U | PVT | ORI-P-0005 | ST-10 | Memory | Memtest stress 12h | Pass |  | 649 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02599 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0032 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 61 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02600 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0054 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02601 | 2026-09-16 | Night | ORION-2U | PVT | ORI-P-0013 | ST-01 | BMC/Firmware | Redfish API check | Pass |  | 62 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02602 | 2026-09-16 | Day | ORION-2U | PVT | ORI-P-0033 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02603 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0006 | ST-03 | Memory | ECC injection | Pass |  | 687 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02604 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-02 | Network | Link flap test | Pass |  | 59 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02605 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0001 | ST-05 | Network | Link flap test | Pass |  | 56 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02606 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-09 | Memory | ECC injection | Pass |  | 700 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02607 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0030 | ST-03 | Network | Link flap test | Pass |  | 65 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02608 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-09 | Memory | ECC injection | Pass |  | 697 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02609 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0014 | ST-04 | Memory | ECC injection | Pass |  | 736 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02610 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0037 | ST-08 | Network | Link flap test | Pass |  | 56 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02611 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0013 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 65 | 23 | 2.3.4 | V1.05 | Dramtek | D2606
R02612 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0014 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02613 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-09 | Memory | ECC injection | Pass |  | 707 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02614 | 2026-09-16 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02615 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0008 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 195 | 35 | 2.3.4 | V1.05 | MemCo-B | B2607
R02616 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0029 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02617 | 2026-09-16 | Night | VEGA-1U | DVT | VEG-D-0007 | ST-09 | Storage | FIO random R/W | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02618 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0014 | ST-09 | Memory | Memtest stress 12h | Pass |  | 756 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02619 | 2026-09-16 | Night | LYRA-4U | DVT | LYR-D-0010 | ST-09 | PCIe/GPU | PCIe link training | Pass |  | 241 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02620 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0031 | ST-09 | Storage | FIO random R/W | Pass |  | 61 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02621 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0033 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 193 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02622 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0009 | ST-10 | Memory | ECC injection | Pass |  | 710 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02623 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0036 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 221 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02624 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0025 | ST-03 | Storage | NVMe hot-plug | Pass |  | 62 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02625 | 2026-09-16 | Night | LYRA-4U | DVT | LYR-D-0031 | ST-03 | Storage | NVMe hot-plug | Pass |  | 56 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02626 | 2026-09-16 | Night | LYRA-4U | DVT | LYR-D-0001 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 20 | 30 | 2.3.4 | L1.05 | MemCo-B | B2604
R02627 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0016 | ST-09 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02628 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0026 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02629 | 2026-09-16 | Day | LYRA-4U | DVT | LYR-D-0002 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 166 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02630 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0003 | ST-06 | Network | Link flap test | Pass |  | 59 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02631 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0042 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02632 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0013 | ST-10 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02633 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0014 | ST-08 | Network | NIC throughput 100G | Pass |  | 63 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02634 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0008 | ST-03 | Storage | NVMe hot-plug | Pass |  | 60 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02635 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0038 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02636 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0052 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 235 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02637 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0009 | ST-07 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02638 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0005 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 59 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02639 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0030 | ST-10 | Memory | Memtest stress 12h | Pass |  | 663 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02640 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0032 | ST-10 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02641 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0023 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2667 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02642 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0052 | ST-10 | Burn-in | Burn-in 48h | Pass |  | 3012 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02643 | 2026-09-17 | Night | ORION-2U | PVT | ORI-P-0054 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 64 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02644 | 2026-09-17 | Day | ORION-2U | PVT | ORI-P-0014 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2759 | 25 | 2.3.4 | O1.05 | MemCo-B | B2607
R02645 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0033 | ST-04 | Network | NIC throughput 100G | Fail | Throughput below spec | 16 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02646 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0007 | ST-09 | Network | NIC throughput 100G | Pass |  | 57 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02647 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0003 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02648 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-03 | BMC/Firmware | BMC FW update stress | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02649 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02650 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0038 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02651 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0023 | ST-07 | Memory | ECC injection | Pass |  | 722 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02652 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0002 | ST-10 | Memory | ECC injection | Pass |  | 717 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02653 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-05 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02654 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-03 | Network | NIC throughput 100G | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02655 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0020 | ST-04 | Network | Link flap test | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02656 | 2026-09-17 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 55 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02657 | 2026-09-17 | Night | VEGA-1U | DVT | VEG-D-0036 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02658 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0028 | ST-02 | Memory | Memtest stress 12h | Pass |  | 732 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02659 | 2026-09-17 | Night | LYRA-4U | DVT | LYR-D-0039 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02660 | 2026-09-17 | Night | LYRA-4U | DVT | LYR-D-0035 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 54 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02661 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0015 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 63 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02662 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0028 | ST-01 | Memory | Memtest stress 12h | Pass |  | 723 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02663 | 2026-09-17 | Night | LYRA-4U | DVT | LYR-D-0002 | ST-02 | Storage | FIO random R/W | Pass |  | 54 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02664 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0012 | ST-08 | Memory | ECC injection | Pass |  | 739 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02665 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0026 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02666 | 2026-09-17 | Day | LYRA-4U | DVT | LYR-D-0004 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 59 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02667 | 2026-09-18 | Night | ORION-2U | PVT | ORI-P-0003 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 220 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02668 | 2026-09-18 | Day | ORION-2U | PVT | ORI-P-0037 | ST-07 | Memory | ECC injection | Pass |  | 782 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02669 | 2026-09-18 | Day | ORION-2U | PVT | ORI-P-0046 | ST-10 | Storage | FIO random R/W | Pass |  | 59 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02670 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0005 | ST-06 | Memory | Memtest stress 12h | Pass |  | 657 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02671 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0028 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02672 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-10 | Network | Link flap test | Pass |  | 64 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02673 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-10 | BMC/Firmware | Redfish API check | Pass |  | 55 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02674 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0030 | TC-02 | Thermal | Thermal chamber | Pass |  | 183 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02675 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0034 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02676 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 245 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02677 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0014 | ST-02 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02678 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2968 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02679 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0025 | ST-03 | PCIe/GPU | GPU burn 24h | Pass |  | 234 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02680 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0014 | ST-08 | Memory | ECC injection | Pass |  | 702 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02681 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0001 | TC-02 | Thermal | Thermal chamber | Pass |  | 173 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02682 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0013 | ST-02 | Memory | Memtest stress 12h | Pass |  | 785 | 23 | 2.3.4 | V1.05 | Dramtek | D2606
R02683 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-02 | Memory | ECC injection | Pass |  | 752 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02684 | 2026-09-18 | Night | VEGA-1U | DVT | VEG-D-0033 | ST-10 | Network | NIC throughput 100G | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02685 | 2026-09-18 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-10 | Storage | NVMe hot-plug | Pass |  | 55 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02686 | 2026-09-18 | Day | LYRA-4U | DVT | LYR-D-0011 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02687 | 2026-09-18 | Night | LYRA-4U | DVT | LYR-D-0031 | ST-06 | Memory | ECC injection | Pass |  | 775 | 24 | 2.3.4 | L1.05 | Dramtek | D2606
R02688 | 2026-09-18 | Night | LYRA-4U | DVT | LYR-D-0016 | TC-02 | Thermal | Thermal chamber | Pass |  | 169 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02689 | 2026-09-18 | Day | LYRA-4U | DVT | LYR-D-0006 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 251 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02690 | 2026-09-18 | Day | LYRA-4U | DVT | LYR-D-0021 | ST-03 | Network | NIC throughput 100G | Pass |  | 54 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02691 | 2026-09-18 | Night | LYRA-4U | DVT | LYR-D-0017 | ST-04 | BMC/Firmware | Redfish API check | Pass |  | 57 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02692 | 2026-09-18 | Night | LYRA-4U | DVT | LYR-D-0011 | ST-02 | PCIe/GPU | PCIe link training | Pass |  | 224 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02693 | 2026-09-19 | Day | ORION-2U | PVT | ORI-P-0059 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 216 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02694 | 2026-09-19 | Day | ORION-2U | PVT | ORI-P-0050 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 2876 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02695 | 2026-09-19 | Day | ORION-2U | PVT | ORI-P-0010 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 58 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02696 | 2026-09-19 | Night | ORION-2U | PVT | ORI-P-0010 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02697 | 2026-09-19 | Day | ORION-2U | PVT | ORI-P-0004 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 258 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02698 | 2026-09-19 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-05 | Network | NIC throughput 100G | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02699 | 2026-09-19 | Day | VEGA-1U | DVT | VEG-D-0008 | ST-10 | Storage | NVMe hot-plug | Pass |  | 55 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02700 | 2026-09-19 | Night | VEGA-1U | DVT | VEG-D-0033 | ST-05 | Storage | FIO random R/W | Pass |  | 57 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02701 | 2026-09-19 | Night | VEGA-1U | DVT | VEG-D-0028 | ST-04 | Memory | ECC injection | Pass |  | 716 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02702 | 2026-09-19 | Night | VEGA-1U | DVT | VEG-D-0019 | ST-07 | Network | NIC throughput 100G | Pass |  | 57 | 24 | 2.3.4 | V1.05 | MemCo-A | A2607
R02703 | 2026-09-19 | Night | LYRA-4U | DVT | LYR-D-0038 | ST-05 | Storage | FIO random R/W | Pass |  | 62 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02704 | 2026-09-19 | Night | LYRA-4U | DVT | LYR-D-0008 | ST-06 | PCIe/GPU | GPU burn 24h | Pass |  | 224 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02705 | 2026-09-19 | Night | LYRA-4U | DVT | LYR-D-0014 | ST-03 | Network | NIC throughput 100G | Pass |  | 65 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02706 | 2026-09-19 | Day | LYRA-4U | DVT | LYR-D-0014 | TC-02 | Thermal | Thermal chamber | Pass |  | 170 | 30 | 2.3.4 | L1.05 | MemCo-B | B2604
R02707 | 2026-09-19 | Day | LYRA-4U | DVT | LYR-D-0017 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 174 | 30 | 2.3.4 | L1.05 | MemCo-B | B2607
R02708 | 2026-09-19 | Night | LYRA-4U | DVT | LYR-D-0001 | ST-04 | Burn-in | Burn-in 48h | Fail | Unexpected reboot | 1578 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02709 | 2026-09-19 | Day | LYRA-4U | DVT | LYR-D-0030 | TC-02 | Thermal | Thermal chamber | Pass |  | 187 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02710 | 2026-09-20 | Day | ORION-2U | PVT | ORI-P-0014 | ST-03 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 472 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02711 | 2026-09-20 | Day | ORION-2U | PVT | ORI-P-0032 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 232 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02712 | 2026-09-20 | Night | ORION-2U | PVT | ORI-P-0009 | ST-10 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 37 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02713 | 2026-09-20 | Day | ORION-2U | PVT | ORI-P-0042 | TC-01 | Thermal | Thermal chamber | Pass |  | 197 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02714 | 2026-09-20 | Night | ORION-2U | PVT | ORI-P-0029 | ST-09 | Memory | ECC injection | Pass |  | 723 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02715 | 2026-09-20 | Day | ORION-2U | PVT | ORI-P-0035 | ST-06 | Burn-in | Burn-in 48h | Pass |  | 3116 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02716 | 2026-09-20 | Day | ORION-2U | PVT | ORI-P-0017 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02717 | 2026-09-20 | Day | VEGA-1U | DVT | VEG-D-0012 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 184 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02718 | 2026-09-20 | Day | VEGA-1U | DVT | VEG-D-0032 | ST-02 | Network | Link flap test | Pass |  | 61 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02719 | 2026-09-20 | Day | VEGA-1U | DVT | VEG-D-0036 | ST-06 | Memory | ECC injection | Pass |  | 692 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02720 | 2026-09-20 | Night | VEGA-1U | DVT | VEG-D-0005 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2605 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02721 | 2026-09-20 | Day | VEGA-1U | DVT | VEG-D-0010 | ST-08 | Network | Link flap test | Pass |  | 64 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02722 | 2026-09-20 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-02 | Memory | Memtest stress 12h | Fail | DIMM not detected | 255 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02723 | 2026-09-20 | Day | LYRA-4U | DVT | LYR-D-0015 | ST-04 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02724 | 2026-09-20 | Night | LYRA-4U | DVT | LYR-D-0023 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2993 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02725 | 2026-09-20 | Night | LYRA-4U | DVT | LYR-D-0007 | ST-03 | BMC/Firmware | Redfish API check | Pass |  | 63 | 23 | 2.3.4 | L1.05 | MemCo-A | A2605
R02726 | 2026-09-20 | Night | LYRA-4U | DVT | LYR-D-0023 | ST-01 | Memory | ECC injection | Pass |  | 781 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02727 | 2026-09-20 | Day | LYRA-4U | DVT | LYR-D-0028 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 58 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02728 | 2026-09-20 | Night | LYRA-4U | DVT | LYR-D-0025 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 61 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02729 | 2026-09-20 | Day | LYRA-4U | DVT | LYR-D-0020 | ST-10 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02730 | 2026-09-21 | Day | ORION-2U | PVT | ORI-P-0024 | ST-10 | Storage | FIO random R/W | Pass |  | 60 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02731 | 2026-09-21 | Night | ORION-2U | PVT | ORI-P-0035 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 62 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02732 | 2026-09-21 | Day | ORION-2U | PVT | ORI-P-0014 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | O1.05 | MemCo-B | B2607
R02733 | 2026-09-21 | Night | ORION-2U | PVT | ORI-P-0026 | ST-06 | Network | NIC throughput 100G | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02734 | 2026-09-21 | Night | ORION-2U | PVT | ORI-P-0049 | ST-06 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 7 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02735 | 2026-09-21 | Day | ORION-2U | PVT | ORI-P-0057 | ST-09 | Memory | ECC injection | Pass |  | 738 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02736 | 2026-09-21 | Night | ORION-2U | PVT | ORI-P-0045 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 64 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02737 | 2026-09-21 | Day | ORION-2U | PVT | ORI-P-0027 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 194 | 35 | 2.3.4 | O1.05 | MemCo-A | A2605
R02738 | 2026-09-21 | Night | ORION-2U | PVT | ORI-P-0002 | ST-05 | Memory | ECC injection | Pass |  | 768 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02739 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0008 | TC-02 | Thermal | Thermal chamber | Pass |  | 177 | 30 | 2.3.4 | V1.05 | MemCo-B | B2607
R02740 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-07 | Network | NIC throughput 100G | Pass |  | 63 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02741 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0029 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02742 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0009 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 3000 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02743 | 2026-09-21 | Day | VEGA-1U | DVT | VEG-D-0020 | ST-08 | Burn-in | Burn-in 48h | Pass |  | 3006 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02744 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0004 | ST-04 | Power-on/POST | DC cycle 500x | Fail | No POST | 40 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02745 | 2026-09-21 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02746 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02747 | 2026-09-21 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 22 | 2.3.4 | V1.05 | MemCo-A | A2607
R02748 | 2026-09-21 | Day | VEGA-1U | DVT | VEG-D-0011 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 59 | 23 | 2.3.4 | V1.05 | MemCo-A | A2605
R02749 | 2026-09-21 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2676 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02750 | 2026-09-21 | Day | LYRA-4U | DVT | LYR-D-0001 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 182 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02751 | 2026-09-21 | Day | LYRA-4U | DVT | LYR-D-0020 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 169 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02752 | 2026-09-21 | Night | LYRA-4U | DVT | LYR-D-0018 | ST-07 | Memory | ECC injection | Pass |  | 770 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02753 | 2026-09-21 | Day | LYRA-4U | DVT | LYR-D-0003 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 218 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02754 | 2026-09-21 | Day | LYRA-4U | DVT | LYR-D-0014 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02755 | 2026-09-21 | Night | LYRA-4U | DVT | LYR-D-0025 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 220 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02756 | 2026-09-21 | Night | LYRA-4U | DVT | LYR-D-0037 | ST-05 | Storage | FIO random R/W | Pass |  | 55 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02757 | 2026-09-21 | Night | LYRA-4U | DVT | LYR-D-0027 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 59 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02758 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0004 | ST-07 | Storage | FIO random R/W | Pass |  | 54 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02759 | 2026-09-22 | Night | ORION-2U | PVT | ORI-P-0007 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 60 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02760 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0030 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 30 | 2.3.4 | O1.05 | MemCo-A | A2605
R02761 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0039 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02762 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0008 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 61 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02763 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0006 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 25 | 2.3.4 | O1.05 | MemCo-A | A2607
R02764 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0014 | ST-06 | Network | NIC throughput 100G | Pass |  | 59 | 23 | 2.3.4 | O1.05 | MemCo-B | B2607
R02765 | 2026-09-22 | Day | ORION-2U | PVT | ORI-P-0049 | ST-10 | Network | Link flap test | Pass |  | 57 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02766 | 2026-09-22 | Night | ORION-2U | PVT | ORI-P-0034 | ST-10 | Network | NIC throughput 100G | Pass |  | 61 | 22 | 2.3.4 | O1.05 | MemCo-B | B2607
R02767 | 2026-09-22 | Night | VEGA-1U | DVT | VEG-D-0037 | ST-04 | Network | NIC throughput 100G | Pass |  | 54 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02768 | 2026-09-22 | Night | VEGA-1U | DVT | VEG-D-0008 | ST-03 | Network | Link flap test | Pass |  | 54 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02769 | 2026-09-22 | Day | VEGA-1U | DVT | VEG-D-0016 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 165 | 30 | 2.3.4 | V1.05 | MemCo-A | A2605
R02770 | 2026-09-22 | Night | VEGA-1U | DVT | VEG-D-0024 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 163 | 30 | 2.3.4 | V1.05 | MemCo-A | A2607
R02771 | 2026-09-22 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-01 | Burn-in | Burn-in 48h | Pass |  | 2909 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02772 | 2026-09-22 | Day | VEGA-1U | DVT | VEG-D-0012 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 179 | 35 | 2.3.4 | V1.05 | MemCo-B | B2607
R02773 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0021 | ST-04 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02774 | 2026-09-22 | Night | LYRA-4U | DVT | LYR-D-0035 | ST-03 | PCIe/GPU | PCIe link training | Pass |  | 216 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02775 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0015 | ST-01 | Storage | FIO random R/W | Pass |  | 57 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02776 | 2026-09-22 | Night | LYRA-4U | DVT | LYR-D-0003 | ST-06 | BMC/Firmware | BMC FW update stress | Pass |  | 54 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02777 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0032 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02778 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0017 | ST-07 | PCIe/GPU | PCIe link training | Pass |  | 250 | 25 | 2.3.4 | L1.05 | MemCo-B | B2607
R02779 | 2026-09-22 | Night | LYRA-4U | DVT | LYR-D-0035 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 57 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02780 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0008 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 249 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02781 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 162 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02782 | 2026-09-22 | Night | LYRA-4U | DVT | LYR-D-0037 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 225 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02783 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0036 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 262 | 22 | 2.3.4 | L1.05 | Dramtek | D2606
R02784 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0011 | ST-06 | Network | NIC throughput 100G | Pass |  | 56 | 22 | 2.3.4 | L1.05 | MemCo-A | A2605
R02785 | 2026-09-22 | Day | LYRA-4U | DVT | LYR-D-0037 | TC-02 | Thermal | Fan redundancy (1 fan off) | Fail | GPU throttling | 44 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02786 | 2026-09-23 | Night | ORION-2U | PVT | ORI-P-0026 | ST-10 | Network | NIC throughput 100G | Pass |  | 62 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02787 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0040 | ST-04 | Burn-in | Burn-in 48h | Pass |  | 2886 | 24 | 2.3.4 | O1.05 | Dramtek | D2606
R02788 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0044 | ST-07 | Memory | ECC injection | Pass |  | 719 | 23 | 2.3.4 | O1.05 | MemCo-A | A2605
R02789 | 2026-09-23 | Night | ORION-2U | PVT | ORI-P-0055 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 220 | 25 | 2.3.4 | O1.05 | Dramtek | D2606
R02790 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0053 | ST-03 | Power-on/POST | AC cycle 500x | Pass |  | 57 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02791 | 2026-09-23 | Night | ORION-2U | PVT | ORI-P-0038 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 3018 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02792 | 2026-09-23 | Night | ORION-2U | PVT | ORI-P-0029 | TC-01 | Thermal | Thermal chamber | Pass |  | 187 | 30 | 2.3.4 | O1.05 | MemCo-A | A2607
R02793 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0010 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 223 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02794 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0046 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 175 | 30 | 2.3.4 | O1.05 | MemCo-A | A2605
R02795 | 2026-09-23 | Day | ORION-2U | PVT | ORI-P-0013 | ST-07 | Storage | NVMe hot-plug | Pass |  | 58 | 23 | 2.3.4 | O1.05 | MemCo-B | B2604
R02796 | 2026-09-23 | Day | VEGA-1U | DVT | VEG-D-0038 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 187 | 35 | 2.3.4 | V1.05 | MemCo-B | B2607
R02797 | 2026-09-23 | Night | VEGA-1U | DVT | VEG-D-0017 | ST-08 | BMC/Firmware | Redfish API check | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02798 | 2026-09-23 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-10 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02799 | 2026-09-23 | Night | VEGA-1U | DVT | VEG-D-0005 | ST-07 | Memory | Memtest stress 12h | Pass |  | 655 | 22 | 2.3.4 | V1.05 | MemCo-B | B2604
R02800 | 2026-09-23 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-07 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02801 | 2026-09-23 | Night | VEGA-1U | DVT | VEG-D-0032 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 54 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02802 | 2026-09-23 | Day | VEGA-1U | DVT | VEG-D-0018 | ST-05 | Memory | Memtest stress 12h | Pass |  | 758 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02803 | 2026-09-23 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-01 | Network | Link flap test | Pass |  | 58 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02804 | 2026-09-23 | Day | VEGA-1U | DVT | VEG-D-0023 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2595 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02805 | 2026-09-23 | Night | LYRA-4U | DVT | LYR-D-0036 | ST-03 | Storage | NVMe hot-plug | Pass |  | 64 | 25 | 2.3.4 | L1.05 | Dramtek | D2606
R02806 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0034 | TC-01 | Thermal | Thermal chamber | Fail | GPU throttling | 63 | 30 | 2.3.4 | L1.05 | MemCo-A | A2607
R02807 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0018 | ST-02 | Memory | Memtest stress 12h | Pass |  | 782 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02808 | 2026-09-23 | Night | LYRA-4U | DVT | LYR-D-0027 | ST-08 | PCIe/GPU | PCIe link training | Pass |  | 221 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02809 | 2026-09-23 | Night | LYRA-4U | DVT | LYR-D-0033 | ST-03 | Memory | ECC injection | Pass |  | 700 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02810 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0012 | ST-04 | Memory | ECC injection | Pass |  | 709 | 24 | 2.3.4 | L1.05 | MemCo-B | B2607
R02811 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0034 | ST-05 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02812 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0029 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 194 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02813 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0021 | ST-05 | BMC/Firmware | BMC FW update stress | Pass |  | 56 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02814 | 2026-09-23 | Night | LYRA-4U | DVT | LYR-D-0018 | ST-07 | PCIe/GPU | GPU burn 24h | Pass |  | 216 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02815 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0018 | ST-04 | PCIe/GPU | PCIe link training | Pass |  | 220 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02816 | 2026-09-23 | Day | LYRA-4U | DVT | LYR-D-0007 | ST-02 | PCIe/GPU | GPU burn 24h | Pass |  | 216 | 25 | 2.3.4 | L1.05 | MemCo-A | A2605
R02817 | 2026-09-24 | Night | ORION-2U | PVT | ORI-P-0038 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 56 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02818 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0015 | ST-05 | Network | NIC throughput 100G | Pass |  | 56 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02819 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0042 | ST-09 | Network | Link flap test | Pass |  | 64 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02820 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0013 | ST-02 | BMC/Firmware | Redfish API check | Pass |  | 56 | 25 | 2.3.4 | O1.05 | MemCo-B | B2604
R02821 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0026 | ST-03 | Storage | NVMe hot-plug | Fail | NVMe drive dropped after hot-plug | 37 | 22 | 2.3.4 | O1.05 | MemCo-A | A2605
R02822 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0026 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 62 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02823 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0058 | ST-05 | Burn-in | Burn-in 48h | Pass |  | 2677 | 24 | 2.3.4 | O1.05 | MemCo-B | B2604
R02824 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0019 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 186 | 35 | 2.3.4 | O1.05 | MemCo-B | B2607
R02825 | 2026-09-24 | Night | ORION-2U | PVT | ORI-P-0037 | ST-07 | Memory | Memtest stress 12h | Pass |  | 735 | 24 | 2.3.4 | O1.05 | MemCo-A | A2607
R02826 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0031 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 23 | 2.3.4 | O1.05 | Dramtek | D2606
R02827 | 2026-09-24 | Day | ORION-2U | PVT | ORI-P-0037 | ST-10 | Network | NIC throughput 100G | Pass |  | 59 | 22 | 2.3.4 | O1.05 | MemCo-A | A2607
R02828 | 2026-09-24 | Night | ORION-2U | PVT | ORI-P-0006 | ST-08 | Power-on/POST | DC cycle 500x | Fail | No POST | 37 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02829 | 2026-09-24 | Night | ORION-2U | PVT | ORI-P-0036 | ST-07 | Burn-in | Burn-in 48h | Pass |  | 2997 | 22 | 2.3.4 | O1.05 | MemCo-B | B2604
R02830 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0012 | ST-10 | Memory | Memtest stress 12h | Pass |  | 660 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02831 | 2026-09-24 | Night | VEGA-1U | DVT | VEG-D-0022 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 54 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02832 | 2026-09-24 | Night | VEGA-1U | DVT | VEG-D-0028 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 60 | 22 | 2.3.4 | V1.05 | MemCo-A | A2605
R02833 | 2026-09-24 | Night | VEGA-1U | DVT | VEG-D-0016 | ST-05 | Network | NIC throughput 100G | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-A | A2605
R02834 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0017 | ST-10 | Storage | NVMe hot-plug | Pass |  | 62 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02835 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0039 | ST-10 | Memory | Memtest stress 12h | Pass |  | 762 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02836 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-10 | Memory | ECC injection | Pass |  | 726 | 25 | 2.3.4 | V1.05 | MemCo-B | B2604
R02837 | 2026-09-24 | Night | VEGA-1U | DVT | VEG-D-0035 | ST-01 | BMC/Firmware | BMC FW update stress | Pass |  | 61 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02838 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-02 | Storage | NVMe hot-plug | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02839 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0035 | ST-08 | Memory | Memtest stress 12h | Fail | Correctable ECC errors over threshold | 474 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02840 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0024 | ST-06 | Storage | FIO random R/W | Pass |  | 54 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02841 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-01 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 23 | 2.3.4 | V1.05 | MemCo-B | B2607
R02842 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0034 | ST-10 | Memory | ECC injection | Pass |  | 766 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02843 | 2026-09-24 | Day | VEGA-1U | DVT | VEG-D-0009 | ST-02 | Burn-in | Burn-in 48h | Pass |  | 3106 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02844 | 2026-09-24 | Night | LYRA-4U | DVT | LYR-D-0033 | ST-02 | Power-on/POST | DC cycle 500x | Pass |  | 60 | 25 | 2.3.4 | L1.05 | MemCo-B | B2604
R02845 | 2026-09-24 | Night | LYRA-4U | DVT | LYR-D-0003 | ST-05 | Memory | Memtest stress 12h | Pass |  | 721 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02846 | 2026-09-24 | Night | LYRA-4U | DVT | LYR-D-0038 | ST-01 | Memory | ECC injection | Pass |  | 736 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02847 | 2026-09-24 | Day | LYRA-4U | DVT | LYR-D-0030 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 194 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02848 | 2026-09-24 | Day | LYRA-4U | DVT | LYR-D-0031 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 218 | 23 | 2.3.4 | L1.05 | Dramtek | D2606
R02849 | 2026-09-24 | Night | LYRA-4U | DVT | LYR-D-0003 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 192 | 35 | 2.3.4 | L1.05 | MemCo-B | B2604
R02850 | 2026-09-24 | Day | LYRA-4U | DVT | LYR-D-0035 | TC-01 | Thermal | Fan redundancy (1 fan off) | Pass |  | 194 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02851 | 2026-09-24 | Day | LYRA-4U | DVT | LYR-D-0006 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 242 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02852 | 2026-09-24 | Night | LYRA-4U | DVT | LYR-D-0033 | ST-04 | Memory | ECC injection | Pass |  | 703 | 23 | 2.3.4 | L1.05 | MemCo-B | B2604
R02853 | 2026-09-25 | Night | ORION-2U | PVT | ORI-P-0010 | ST-07 | Memory | ECC injection | Pass |  | 751 | 23 | 2.3.4 | O1.05 | MemCo-A | A2607
R02854 | 2026-09-25 | Day | ORION-2U | PVT | ORI-P-0033 | ST-02 | Network | NIC throughput 100G | Pass |  | 58 | 22 | 2.3.4 | O1.05 | Dramtek | D2606
R02855 | 2026-09-25 | Day | ORION-2U | PVT | ORI-P-0049 | ST-01 | Power-on/POST | AC cycle 500x | Pass |  | 59 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02856 | 2026-09-25 | Night | ORION-2U | PVT | ORI-P-0003 | ST-04 | Network | NIC throughput 100G | Pass |  | 61 | 25 | 2.3.4 | O1.05 | MemCo-A | A2605
R02857 | 2026-09-25 | Day | ORION-2U | PVT | ORI-P-0051 | ST-06 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 24 | 2.3.4 | O1.05 | MemCo-A | A2605
R02858 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0022 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 167 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02859 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0002 | ST-06 | BMC/Firmware | Redfish API check | Pass |  | 64 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02860 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0001 | ST-09 | Memory | Memtest stress 12h | Pass |  | 755 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02861 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0026 | ST-05 | Network | NIC throughput 100G | Pass |  | 58 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02862 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0021 | ST-09 | Power-on/POST | AC cycle 500x | Pass |  | 64 | 24 | 2.3.4 | V1.05 | MemCo-B | B2604
R02863 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0029 | ST-02 | Storage | FIO random R/W | Pass |  | 59 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02864 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0012 | ST-04 | Storage | FIO random R/W | Pass |  | 63 | 24 | 2.3.4 | V1.05 | MemCo-B | B2607
R02865 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0030 | ST-08 | Power-on/POST | DC cycle 500x | Pass |  | 56 | 24 | 2.3.4 | V1.05 | MemCo-A | A2605
R02866 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0026 | ST-09 | BMC/Firmware | Redfish API check | Pass |  | 61 | 23 | 2.3.4 | V1.05 | MemCo-A | A2607
R02867 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0027 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 65 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02868 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0014 | TC-02 | Thermal | Thermal chamber | Pass |  | 165 | 35 | 2.3.4 | V1.05 | MemCo-B | B2607
R02869 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0038 | ST-09 | Power-on/POST | DC cycle 500x | Pass |  | 58 | 22 | 2.3.4 | V1.05 | MemCo-B | B2607
R02870 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0040 | ST-02 | Network | Link flap test | Pass |  | 60 | 25 | 2.3.4 | V1.05 | MemCo-B | B2607
R02871 | 2026-09-25 | Day | VEGA-1U | DVT | VEG-D-0020 | ST-08 | PCIe/GPU | GPU burn 24h | Pass |  | 262 | 25 | 2.3.4 | V1.05 | MemCo-A | A2607
R02872 | 2026-09-25 | Night | VEGA-1U | DVT | VEG-D-0021 | ST-03 | Power-on/POST | DC cycle 500x | Pass |  | 62 | 23 | 2.3.4 | V1.05 | MemCo-B | B2604
R02873 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0013 | ST-10 | PCIe/GPU | GPU burn 24h | Pass |  | 246 | 23 | 2.3.4 | L1.05 | MemCo-A | A2607
R02874 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0012 | ST-04 | Power-on/POST | AC cycle 500x | Pass |  | 63 | 22 | 2.3.4 | L1.05 | MemCo-B | B2607
R02875 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0023 | ST-08 | Network | Link flap test | Pass |  | 60 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02876 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0006 | ST-09 | Burn-in | Burn-in 48h | Pass |  | 2895 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02877 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0023 | ST-06 | PCIe/GPU | PCIe link training | Pass |  | 233 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604
R02878 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0008 | TC-02 | Thermal | Thermal chamber | Fail | GPU throttling | 129 | 35 | 2.3.4 | L1.05 | MemCo-A | A2607
R02879 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0032 | ST-05 | PCIe/GPU | GPU burn 24h | Pass |  | 241 | 25 | 2.3.4 | L1.05 | MemCo-A | A2607
R02880 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0022 | ST-09 | PCIe/GPU | GPU burn 24h | Pass |  | 230 | 24 | 2.3.4 | L1.05 | MemCo-A | A2605
R02881 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0001 | ST-06 | BMC/Firmware | Redfish API check | Fail | Sensor reading missing | 32 | 24 | 2.3.4 | L1.05 | MemCo-B | B2604
R02882 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0020 | ST-04 | Memory | Memtest stress 12h | Pass |  | 713 | 22 | 2.3.4 | L1.05 | MemCo-A | A2607
R02883 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0013 | ST-06 | Power-on/POST | AC cycle 500x | Pass |  | 65 | 24 | 2.3.4 | L1.05 | MemCo-A | A2607
R02884 | 2026-09-25 | Day | LYRA-4U | DVT | LYR-D-0015 | TC-02 | Thermal | Fan redundancy (1 fan off) | Pass |  | 173 | 35 | 2.3.4 | L1.05 | MemCo-A | A2607
R02885 | 2026-09-25 | Night | LYRA-4U | DVT | LYR-D-0003 | ST-08 | Power-on/POST | AC cycle 500x | Pass |  | 61 | 22 | 2.3.4 | L1.05 | MemCo-B | B2604

## issue_log
Issue_ID | Run_ID | Open_Date | Project | Build_Stage | Test_Category | Symptom | Severity | Owner_Dept | Status | Close_Date | Root_Cause_Category | Root_Cause_Note
ISS-0001 | R00007 | 2026-06-01 | ORION-2U | EVT | Network | Throughput below spec | Minor |  | Closed | 2026-07-01 | No Fault Found | Could not reproduce
ISS-0002 | R00027 | 2026-06-03 | ORION-2U | EVT | Storage | IOPS below spec | Major | SQE | Closed | 2026-06-24 | Component | Replaced component; supplier FA requested
ISS-0003 | R00041 | 2026-06-04 | ORION-2U | EVT | Memory | Error not logged in SEL | Major | RD-BIOS | Closed | 2026-06-23 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0004 | R00042 | 2026-06-04 | ORION-2U | EVT | Burn-in | Unexpected reboot | Critical | ME | Closed | 2026-06-11 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0005 | R00060 | 2026-06-06 | ORION-2U | EVT | Thermal | Fan speed not responding | Minor | RD-BIOS | Closed | 2026-06-10 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0006 | R00071 | 2026-06-07 | ORION-2U | EVT | Memory | Correctable ECC errors over threshold | Major | RD-BIOS | Closed | 2026-06-12 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0007 | R00078 | 2026-06-08 | ORION-2U | EVT | Storage | IOPS below spec | Minor | RD-HW | Closed | 2026-06-14 | Design | Design change under review
ISS-0008 | R00104 | 2026-06-10 | ORION-2U | EVT | Storage | IOPS below spec | Major | RD-HW | Closed | 2026-06-14 | Design | Design change under review
ISS-0009 | R00106 | 2026-06-10 | ORION-2U | EVT | BMC/Firmware | Sensor reading missing | Major | RD-FW | Closed | 2026-06-13 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0010 | R00110 | 2026-06-10 | ORION-2U | EVT | PCIe/GPU | GPU fell off bus | Major | RD-HW | Closed | 2026-06-23 | Design | Design change under review
ISS-0011 | R00113 | 2026-06-11 | ORION-2U | EVT | Power-on/POST | No POST | Minor | RD-BIOS | Closed | 2026-06-30 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0012 | R00142 | 2026-06-15 | ORION-2U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Major | RD-HW | Closed | 2026-06-16 | Design | Design change under review
ISS-0013 | R00151 | 2026-06-15 | ORION-2U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Critical | RD-HW | Closed | 2026-07-03 | Design | Design change under review
ISS-0014 | R00160 | 2026-06-15 | VEGA-1U | EVT | Memory | Correctable ECC errors over threshold | Major | SQE | Closed | 2026-09-14 | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0015 | R00194 | 2026-06-17 | ORION-2U | EVT | Network | Throughput below spec | Minor | RD-HW | Closed | 2026-07-05 | Design | Design change under review
ISS-0016 | R00210 | 2026-06-17 | ORION-2U | EVT | BMC/Firmware | BMC unresponsive after update | Minor | ME | Closed | 2026-06-20 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0017 | R00214 | 2026-06-17 | ORION-2U | EVT | Storage | NVMe drive dropped after hot-plug | Minor | SQE | Closed | 2026-07-12 | Component | Replaced component; supplier FA requested
ISS-0018 | R00219 | 2026-06-17 | ORION-2U | EVT | Network | Link down | Major | Test Eng | Closed | 2026-06-25 | No Fault Found | Could not reproduce
ISS-0019 | R00236 | 2026-06-17 | VEGA-1U | EVT | Memory | Correctable ECC errors over threshold | Minor | RD-BIOS | Closed | 2026-06-21 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0020 | R00254 | 2026-06-18 | VEGA-1U | EVT | Power-on/POST | POST hang at code 0xB2 | Minor |  | Closed | 2026-07-09 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0021 | R00288 | 2026-06-20 | ORION-2U | EVT | Power-on/POST | System stuck in S5 | Major | RD-BIOS | Closed | 2026-06-23 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0022 | R00291 | 2026-06-20 | VEGA-1U | EVT | Network | Link down | Major | ME | Closed | 2026-06-23 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0023 | R00296 | 2026-06-20 | VEGA-1U | EVT | Burn-in | Kernel panic | Minor | Test Eng | Closed | 2026-08-07 | No Fault Found | Could not reproduce
ISS-0024 | R00309 | 2026-06-21 | VEGA-1U | EVT | Thermal | Fan speed not responding | Critical | ME | Closed | 2026-07-01 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0025 | R00311 | 2026-06-21 | VEGA-1U | EVT | Memory | Correctable ECC errors over threshold | Minor | ME | Closed | 2026-07-19 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0026 | R00314 | 2026-06-21 | VEGA-1U | EVT | Power-on/POST | No POST | Major | RD-HW | Closed | 2026-06-25 | Design | Design change under review
ISS-0027 | R00315 | 2026-06-21 | VEGA-1U | EVT | Power-on/POST | No POST | Major | SQE | Closed | 2026-07-06 | Component | Replaced component; supplier FA requested
ISS-0028 | R00326 | 2026-06-22 | ORION-2U | EVT | Memory | DIMM not detected | Major | RD-BIOS | Closed | 2026-07-11 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0029 | R00328 | 2026-06-22 | VEGA-1U | EVT | Network | Throughput below spec | Major | SQE | Closed | 2026-06-24 | Component | Replaced component; supplier FA requested
ISS-0030 | R00333 | 2026-06-22 | VEGA-1U | EVT | Thermal | CPU throttling | Major | SQE | Closed | 2026-07-18 | Component | Replaced component; supplier FA requested
ISS-0031 | R00338 | 2026-06-22 | VEGA-1U | EVT | Thermal | Fan speed not responding | Critical | RD-BIOS | Closed | 2026-06-29 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0032 | R00339 | 2026-06-22 | VEGA-1U | EVT | BMC/Firmware | BMC unresponsive after update | Critical | ME | Closed | 2026-07-03 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0033 | R00362 | 2026-06-24 | ORION-2U | EVT | Memory | DIMM not detected | Minor | SQE | Closed | 2026-07-09 | Component | Replaced component; supplier FA requested
ISS-0034 | R00364 | 2026-06-24 | ORION-2U | EVT | Storage | NVMe drive dropped after hot-plug | Minor | SQE | Closed | 2026-07-09 | Component | Replaced component; supplier FA requested
ISS-0035 | R00386 | 2026-06-25 | ORION-2U | EVT | Network | Link down | Critical | RD-HW | Closed | 2026-07-08 | Design | Design change under review
ISS-0036 | R00405 | 2026-06-26 | ORION-2U | EVT | Memory | Error not logged in SEL | Critical | ME | Closed | 2026-08-20 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0037 | R00411 | 2026-06-26 | VEGA-1U | EVT | Thermal | Fan speed not responding | Minor | Test Eng | Closed | 2026-07-07 | No Fault Found | Could not reproduce
ISS-0038 | R00479 | 2026-06-30 | ORION-2U | EVT | Thermal | Fan speed not responding | Major | Thermal | Closed | 2026-07-07 | Design | Design change under review
ISS-0039 | R00502 | 2026-06-30 | vega-1u | EVT | Burn-in | Kernel panic | Major | RD-BIOS | Closed | 2026-07-04 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0040 | R00519 | 2026-07-01 | VEGA-1U | EVT | Memory | Error not logged in SEL | Critical | SQE | Closed | 2026-07-07 | Component | Replaced component; supplier FA requested
ISS-0041 | R00521 | 2026-07-01 | VEGA-1U | EVT | Thermal | CPU throttling | Minor | RD-BIOS | Closed | 2026-07-06 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0042 | R00539 | 2026-07-01 | LYRA-4U | EVT | Memory | Error not logged in SEL | Major | RD-HW | Closed | 2026-07-17 | Design | Design change under review
ISS-0043 | R00552 | 2026-07-02 | ORION-2U | EVT | Storage | NVMe drive dropped after hot-plug | Major | RD-BIOS | Closed | 2026-07-09 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0044 | R00553 | 2026-07-02 | VEGA-1U | EVT | PCIe/GPU | GPU fell off bus | Major | ME | Closed | 2026-07-06 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0045 | R00590 | 2026-07-03 | VEGA-1U | EVT | Power-on/POST | POST hang at code 0xB2 | Critical | SQE | Closed | 2026-08-08 | Component | Replaced component; supplier FA requested
ISS-0046 | R00592 | 2026-07-03 | VEGA-1U | EVT | Storage | IOPS below spec | Major | Test Eng | Closed | 2026-07-15 | No Fault Found | Could not reproduce
ISS-0047 | R00609 | 2026-07-04 | VEGA-1U | EVT | Memory | Correctable ECC errors over threshold | Minor | ME | Closed | 2026-07-28 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0048 | R00640 | 2026-07-06 | ORION-2U | EVT | Burn-in | Kernel panic | Major | ME | Closed | 2026-07-18 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0049 | R00655 | 2026-07-06 | VEGA-1U | EVT | Power-on/POST | System stuck in S5 | Major | Test Eng | Closed | 2026-07-08 | No Fault Found | Could not reproduce
ISS-0050 | R00661 | 2026-07-06 | LYRA-4U | EVT | Power-on/POST | System stuck in S5 | Minor | RD-HW | Closed | 2026-07-16 | Design | Design change under review
ISS-0051 | R00663 | 2026-07-06 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0052 | R00673 | 2026-07-07 | VEGA-1U | EVT | Storage | IOPS below spec | Major | Test Eng | Closed | 2026-07-24 | No Fault Found | Could not reproduce
ISS-0053 | R00684 | 2026-07-07 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0054 | R00698 | 2026-07-08 | VEGA-1U | EVT | Memory | Correctable ECC errors over threshold | Major | SQE | Closed | 2026-09-23 | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0055 | R00715 | 2026-07-08 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0056 | R00730 | 2026-07-09 | VEGA-1U | EVT | Thermal | Fan speed not responding | Major | Thermal | Closed | 2026-07-29 | Design | Design change under review
ISS-0057 | R00743 | 2026-07-09 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0058 | R00745 | 2026-07-09 | LYRA-4U | EVT | PCIe/GPU | GPU fell off bus | Major | SQE | Closed | 2026-07-15 | Component | Replaced component; supplier FA requested
ISS-0059 | R00765 | 2026-07-10 | VEGA-1U | EVT | PCIe/GPU | GPU fell off bus | Minor | SQE | Closed | 2026-07-16 | Component | Replaced component; supplier FA requested
ISS-0060 | R00771 | 2026-07-10 | VEGA-1U | EVT | Storage | IOPS below spec | Major | RD-BIOS | Closed | 2026-07-18 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0061 | R00799 | 2026-07-11 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0062 | R00802 | 2026-07-11 | LYRA-4U | EVT | Power-on/POST | No POST | Major | SQE | Closed | 2026-07-17 | Component | Replaced component; supplier FA requested
ISS-0063 | R00809 | 2026-07-12 | VEGA-1U | EVT | BMC/Firmware | Sensor reading missing | Critical | RD-FW | Closed | 2026-07-25 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0064 | R00839 | 2026-07-13 | VEGA-1U | EVT | Thermal | CPU throttling | Critical | Thermal | Closed | 2026-07-27 | Design | Design change under review
ISS-0065 | R00853 | 2026-07-14 | ORION-2U | DVT | Memory | Error not logged in SEL | Major | RD-BIOS | Closed | 2026-07-26 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0066 | R00858 | 2026-07-14 | ORION-2U | DVT | Thermal | CPU throttling | Major | Test Eng | Closed | 2026-07-21 | No Fault Found | Could not reproduce
ISS-0067 | R00864 | 2026-07-14 | VEGA-1U | EVT | Power-on/POST | No POST | Minor | SQE | Closed | 2026-07-23 | Component | Replaced component; supplier FA requested
ISS-0068 | R00872 | 2026-07-14 | LYRA-4U | EVT | Burn-in | Kernel panic | Critical | RD-HW | Closed | 2026-07-29 | Design | Design change under review
ISS-0069 | R00875 | 2026-07-14 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0070 | R00881 | 2026-07-15 | ORION-2U | DVT | Memory | Error not logged in SEL | Minor | ME | Closed | 2026-07-27 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0071 | R00895 | 2026-07-15 | LYRA-4U | EVT | Memory | Correctable ECC errors over threshold | Major | RD-BIOS | Closed | 2026-07-25 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0072 | R00904 | 2026-07-15 | LYRA-4U | EVT | Memory | DIMM not detected | Critical | ME | Closed | 2026-07-30 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0073 | R00907 | 2026-07-16 | ORION-2U | DVT | Memory | Error not logged in SEL | Minor | Test Eng | Closed | 2026-07-23 | No Fault Found | Could not reproduce
ISS-0074 | R00910 | 2026-07-16 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-29 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0075 | R00919 | 2026-07-16 | ORION-2U | DVT | Memory | Error not logged in SEL | Major | SQE | Closed | 2026-07-24 | Component | Replaced component; supplier FA requested
ISS-0076 | R00945 | 2026-07-17 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-25 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0077 | R00949 | 2026-07-17 | ORION-2U | DVT | Memory | Error not logged in SEL | Critical | RD-BIOS | Closed | 2026-07-25 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0078 | R00950 | 2026-07-17 | ORION-2U | DVT | Thermal | Fan speed not responding | Minor | SQE | Closed | 2026-07-20 | Component | Replaced component; supplier FA requested
ISS-0079 | R00954 | 2026-07-17 | VEGA-1U | EVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-28 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0080 | R00961 | 2026-07-17 | VEGA-1U | EVT | Burn-in | Unexpected reboot | Minor | ME | Closed | 2026-07-25 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0081 | R00966 | 2026-07-17 | LYRA-4U | EVT | PCIe/GPU | GPU fell off bus | Minor | ME | Closed | 2026-07-19 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0082 | R00975 | 2026-07-18 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-23 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0083 | R00986 | 2026-07-18 | LYRA-4U | EVT | Power-on/POST | No POST | Minor | SQE | Closed | 2026-07-29 | Component | Replaced component; supplier FA requested
ISS-0084 | R00992 | 2026-07-18 | LYRA-4U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-29 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0085 | R00996 | 2026-07-19 | ORION-2U | DVT | Storage | NVMe drive dropped after hot-plug | Minor | Test Eng | Closed | 2026-07-30 | No Fault Found | Could not reproduce
ISS-0086 | R01004 | 2026-07-19 | VEGA-1U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-25 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0087 | R01013 | 2026-07-20 | ORION-2U | DVT | Network | Link down | Minor | RD-HW | Closed | 2026-07-26 | Design | Design change under review
ISS-0088 | R01016 | 2026-07-20 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-BIOS | Closed | 2026-07-24 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0089 | R01028 | 2026-07-20 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0090 | R01044 | 2026-07-20 | LYRA-4U | EVT | BMC/Firmware | Sensor reading missing | Major | SQE | Closed | 2026-07-29 | Component | Replaced component; supplier FA requested
ISS-0091 | R01053 | 2026-07-21 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0092 | R01062 | 2026-07-21 | VEGA-1U | EVT | Burn-in | Kernel panic | Minor | RD-BIOS | Closed | 2026-07-25 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0093 | R01065 | 2026-07-21 | VEGA-1U | EVT | Burn-in | Unexpected reboot | Major | RD-BIOS | Closed | 2026-07-28 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0094 | R01067 | 2026-07-21 | VEGA-1U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-28 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0095 | R01072 | 2026-07-21 | lyra-4u | EVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-07-23 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0096 | R01095 | 2026-07-22 | VEGA-1U | EVT | BMC/Firmware | Sensor reading missing | Major | ME | Closed | 2026-08-04 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0097 | R01106 | 2026-07-23 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0098 | R01125 | 2026-07-23 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0099 | R01133 | 2026-07-23 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0100 | R01135 | 2026-07-24 | ORION-2U | DVT | Network | Link down | Minor | Test Eng | Closed | 2026-07-25 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0101 | R01146 | 2026-07-24 | VEGA-1U | EVT | Storage | IOPS below spec | Minor | ME | Closed | 2026-08-03 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0102 | R01153 | 2026-07-24 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0103 | R01154 | 2026-07-24 | LYRA-4U | EVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-07-27 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0104 | R01161 | 2026-07-25 | ORION-2U | DVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-07-30 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0105 | R01167 | 2026-07-25 | VEGA-1U | EVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-07-26 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0106 | R01176 | 2026-07-25 | LYRA-4U | EVT | Power-on/POST | No POST | Minor | Test Eng | Closed | 2026-07-29 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0107 | R01188 | 2026-07-26 | VEGA-1U | EVT | Network | Link down | Major | ME | Closed | 2026-07-31 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0108 | R01192 | 2026-07-26 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0109 | R01194 | 2026-07-26 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0110 | R01205 | 2026-07-27 | ORION-2U | DVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-07-28 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0111 | R01211 | 2026-07-27 | VEGA-1U | EVT | PCIe/GPU | GPU fell off bus | Minor | RD-BIOS | Closed | 2026-08-03 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0112 | R01224 | 2026-07-27 | LYRA-4U | EVT | PCIe/GPU | GPU fell off bus | Minor | ME | Closed | 2026-08-07 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0113 | R01225 | 2026-07-27 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0114 | R01228 | 2026-07-27 | LYRA-4U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-29 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0115 | R01232 | 2026-07-27 | LYRA-4U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0116 | R01234 | 2026-07-28 | ORION-2U | DVT | Power-on/POST | POST hang at code 0xB2 | Major | SQE | Closed | 2026-08-08 | Component | Replaced component; supplier FA requested
ISS-0117 | R01255 | 2026-07-28 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0118 | R01283 | 2026-07-29 | LYRA-4U | EVT | Network | Link down | Major | Test Eng | Closed | 2026-07-31 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0119 | R01293 | 2026-07-30 | ORION-2U | DVT | BMC/Firmware | BMC unresponsive after update | Critical | RD-HW | Closed | 2026-08-06 | Design | Design change under review
ISS-0120 | R01294 | 2026-07-30 | ORION-2U | DVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Minor | Test Eng | Closed | 2026-08-01 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0121 | R01299 | 2026-07-30 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0122 | R01301 | 2026-07-30 | VEGA-1U | EVT | Power-on/POST | No POST | Minor | Test Eng | Closed | 2026-08-02 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0123 | R01302 | 2026-07-30 | VEGA-1U | EVT | Network | Link down | Major | RD-HW | Closed | 2026-08-24 | Design | Design change under review
ISS-0124 | R01305 | 2026-07-30 | VEGA-1U | EVT | BMC/Firmware | BMC unresponsive after update | Major | ME | Closed | 2026-08-10 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0125 | R01321 | 2026-07-30 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0126 | R01325 | 2026-07-30 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0127 | R01337 | 2026-07-31 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-29 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0128 | R01339 | 2026-07-31 | ORION-2U | DVT | BMC/Firmware | BMC unresponsive after update | Major | RD-FW | Closed | 2026-08-11 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0129 | R01340 | 2026-07-31 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0130 | R01350 | 2026-07-31 | VEGA-1U | EVT | Network | Throughput below spec | Major | ME | Closed | 2026-08-01 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0131 | R01371 | 2026-07-31 | LYRA-4U | EVT | Power-on/POST | POST hang at code 0xB2 | Minor | RD-HW | Closed | 2026-08-06 | Design | Design change under review
ISS-0132 | R01385 | 2026-08-01 | VEGA-1U | DVT | Burn-in | Unexpected reboot | Major | Test Eng | Closed | 2026-08-05 | No Fault Found | Could not reproduce
ISS-0133 | R01406 | 2026-08-02 | LYRA-4U | EVT | Network | Link down | Major | Test Eng | Closed | 2026-08-04 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0134 | R01428 | 2026-08-03 | VEGA-1U | DVT | Network | Link down | Major | Test Eng | Closed | 2026-08-05 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0135 | R01432 | 2026-08-03 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0136 | R01441 | 2026-08-03 | LYRA-4U | EVT | Power-on/POST | No POST | Minor | RD-BIOS | Closed | 2026-08-11 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0137 | R01466 | 2026-08-04 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0138 | R01490 | 2026-08-05 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0139 | R01492 | 2026-08-05 | VEGA-1U | DVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-08-09 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0140 | R01496 | 2026-08-05 | VEGA-1U | DVT | BMC/Firmware | Sensor reading missing | Minor | Test Eng | Closed | 2026-08-14 | No Fault Found | Could not reproduce
ISS-0141 | R01498 | 2026-08-05 | VEGA-1U | DVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-08-06 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0142 | R01501 | 2026-08-05 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0143 | R01505 | 2026-08-05 | LYRA-4U | EVT | Burn-in | Unexpected reboot | Minor | RD-BIOS | Closed | 2026-08-08 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0144 | R01521 | 2026-08-06 | ORION-2U | DVT | Power-on/POST | No POST | Minor | Test Eng | Closed | 2026-08-11 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0145 | R01528 | 2026-08-06 | ORION-2U | DVT | Storage | NVMe drive dropped after hot-plug | Minor | Test Eng | Closed | 2026-08-16 | No Fault Found | Could not reproduce
ISS-0146 | R01553 | 2026-08-07 | ORION-2U | DVT | Memory | Error not logged in SEL | Major | RD-HW | Closed | 2026-08-11 | Design | Design change under review
ISS-0147 | R01563 | 2026-08-07 | VEGA-1U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-28 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0148 | R01564 | 2026-08-07 | VEGA-1U | DVT | Storage | NVMe drive dropped after hot-plug | Major | SQE | Closed | 2026-08-14 | Component | Replaced component; supplier FA requested
ISS-0149 | R01567 | 2026-08-07 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0150 | R01570 | 2026-08-07 | LYRA-4U | EVT | BMC/Firmware | Sensor reading missing | Minor | SQE | Closed | 2026-08-13 | Component | Replaced component; supplier FA requested
ISS-0151 | R01574 | 2026-08-07 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0152 | R01582 | 2026-08-08 | vega-1u | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-29 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0153 | R01586 | 2026-08-08 | VEGA-1U | DVT | Burn-in | Kernel panic | Major | SQE | Closed | 2026-08-26 | Component | Replaced component; supplier FA requested
ISS-0154 | R01605 | 2026-08-09 | VEGA-1U | DVT | Power-on/POST | No POST | Major | Test Eng | Closed | 2026-08-11 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0155 | R01619 | 2026-08-10 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0156 | R01637 | 2026-08-10 | VEGA-1U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-23 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0157 | R01643 | 2026-08-10 | LYRA-4U | EVT | PCIe/GPU | GPU fell off bus | Major | Test Eng | Closed | 2026-08-14 | No Fault Found | Could not reproduce
ISS-0158 | R01644 | 2026-08-10 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0159 | R01652 | 2026-08-11 | ORION-2U | DVT | Power-on/POST | POST hang at code 0xB2 | Major | RD-BIOS | Closed | 2026-08-19 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0160 | R01653 | 2026-08-11 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0161 | R01659 | 2026-08-11 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | Closed | 2026-09-23 | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0162 | R01660 | 2026-08-11 | LYRA-4U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Major | Test Eng | Closed | 2026-08-12 | No Fault Found | Retest passed on another station; could not reproduce
ISS-0163 | R01665 | 2026-08-12 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0164 | R01675 | 2026-08-12 | VEGA-1U | DVT | Network | Link down | Major | Test Eng | Closed | 2026-08-17 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0165 | R01692 | 2026-08-13 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-26 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0166 | R01694 | 2026-08-13 | ORION-2U | DVT | Burn-in | Kernel panic | Major | RD-HW | Closed | 2026-08-19 | Design | Design change under review
ISS-0167 | R01697 | 2026-08-13 | ORION-2U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-28 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0168 | R01711 | 2026-08-13 | LYRA-4U | EVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-28 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0169 | R01720 | 2026-08-14 | ORION-2U | DVT | Network | Link down | Major | SQE | Closed | 2026-08-16 | Component | Replaced component; supplier FA requested
ISS-0170 | R01728 | 2026-08-14 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0171 | R01735 | 2026-08-14 | LYRA-4U | EVT | Thermal | Fan speed not responding | Minor | Test Eng | Closed | 2026-08-23 | No Fault Found | Could not reproduce
ISS-0172 | R01738 | 2026-08-14 | LYRA-4U | EVT | Power-on/POST | No POST | Minor | Test Eng | Closed | 2026-08-16 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0173 | R01740 | 2026-08-14 | LYRA-4U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Major | Test Eng | Closed | 2026-08-17 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0174 | R01748 | 2026-08-15 | ORION-2U | DVT | Burn-in | Unexpected reboot | Minor | RD-HW | Closed | 2026-08-29 | Design | Design change under review
ISS-0175 | R01758 | 2026-08-15 | VEGA-1U | DVT | Thermal | Fan speed not responding | Critical | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0176 | R01767 | 2026-08-15 | LYRA-4U | EVT | Power-on/POST | No POST | Minor | RD-BIOS | Closed | 2026-08-26 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0177 | R01783 | 2026-08-16 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0178 | R01795 | 2026-08-17 | VEGA-1U | DVT | THERMAL | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0179 | R01817 | 2026-08-18 | ORION-2U | DVT | Thermal | Fan speed not responding | Major | RD-FW | Closed | 2026-08-24 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0180 | R01829 | 2026-08-18 | VEGA-1U | DVT | BMC/Firmware | BMC unresponsive after update | Minor | RD-HW | Closed | 2026-08-24 | Design | Design change under review
ISS-0181 | R01831 | 2026-08-18 | VEGA-1U | DVT | Network | Link down | Major | Test Eng | Closed | 2026-08-22 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0182 | R01867 | 2026-08-19 | LYRA-4U | EVT | Storage | IOPS below spec | Minor | ME | Closed | 2026-08-23 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0183 | R01884 | 2026-08-20 | VEGA-1U | DVT | Thermal | Fan speed not responding | Major |  | Closed | 2026-08-25 | Firmware/BIOS | BMC 2.3.1 fan table not loaded after AC cycle; fixed in 2.3.4
ISS-0184 | R01886 | 2026-08-20 | LYRA-4U | EVT | BMC/Firmware | Sensor reading missing | Major | SQE | Closed | 2026-08-30 | Component | Replaced component; supplier FA requested
ISS-0185 | R01903 | 2026-08-21 | ORION-2U | DVT | Power-on/POST | No POST | Critical | Test Eng | Closed | 2026-09-04 | No Fault Found | Could not reproduce
ISS-0186 | R01921 | 2026-08-21 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0187 | R01928 | 2026-08-21 | LYRA-4U | EVT | Network | Link down | Major | Test Eng | Closed | 2026-08-22 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0188 | R01939 | 2026-08-22 | VEGA-1U | DVT | Storage | NVMe drive dropped after hot-plug | Major | RD-BIOS | Closed | 2026-08-28 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0189 | R01969 | 2026-08-24 | ORION-2U | DVT | Storage | IOPS below spec | Major | RD-HW | Closed | 2026-09-06 | Design | Design change under review
ISS-0190 | R01985 | 2026-08-24 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0191 | R01993 | 2026-08-24 | LYRA-4U | EVT | Memory | Error not logged in SEL | Minor | SQE | Closed | 2026-08-30 | Component | Replaced component; supplier FA requested
ISS-0192 | R02009 | 2026-08-25 | VEGA-1U | DVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Minor | Test Eng | Closed | 2026-08-30 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0193 | R02015 | 2026-08-25 | LYRA-4U | EVT | Network | Link down | Minor | Test Eng | Closed | 2026-08-26 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0194 | R02022 | 2026-08-25 | LYRA-4U | EVT | Power-on/POST | System stuck in S5 | Major | RD-BIOS | Closed | 2026-09-02 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0195 | R02044 | 2026-08-26 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | Open |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0196 | R02049 | 2026-08-26 | LYRA-4U | EVT | Burn-in | Kernel panic | Minor | RD-HW | Closed | 2026-09-01 | Design | Design change under review
ISS-0197 | R02060 | 2026-08-27 | ORION-2U | DVT | Power-on/POST | No POST | Critical | RD-BIOS | Closed | 2026-09-08 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0198 | R02085 | 2026-08-27 | LYRA-4U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Major | Test Eng | Closed | 2026-09-01 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0199 | R02094 | 2026-08-28 | ORION-2U | DVT | Thermal | Fan speed not responding | Minor | Thermal | Closed | 2026-09-07 | Design | Design change under review
ISS-0200 | R02101 | 2026-08-28 | ORION-2U | DVT | PCIE/GPU | Link trained at Gen4 instead of Gen5 | Minor | Test Eng | Closed | 2026-08-31 | Test Setup/Fixture | Worn high-speed cable on ST-07; retest on other station passed
ISS-0201 | R02111 | 2026-08-28 | VEGA-1U | DVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Critical | ME | Closed | 2026-09-13 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0202 | R02121 | 2026-08-28 | LYRA-4U | EVT | BMC/Firmware | BMC unresponsive after update | Major | RD-FW | Closed | 2026-09-07 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0203 | R02129 | 2026-08-29 | ORION-2U | DVT | Memory | Error not logged in SEL | Minor | Test Eng | Closed | 2026-09-07 | No Fault Found | Could not reproduce
ISS-0204 | R02141 | 2026-08-29 | LYRA-4U | EVT | Network | Link down | Minor | RD-BIOS | Closed | 2026-09-08 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0205 | R02152 | 2026-08-30 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0206 | R02163 | 2026-08-31 | ORION-2U | DVT | Memory | DIMM not detected | Minor | SQE | Closed | 2026-09-06 | Component | Replaced component; supplier FA requested
ISS-0207 | R02176 | 2026-08-31 | LYRA-4U | EVT | Memory | Correctable ECC errors over threshold | Major | SQE | Open |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0208 | R02183 | 2026-09-01 | ORION-2U | PVT | Storage | NVMe drive dropped after hot-plug | Major | Test Eng | Closed | 2026-09-11 | No Fault Found | Could not reproduce
ISS-0209 | R02206 | 2026-09-01 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0210 | R02220 | 2026-09-02 | VEGA-1U | DVT | Power-on/POST | No POST | Major | RD-HW | Closed | 2026-09-09 | Design | Design change under review
ISS-0211 | R02227 | 2026-09-02 | LYRA-4U | EVT | Network | Link down | Major | ME | Closed | 2026-09-06 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0212 | R02228 | 2026-09-02 | lyra-4u | EVT | Power-on/POST | No POST | Critical | Test Eng | Closed | 2026-09-06 | No Fault Found | Could not reproduce
ISS-0213 | R02235 | 2026-09-02 | LYRA-4U | EVT | Memory | Error not logged in SEL | Major | Test Eng | In Progress |  | No Fault Found | Could not reproduce
ISS-0214 | R02254 | 2026-09-03 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0215 | R02273 | 2026-09-04 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | Open |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0216 | R02292 | 2026-09-05 | VEGA-1U | DVT | PCIe/GPU | GPU fell off bus | Major | SQE | Closed | 2026-09-15 | Component | Replaced component; supplier FA requested
ISS-0217 | R02332 | 2026-09-07 | vega-1u | DVT | Memory | Correctable ECC errors over threshold | Minor | RD-BIOS | Closed | 2026-09-17 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0218 | R02343 | 2026-09-07 | VEGA-1U | DVT | Memory | Error not logged in SEL | Minor | RD-HW | Closed | 2026-09-24 | Design | Design change under review
ISS-0219 | R02355 | 2026-09-07 | LYRA-4U | EVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0220 | R02366 | 2026-09-08 | ORION-2U | PVT | Memory | Correctable ECC errors over threshold | Major | SQE | Open |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0221 | R02395 | 2026-09-08 | LYRA-4U | EVT | Storage | IOPS below spec | Minor | RD-BIOS | Closed | 2026-09-25 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0222 | R02412 | 2026-09-09 | VEGA-1U | DVT | Burn-in | Unexpected reboot | Minor | RD-HW | Closed | 2026-09-13 | Design | Design change under review
ISS-0223 | R02415 | 2026-09-09 | LYRA-4U | EVT | Network | Throughput below spec | Major | ME | Closed | 2026-09-16 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0224 | R02417 | 2026-09-09 | LYRA-4U | EVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Minor | SQE | Closed | 2026-09-16 | Component | Replaced component; supplier FA requested
ISS-0225 | R02423 | 2026-09-09 | LYRA-4U | EVT | Power-on/POST | POST hang at code 0xB2 | Minor | RD-BIOS | Closed | 2026-09-12 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0226 | R02427 | 2026-09-09 | LYRA-4U | EVT | Memory | Error not logged in SEL | Minor | ME | Closed | 2026-09-13 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0227 | R02447 | 2026-09-10 | ORION-2U | PVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0228 | R02464 | 2026-09-10 | LYRA-4U | EVT | Memory | Correctable ECC errors over threshold | Minor | ME | Closed | 2026-09-21 | Assembly/Process | Cable routing / torque issue at assembly
ISS-0229 | R02465 | 2026-09-10 | LYRA-4U | EVT | Burn-in | Kernel panic | Major | RD-BIOS | Closed | 2026-09-23 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0230 | R02484 | 2026-09-11 | VEGA-1U | DVT | Storage | NVMe drive dropped after hot-plug | Minor | Test Eng | Closed | 2026-09-25 | No Fault Found | Could not reproduce
ISS-0231 | R02522 | 2026-09-13 | VEGA-1U | DVT | PCIe/GPU | Link trained at Gen4 instead of Gen5 | Critical | Test Eng | In Progress |  | No Fault Found | Could not reproduce
ISS-0232 | R02533 | 2026-09-13 | LYRA-4U | DVT | Power-on/POST | System stuck in S5 | Major | RD-BIOS | Closed | 2026-09-18 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0233 | R02573 | 2026-09-15 | VEGA-1U | DVT | Storage | NVMe drive dropped after hot-plug | Minor | RD-BIOS | Closed | 2026-09-22 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0234 | R02584 | 2026-09-15 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0235 | R02626 | 2026-09-16 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0236 | R02645 | 2026-09-17 | VEGA-1U | DVT | Network | Throughput below spec | Major | SQE | Closed | 2026-09-21 | Component | Replaced component; supplier FA requested
ISS-0237 | R02660 | 2026-09-17 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0238 | R02708 | 2026-09-19 | LYRA-4U | DVT | Burn-in | Unexpected reboot | Major | RD-BIOS | Closed | 2026-09-24 | Firmware/BIOS | Fixed in next BIOS/BMC drop
ISS-0239 | R02710 | 2026-09-20 | ORION-2U | PVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0240 | R02712 | 2026-09-20 | ORION-2U | PVT | BMC/Firmware | Sensor reading missing | Critical | SQE | In Progress |  | Under Analysis
ISS-0241 | R02722 | 2026-09-20 | VEGA-1U | DVT | Memory | DIMM not detected | Minor | SQE | In Progress |  | Under Analysis
ISS-0242 | R02734 | 2026-09-21 | ORION-2U | PVT | Storage | NVMe drive dropped after hot-plug | Critical | Test Eng | Open |  | Under Analysis
ISS-0243 | R02744 | 2026-09-21 | VEGA-1U | DVT | Power-on/POST | No POST | Minor | Test Eng | In Progress |  | Under Analysis
ISS-0244 | R02785 | 2026-09-22 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0245 | R02806 | 2026-09-23 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0246 | R02821 | 2026-09-24 | ORION-2U | PVT | Storage | NVMe drive dropped after hot-plug | Major | RD-BIOS | Open |  | Under Analysis
ISS-0247 | R02828 | 2026-09-24 | ORION-2U | PVT | Power-on/POST | No POST | Minor | SQE | In Progress |  | Under Analysis
ISS-0248 | R02839 | 2026-09-24 | VEGA-1U | DVT | Memory | Correctable ECC errors over threshold | Major | SQE | In Progress |  | Component | DIMM lot B2607 marginal; supplier 8D requested, lot quarantined 2026-09-08
ISS-0249 | R02878 | 2026-09-25 | LYRA-4U | DVT | Thermal | GPU throttling | Critical | Thermal | In Progress |  | Design | GPU heatsink airflow insufficient at >=30C ambient; new shroud in evaluation
ISS-0250 | R02881 | 2026-09-25 | LYRA-4U | DVT | BMC/Firmware | Sensor reading missing | Major | RD-FW | In Progress |  | Under Analysis

## thermal_log
Run_ID | Max_CPU_Temp_C | Max_GPU_Temp_C | Avg_Fan_Duty_pct | CPU_Throttle | GPU_Throttle
R00004 | 74.9 |  | 82.5 | N
R00008 | 68.5 |  | 68.4 | N
R00009 | 70.6 |  | 89.1 | N
R00029 | 78.4 |  | 83.4 | N
R00030 | 81.2 |  | 86.1 | N
R00032 | 68.3 |  | 66.9 | N
R00039 | 77.2 |  | 82.1 | N
R00043 | 71.8 |  | 77.7 | N
R00053 | 66.9 |  | 69.2 | N
R00060 | 75.2 |  | 76.3 | N
R00062 | 85.5 |  | 87.7 | N
R00080 | 81.3 |  | 86.6 | N
R00086 | 75.3 |  | 84.4 | N
R00090 | 70.2 |  | 72.4 | N
R00091 | 72.3 |  | 70.7 | N
R00094 | 72.3 |  | 81.3 | N
R00096 | 71.7 |  | 85.6 | N
R00100 | 60.4 |  | 70.2 | N
R00103 | 67.2 |  | 76.2 | N
R00105 | 75.9 |  | 81 | N
R00107 | 57.2 |  | 57.7 | N
R00117 | 65.1 |  | 72.1 | N
R00125 | 74.1 |  | 74 | N
R00132 | 64.8 |  | 72.1 | N
R00134 | 76.7 |  | 86.1 | N
R00136 | 78.3 |  | 81.9 | N
R00170 | 70.9 |  | 55.7 | N
R00173 | 63.5 |  | 57.1 | N
R00192 | 63.8 |  | 80.7 | N
R00198 | 78.1 |  | 88.6 | N
R00201 | 73 |  | 85.2 | N
R00207 | 70.7 |  | 72 | N
R00212 | 71.1 |  | 75 | N
R00232 | 67.9 |  | 79.3 | N
R00261 | 69.6 |  | 75 | N
R00271 | 77.6 |  | 82.1 | N
R00274 | 67.5 |  | 65.6 | N
R00280 | 78.7 |  | 79.2 | N
R00309 | 65.7 |  | 72.6 | N
R00333 | 79.6 |  | 65.9 | N
R00334 | 60 |  | 65.4 | N
R00336 | 72.3 |  | 82.3 | N
R00338 | 65.5 |  | 71.2 | N
R00354 | 75.9 |  | 85 | N
R00366 | 64.3 |  | 74.3 | N
R00368 | 82.4 |  | 86 | N
R00372 | 68 |  | 65.8 | N
R00376 | 63.9 |  | 63.1 | N
R00378 | 64.6 |  | 74.5 | N
R00380 | 66.1 |  | 65.5 | N
R00381 | 61.6 |  | 70.1 | N
R00382 | 71.2 |  | 63.3 | N
R00384 | 63.4 |  | 72.7 | N
R00395 | 76.8 |  | 77 | N
R00396 | 72.5 |  | 64.7 | N
R00403 | 80.4 |  | 88.4 | N
R00404 | 73.2 |  | 86.7 | N
R00411 | 72.4 |  | 70.2 | N
R00422 | 63.6 |  | 56.3 | N
R00430 | 72 |  | 67.3 | N
R00433 | 80.2 |  | 71.5 | N
R00438 | 79.4 |  | 87.2 | N
R00443 | 66.8 |  | 74.7 | N
R00451 | 63.7 |  | 74 | N
R00452 | 66.9 |  | 58.5 | N
R00459 | 73.4 |  | 85.6 | N
R00460 | 77.5 |  | 82.1 | N
R00461 | 63.6 |  | 64 | N
R00475 | 62.2 |  | 66.5 | N
R00479 | 60.3 |  | 60.1 | N
R00487 | 73.2 |  | 72.6 | N
R00521 | 81.9 |  | 78.6 | N
R00534 | 76.4 | 77.8 | 73.2 | N | N
R00536 | 72.4 | 86.7 | 72.2 | N | N
R00547 | 71.3 |  | 73 | N
R00557 | 75.2 |  | 72.6 | N
R00565 | 81.6 | 85.7 | 85.2 | N | N
R00572 | 72.6 |  | 72.8 | N
R00578 | 82.1 |  | 83.6 | N
R00599 | 74.5 |  | 88.8 | N
R00604 | 68.9 |  | 64.1 | N
R00633 | 69.2 | 69.7 | 67.6 | N | N
R00645 | 57.4 |  | 55.8 | N
R00647 | 63.9 |  | 59.3 | N
R00662 | 78.2 | 87.2 | 86.5 | N | Y
R00663 | 72 | 89.5 | 81.8 | N | Y
R00666 | 72.1 |  | 78.8 | N
R00667 | 61.9 |  | 74.7 | N
R00672 | 79.4 |  | 80.6 | N
R00684 | 67.9 | 87.9 | 74.4 | N | Y
R00686 | 74.3 | 83.2 | 84.1 | N | N
R00706 | 79.2 |  | 80.4 | N
R00709 | 75 | 77.1 | 82 | N | N
R00715 | 76.1 | 88.9 | 71.3 | N | Y
R00726 | 69.6 |  | 78.8 | N
R00728 | 65.6 |  | 74.1 | N
R00730 | 73.7 |  | 82.1 | N
R00740 | 59 | 70 | 69.5 | N | N
R00741 | 75 | 82.2 | 69.3 | N | N
R00742 | 63.5 | 72.2 | 68.8 | N | N
R00743 | 78.9 | 87.6 | 74.7 | N | Y
R00760 | 57.2 |  | 71.5 | N
R00772 | 73.2 |  | 89.9 | N
R00783 | 81 | 84.4 | 88.6 | N | N
R00793 | 72.5 |  | 76 | N
R00797 | 66 | 71.5 | 64.1 | N | N
R00799 | 70.1 | 89 | 74.1 | N | Y
R00806 | 83 |  | 74.2 | N
R00807 | 68.4 |  | 56.8 | N
R00808 | 70.9 |  | 67.1 | N
R00814 | 63.1 |  | 62.4 | N
R00815 | 67.9 |  | 65.9 | N
R00819 | 74 | 78.9 | 79.2 | N | N
R00824 | 74.8 |  | 69.1 | N
R00830 | 64.1 |  | 69.3 | N
R00837 | 67.7 |  | 66.2 | N
R00839 | 79.1 |  | 74.9 | N
R00848 | 66.1 | 68.5 | 57 | N | N
R00852 | 69.6 |  | 72.9 | N
R00857 | 75.9 |  | 72.7 | N
R00858 | 83.7 |  | 80.9 | N
R00868 | 63.2 |  | 66.5 | N
R00873 | 73.8 | 77.3 | 68.9 | N | N
R00875 | 77.7 | 88.1 | 70.9 | N | Y
R00888 | 63.6 |  | 73.5 | N
R00894 | 60.6 | 71.3 | 64.2 | N | N
R00896 | 68 | 71.8 | 64 | N | N
R00905 | 62.8 | 72 | 68.8 | N | N
R00908 | 72.4 |  | 75.9 | N
R00910 | 84 |  | 29.5 | N
R00913 | 72 |  | 80.2 | N
R00914 | 77.1 |  | 88 | N
R00921 | 76.7 |  | 75.3 | N
R00928 | 72.6 |  | 70.2 | N
R00945 | 102.1 |  | 28.2 | Y
R00948 | 78.7 |  | 85.8 | N
R00950 | 67 |  | 69.6 | N
R00951 | 81.3 |  | 77 | N
R00954 | 85.6 |  | 33.1 | N
R00955 | 77.3 |  | 66.2 | N
R00963 | 77.7 |  | 86.1 | N
R00967 | 68.4 | 74.3 | 73 | N | N
R00968 | 79.7 | 85.1 | 81.5 | N | N
R00971 | 62.4 |  | 57.2 | N
R00975 | 86.1 |  | 31.3 | N
R00992 | 87.7 | 95.6 | 31.6 | N | Y
R01004 | 91 |  | 28.9 | N
R01014 | 81.6 |  | 80.6 | N
R01016 | 67.9 |  | 67.2 | N
R01020 | 80.2 |  | 70.4 | N
R01025 | 69.1 |  | 64.7 | N
R01027 | 70.3 |  | 85.5 | N
R01028 | 101 |  | 29.8 | Y
R01031 | 76.3 |  | 67.8 | N
R01032 | 66.3 |  | 73.8 | N
R01037 | 61.8 |  | 57.6 | N
R01051 | 75.3 |  | 78.2 | N
R01053 | 90.8 |  | 31.9 | N
R01060 | 80.8 |  | 73.6 | N
R01067 | 95.4 |  | 31.4 | Y
R01083 | 78.5 |  | 75 | N
R01086 | 77 |  | 82.4 | N
R01087 | 64.2 |  | 72.5 | N
R01089 | 67.4 |  | 77.5 | N
R01104 | 68.3 | 72.5 | 69.7 | N | N
R01106 | 100.4 |  | 33.7 | Y
R01114 | 69.5 |  | 76.8 | N
R01117 | 73.4 |  | 70.5 | N
R01125 | 80.1 | 89.8 | 81 | N | Y
R01126 | 70.5 | 80.6 | 80.3 | N | N
R01133 | 79 | 88.7 | 86 | N | Y
R01136 | 63 |  | 73.6 | N
R01138 | 64.2 |  | 79.9 | N
R01147 | 70.5 |  | 81 | N
R01148 | 67.8 |  | 63.4 | N
R01153 | 75.6 | 88.1 | 73.2 | N | Y
R01157 | 63.1 |  | 80.2 | N
R01158 | 70.1 |  | 81.8 | N
R01159 | 70.7 |  | 58.6 | N
R01163 | 62.4 |  | 69.6 | N
R01165 | 70 |  | 72.9 | N
R01171 | 66.6 | 66.9 | 57.3 | N | N
R01179 | 72.7 |  | 72.5 | N
R01189 | 68 |  | 73 | N
R01190 | 65.6 |  | 67.3 | N
R01192 | 65.5 | 89.9 | 79.7 | N | Y
R01194 | 69.2 | 89.4 | 87.1 | N | Y
R01199 | 63.9 |  | 59 | N
R01201 | 64.8 |  | 66.6 | N
R01213 | 81.4 |  | 70 | N
R01220 | 80.9 |  | 80 | N
R01221 | 73.1 |  | 82.2 | N
R01225 | 66.9 | 87.6 | 78.9 | N | Y
R01228 | 89 | 99.1 | 28.9 | N | Y
R01230 | 73.1 | 78 | 68.6 | N | N
R01232 | 81.6 | 85.7 | 32.7 | N | N
R01237 | 70.2 |  | 72.9 | N
R01241 | 75.9 |  | 82.2 | N
R01250 | 64.7 | 68.2 | 73.5 | N | N
R01255 | 81.6 | 89.3 | 85 | N | Y
R01256 | 68.2 | 67.7 | 68.4 | N | N
R01261 | 59.3 |  | 67.6 | N
R01264 | 71.9 |  | 62.6 | N
R01266 | 70.6 |  | 66.3 | N
R01280 | 63.4 | 70.8 | 55.6 | N | N
R01291 | 73.8 |  | 67.5 | N
R01299 | 93.8 |  | 28 | N
R01303 | 65.5 |  | 68.7 | N
R01310 | 68.8 |  | 65.5 | N
R01321 | 70.1 | 88.6 | 69.2 | N | Y
R01322 | 74.9 | 78.3 | 79.2 | N | N
R01325 | 71.6 | 88 | 73.9 | N | Y
R01326 | 66.6 | 71.5 | 59.1 | N | N
R01333 | 64 |  | 73.2 | N
R01337 | 77.6 |  | 30.7 | N
R01340 | 87 |  | 28.4 | N
R01341 | 65.8 |  | 74.7 | N
R01345 | 61.6 |  | 60.6 | N
R01346 | 68.5 |  | 73.1 | N
R01348 | 66.1 |  | 79.2 | N
R01355 | 66.6 |  | 72.1 | N
R01361 | 78.7 |  | 82.4 | N
R01375 | 75 | 83.2 | 78.1 | N | N
R01407 | 71.4 | 83.6 | 89.1 | N | N
R01418 | 77.6 |  | 86.4 | N
R01420 | 67.9 |  | 75.4 | N
R01433 | 73 |  | 76.6 | N
R01442 | 65.4 |  | 67.1 | N
R01452 | 58.9 |  | 70.3 | N
R01462 | 76.1 |  | 70 | N
R01466 | 72.9 | 89.4 | 79.6 | N | Y
R01480 | 72.9 |  | 65.7 | N
R01501 | 72.4 | 89.6 | 77.1 | N | Y
R01503 | 62.3 | 69.9 | 59.4 | N | N
R01509 | 84.2 | 88.5 | 85.9 | N | Y
R01519 | 70.7 |  | 68.3 | N
R01523 | 81.1 |  | 79.4 | N
R01525 | 59.4 |  | 64.8 | N
R01536 | 63.8 |  | 80.2 | N
R01541 | 71.5 | 79.2 | 74.1 | N | N
R01563 | 95.5 |  | 28.4 | Y
R01565 | 73.2 |  | 70.3 | N
R01567 | 73.1 | 88.2 | 70.1 | N | Y
R01574 | 73.1 | 88.7 | 70.6 | N | Y
R01577 | 70.4 |  | 55.3 | N
R01581 | 72.8 |  | 81.1 | N
R01582 | 92.7 |  | 30.4 | N
R01583 | 69.5 |  | 60.7 | N
R01590 | 77.6 |  | 86.5 | N
R01609 | 70 |  | 72.3 | N
R01619 | 83.1 |  | 31.9 | N
R01632 | 65.2 |  | 55.8 | N
R01633 | 72.8 |  | 82.6 | N
R01635 | 80.1 |  | 73.1 | N
R01636 | 69 |  | 65.9 | N
R01637 | 97.6 |  | 28.5 | Y
R01644 | 74.6 | 88.3 | 70.8 | N | Y
R01645 | 78.3 | 81.7 | 87.3 | N | N
R01647 | 72.5 |  | 65.1 | N
R01653 | 94.7 |  | 33.4 | N
R01665 | 80.3 |  | 33.9 | N
R01670 | 69.5 |  | 72.9 | N
R01677 | 65.7 |  | 57.3 | N
R01678 | 60.4 |  | 71.5 | N
R01692 | 89 |  | 29 | N
R01695 | 73.8 |  | 84.7 | N
R01697 | 75.1 |  | 29.2 | N
R01711 | 96.3 | 103.6 | 29.9 | Y | Y
R01726 | 72.8 |  | 79.2 | N
R01732 | 72.4 |  | 74.4 | N
R01735 | 66.6 | 75.2 | 69 | N | N
R01742 | 68 | 76.3 | 81.3 | N | N
R01746 | 69.5 | 79.5 | 71.8 | N | N
R01749 | 74 |  | 62.9 | N
R01758 | 88.7 |  | 30.8 | N
R01762 | 60.4 | 69.3 | 68 | N | N
R01769 | 69.8 | 78.2 | 63.6 | N | N
R01778 | 71 |  | 78.5 | N
R01780 | 61.3 |  | 64.8 | N
R01781 | 61.8 |  | 70.3 | N
R01783 | 72.5 | 87.6 | 79 | N | Y
R01794 | 81.2 |  | 79.8 | N
R01795 | 98.8 |  | 33.4 | Y
R01796 | 84.5 |  | 78.1 | N
R01798 | 80.3 |  | 88 | N
R01800 | 70.8 |  | 71 | N
R01811 | 81.3 |  | 86.3 | N
R01817 | 86.9 |  | 33.4 | N
R01830 | 66.8 |  | 67.9 | N
R01832 | 66 |  | 75 | N
R01840 | 66.1 |  | 64.6 | N
R01849 | 85.1 |  | 86 | N
R01852 | 73.8 |  | 71.3 | N
R01859 | 79.7 |  | 73.3 | N
R01872 | 77.1 |  | 63.8 | N
R01884 | 90.6 |  | 31.7 | N
R01896 | 73.9 |  | 68 | N
R01909 | 61.6 |  | 60.8 | N
R01918 | 63.6 |  | 56 | N
R01921 | 73.5 | 88.2 | 81.6 | N | Y
R01934 | 66.7 | 68.2 | 55 | N | N
R01944 | 68.2 |  | 72.1 | N
R01946 | 65.4 |  | 71.8 | N
R01951 | 69.5 |  | 74 | N
R01957 | 65.1 |  | 56 | N
R01962 | 72 | 88.1 | 84 | N | Y
R01964 | 79.3 |  | 84.5 | N
R01978 | 67.5 |  | 60.5 | N
R01980 | 69.1 |  | 71.8 | N
R01981 | 68.2 |  | 67.7 | N
R01984 | 71.8 |  | 75.2 | N
R01985 | 75.7 | 87.5 | 73.2 | N | Y
R01986 | 73.8 | 85.7 | 72.7 | N | N
R01987 | 69.9 | 72.1 | 59.4 | N | N
R01990 | 75.9 | 81.2 | 76.7 | N | N
R02000 | 74 |  | 72 | N
R02025 | 74.9 |  | 66.7 | N
R02028 | 73.6 |  | 79.5 | N
R02029 | 81.1 |  | 85.5 | N
R02032 | 64.9 |  | 64.6 | N
R02033 | 61 |  | 55.6 | N
R02034 | 69.7 |  | 64.6 | N
R02036 | 83.8 |  | 83.5 | N
R02046 | 74.6 |  | 71.7 | N
R02052 | 64.4 | 68.1 | 60.5 | N | N
R02054 | 66.2 | 77 | 78 | N | N
R02056 | 70.2 | 77.2 | 66.8 | N | N
R02062 | 74.5 |  | 70.8 | N
R02081 | 64.6 | 70.3 | 63.3 | N | N
R02094 | 64.7 |  | 68.4 | N
R02100 | 78.4 |  | 83.2 | N
R02105 | 64.5 |  | 60 | N
R02115 | 75.5 |  | 77 | N
R02118 | 74.6 | 83.3 | 78.6 | N | N
R02126 | 70.1 |  | 64.6 | N
R02127 | 77.1 |  | 85.1 | N
R02135 | 76.2 |  | 73.6 | N
R02138 | 60.1 | 69.1 | 63.9 | N | N
R02151 | 67.2 |  | 72.3 | N
R02152 | 73.2 | 87.9 | 81.4 | N | Y
R02154 | 83.8 | 84.8 | 70.5 | N | N
R02158 | 76.5 |  | 85.8 | N
R02172 | 66 |  | 64.2 | N
R02181 | 67 | 73.6 | 74.7 | N | N
R02188 | 69.3 |  | 68.5 | N
R02189 | 71.5 |  | 73.5 | N
R02196 | 69.3 | 73.7 | 65.3 | N | N
R02202 | 67.6 | 80.3 | 65.4 | N | N
R02206 | 73.7 | 88.1 | 82.4 | N | Y
R02208 | 73.8 |  | 67.3 | N
R02209 | 58.3 |  | 57.4 | N
R02211 | 80.6 |  | 74.3 | N
R02215 | 66.6 |  | 79.8 | N
R02254 | 80.9 | 90 | 84.2 | N | Y
R02261 | 74.5 |  | 64.6 | N
R02275 | 66.4 |  | 63.1 | N
R02286 | 77.9 |  | 70.8 | N
R02299 | 61.9 | 71 | 65.8 | N | N
R02300 | 67.5 |  | 55.2 | N
R02311 | 67.2 | 77.9 | 76.8 | N | N
R02325 | 78.6 |  | 88 | N
R02328 | 81.1 |  | 85.3 | N
R02336 | 72.1 |  | 73.5 | N
R02344 | 66.7 |  | 83.9 | N
R02346 | 66.1 | 77.6 | 73.2 | N | N
R02352 | 74.3 | 89.5 | 86 | N | Y
R02353 | 63.3 | 70.1 | 67 | N | N
R02354 | 59.6 | 70.9 | 69.5 | N | N
R02355 | 79.9 | 88.4 | 74.5 | N | Y
R02356 | 78.6 |  | 72.3 | N
R02363 | 65.8 |  | 68.8 | N
R02374 | 69.5 |  | 62.7 | N
R02388 | 66.6 | 79 | 82.1 | N | N
R02405 | 68.6 |  | 64.7 | N
R02406 | 71.5 |  | 66.3 | N
R02428 | 64.1 | 69.3 | 58.1 | N | N
R02432 | 74.3 |  | 81.4 | N
R02434 | 75.8 |  | 79.1 | N
R02443 | 70.9 |  | 70.3 | N
R02445 | 74.3 |  | 63.1 | N
R02454 | 66.8 |  | 58.5 | N
R02470 | 73.2 |  | 75.3 | N
R02475 | 71.3 |  | 78.7 | N
R02480 | 67 |  | 64.8 | N
R02497 | 73.7 |  | 90 | N
R02507 | 62.6 |  | 78.5 | N
R02539 | 67 |  | 56.2 | N
R02544 | 63.1 |  | 59 | N
R02548 | 76.5 | 86 | 75.1 | N | N
R02555 | 66.1 |  | 55.7 | N
R02556 | 67.3 |  | 80.6 | N
R02560 | 69.9 |  | 56.9 | N
R02561 | 70.1 |  | 83.7 | N
R02564 | 61.5 |  | 67 | N
R02582 | 75.3 | 80.7 | 64.1 | N | N
R02584 | 67.4 | 89 | 76.1 | N | Y
R02615 | 77.8 |  | 72.9 | N
R02621 | 80 | 88.3 | 77.2 | N | Y
R02626 | 68.1 | 87.6 | 71.9 | N | Y
R02629 | 68.8 | 72.8 | 74.1 | N | N
R02631 | 69.6 |  | 65.4 | N
R02660 | 75.8 | 88.1 | 70 | N | Y
R02665 | 67.3 | 71.1 | 67.6 | N | N
R02674 | 62.3 |  | 61.3 | N
R02681 | 66.2 |  | 60.8 | N
R02688 | 64.5 | 78.5 | 68.2 | N | N
R02706 | 68.2 | 78.4 | 65.6 | N | N
R02707 | 77.5 | 77.4 | 65.1 | N | N
R02709 | 61.8 | 74.8 | 58.2 | N | N
R02713 | 59.4 |  | 70.3 | N
R02717 | 73 |  | 60.8 | N
R02737 | 75.9 |  | 74.4 | N
R02739 | 67 |  | 62.6 | N
R02750 | 72.2 | 70.7 | 55.4 | N | N
R02751 | 65.9 | 72.8 | 68.2 | N | N
R02760 | 74 |  | 69.1 | N
R02769 | 74.9 |  | 71.5 | N
R02770 | 71.2 |  | 77.4 | N
R02772 | 81.9 |  | 72.6 | N
R02781 | 81.2 | 75 | 63.9 | N | N
R02785 | 83.1 | 89.4 | 79.8 | N | Y
R02792 | 67.2 |  | 66.7 | N
R02794 | 70.9 |  | 77 | N
R02796 | 83.8 |  | 88.5 | N
R02806 | 66.7 | 88.9 | 76.8 | N | Y
R02812 | 64.4 | 72 | 66.6 | N | N
R02824 | 80.1 |  | 86.3 | N
R02847 | 67.9 | 70.9 | 59.5 | N | N
R02849 | 82.9 | 85.1 | 81.3 | N | N
R02850 | 65.7 | 68.8 | 61.2 | N | N
R02858 | 66.7 |  | 55.5 | N
R02868 | 74 |  | 80.6 | N
R02878 | 74.6 | 89.4 | 83.6 | N | Y
R02884 | 76.7 | 81.4 | 74.8 | N | N

## schedule
Project | Build_Stage | Planned_Start | Planned_End | Actual_Start | Actual_End | Exit_Criteria | PM_Note
ORION-2U | EVT | 2026-06-01 | 2026-07-10 | 2026-06-01 | 2026-07-10 | 0 open Critical issues; test pass rate >= 85%
ORION-2U | DVT | 2026-07-11 | 2026-08-20 | 2026-07-11 | 2026-08-31 | 0 open Critical issues; test pass rate >= 92% | Exit approved by PM head
ORION-2U | PVT | 2026-08-21 | 2026-10-09 | 2026-09-01 |  | 0 open Critical issues; test pass rate >= 97%
VEGA-1U | EVT | 2026-06-15 | 2026-07-31 | 2026-06-15 | 2026-07-31 | 0 open Critical issues; test pass rate >= 85%
VEGA-1U | DVT | 2026-08-01 | 2026-09-15 | 2026-08-01 |  | 0 open Critical issues; test pass rate >= 92% | Exit review postponed
VEGA-1U | PVT | 2026-09-16 | 2026-10-30 |  |  | 0 open Critical issues; test pass rate >= 97%
LYRA-4U | EVT | 2026-07-01 | 2026-08-25 | 2026-07-01 | 2026-09-10 | 0 open Critical issues; test pass rate >= 85% | Exited on waiver; GPU thermal issue carried into DVT
LYRA-4U | DVT | 2026-08-26 | 2026-10-15 | 2026-09-11 |  | 0 open Critical issues; test pass rate >= 92%
LYRA-4U | PVT | 2026-10-16 | 2026-11-30 |  |  | 0 open Critical issues; test pass rate >= 97%